## Tasks
| Name | Duration | Start | Finish | Cost | Unique ID Successors | Unique ID Predecessors | Unique ID | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01
0 | SimpleRiskRegister | 210 | 2011-11-03 | 2012-08-22 | 2365248 |  |  | 0
1 | Design | #N/A | 2011-11-03 | 2012-01-25 | 336000 | 2 |  | 1
2 | Construction | #N/A | 2012-01-26 | 2012-07-11 | 1909248 | 3 | 1 | 2
3 | Cleanup | #N/A | 2012-07-12 | 2012-08-22 | 120000 | 4 | 2 | 3
4 | Project Complete | 0 | 2012-08-22 | 2012-08-22 | 0 |  | 3 | 4

## Resources
| Resource Name | Initials | Group | Max. Units | Std. Rate | Ovt. Rate | Cost/Use | Accrue At | Base Calendar | Code | @RISK: Functions | ID
1 | Design Team | D |  | 100% | 500 | 0 | 0 | Prorated | Standard |  |  | 1
2 | Construction Team | C |  | 100% | 1000 | 0 | 0 | Prorated | Standard |  |  | 2
3 | Cleanup Team | C |  | 100% | 300 | 0 | 0 | Prorated | Standard |  |  | 3
4 | Management | M |  | 100% | 200 | 0 | 0 | Prorated | Standard |  |  | 4

## RiskSerializationData (hidden)
1 | 0
0
0 | TRUE | 0 | 1 | GF1_rK0qDwEAEADuAAwjACYAXQB1AIkAigCYAKYAyADqAOQAKgD//wAAAAAAAQQAAAAAKV8oKiAjLCMjMF8pO18oKiAoIywjIzApO18oKiAiLSI/P18pO18oQF8pAAAAARJEYXlzIGFkZGVkIHRvIHBsYW4BAAEBEAACAAEKU3RhdGlzdGljcwMBAQD/AQEBAQEAAQEBAAQAAAABAQEBAQABAQEABAAAAAGqAAIaABJEYXlzIGFkZGVkIHRvIHBsYW4AAC8BAAIAAgDQANoAAQECAZqZmZmZmak/AABmZmZmZmbuPwAABQABAQEAAQEBAA== | 1 | 0 | 0 | >75% | <25% | >90% | 0 | 3 | 1 | FALSE | TRUE | 0 | FALSE | #NAME?
0
FALSE | 15680 | 7345 | 41920 | 0
FALSE | 15680 | 7345 | 41920 | 0
FALSE | 15680 | 7345 | 41920 | 0
FALSE | 15680 | 7345 | 41920 | 0
FALSE | 15680 | 7345 | 41920 | 0
0
0 | FALSE | FALSE | 10 | 0.95 | 1

## Risk Register
SIMPLE RISK REGISTER
[5 empty] | Schedule Impacts (days) | [5 empty] | Cost Impacts ($)
Risk | Probability |  | Simulated Occurrence | Occurs? | Min | Most Likely | Max | Mean | Simulated Schedule Impact | Days added to plan | Min | Most Likely | Max | Mean | Simulated Cost Impact | Costs added to plan | Date when Costs added to plan | Risk Functions for Delays and Costs
R1 - Customer Design Approval Risk | 40% | 60% | 0 | No | 15 | 20 | 30 | 8.3333 | 20.8333 | 0 | 25000 | 50000 | 75000 | 20000 | 50000 | 0 | 0 | FALSE
R2 - Enviromental Risk | 20% | 80% | 0 | No | 15 | 30 | 45 | 6 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R3 - Material Price Risk | 50% | 50% | 0 | No | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 100000 | 200000 | 58333.3333 | 116666.6667 | 0 | 2012-03-17 | 0
[5 empty] | 30 | 50 | 75 | 14.3333
[10 empty] | 0 | [5 empty] | 0
| Event formula |  | % of times | How many times
Risk R1 occurred | 0 |  | 0% | #N/A
Risk R1 occurred without R2 or R3 | 0 |  | 0% | #N/A
Risks R1 and R2 occurred | 0 |  | 0% | #N/A
Risk R1 or R2 occurred | 0 |  | 0% | #N/A
Risks R1 and R2 occurred without R3 | 0 |  | 0% | #N/A
Risks R1, R2, and R3 occurred | 0 |  | 0% | #N/A
Risk R3 occurred without R1 or R2 | 0 |  | 0% | #N/A
RUN A SIMULATION TO SEE THE FIGURES.
EXPLANATION: Cells D5, D6, D7 are 0 if a risk does not occur, and 1 if the risk does occur. Cells B11:B17 have logic for the risk or combination of risks you're interested in tracking. In any particular iteration, cells B11:B17 are 1 if the indicated event occurred, and 0 if it did not. To construct logic for combinations of risks in B11:B17, multiply the ones you're interested in. For instance, "R1 and R2 occurred" is (D5>0)*(D6>0), but "R1 and R2 without R3" is (D5>0)*(D6>0)*(D7=0). For a simple risk, as opposed to a combination, add a 0, as was done in cell B11; that makes the cell display as 0 or 1 like the others. To find the total number of occurrences, there's no RiskSum() function, so take RiskMean() in D11:D17 and multiply by the number of iterations to get the number of occurrences in E11:E17. More at http://kb.palisade.com/index.php?pg=kb.page&id=1508

## Sheet1 (hidden)
| Name | Deterministic Start | Deterministic Finish
0 | SimpleRiskRegister | 2011-11-03 | 2012-08-22
1 | Design | 2011-11-03 | 2012-01-25
2 | Construction | 2012-01-26 | 2012-07-11
3 | Cleanup | 2012-07-12 | 2012-08-22
4 | Project Complete | 2012-08-22 | 2012-08-22

## RiskCritStatData1 (hidden)
Simple Risk Register.mpp 0 | Simple Risk Register.mpp 0 | Simple Risk Register.mpp 0 | Simple Risk Register.mpp 1 | Simple Risk Register.mpp 1 | Simple Risk Register.mpp 1 | Simple Risk Register.mpp 2 | Simple Risk Register.mpp 2 | Simple Risk Register.mpp 2 | Simple Risk Register.mpp 3 | Simple Risk Register.mpp 3 | Simple Risk Register.mpp 3 | Simple Risk Register.mpp 4 | Simple Risk Register.mpp 4 | Simple Risk Register.mpp 4
40850.3333 | 41190.6917 | 0 | 40850.3333 | 40928.3569 | 1 | 40928.3569 | 41081.4569 | 1 | 41081.4569 | 41165.6618 | 1 | 41165.6618 | 41190.6917 | 1
40850.3333 | 41192.5715 | 0 | 40850.3333 | 40924.35 | 1 | 40924.35 | 41095.5882 | 1 | 41095.5882 | 41192.5715 | 1 | 41192.5715 | 41192.5715 | 1
40850.3333 | 41184.6549 | 0 | 40850.3333 | 40941.3368 | 1 | 40941.3368 | 41102.5917 | 1 | 41102.5917 | 41184.6549 | 1 | 41184.6549 | 41184.6549 | 1
40850.3333 | 41205.6549 | 0 | 40850.3333 | 40941.4097 | 1 | 40941.4097 | 41123.4299 | 1 | 41123.4299 | 41205.6549 | 1 | 41205.6549 | 41205.6549 | 1
40850.3333 | 41142.4764 | 0 | 40850.3333 | 40938.675 | 1 | 40938.675 | 41099.5618 | 1 | 41099.5618 | 41142.4764 | 1 | 41142.4764 | 41142.4764 | 1
40850.3333 | 41137.4167 | 0 | 40850.3333 | 40935.6181 | 1 | 40935.6181 | 41089.4035 | 1 | 41089.4035 | 41137.4167 | 1 | 41137.4167 | 41137.4167 | 1
40850.3333 | 41130.3597 | 0 | 40850.3333 | 40924.4201 | 1 | 40924.4201 | 41089.4667 | 1 | 41089.4667 | 41130.3597 | 1 | 41130.3597 | 41130.3597 | 1
40850.3333 | 41180.4299 | 0 | 40850.3333 | 40933.6417 | 1 | 40933.6417 | 41103.5618 | 1 | 41103.5618 | 41149.5486 | 1 | 41149.5486 | 41180.4299 | 1
40850.3333 | 41149.3597 | 0 | 40850.3333 | 40921.45 | 1 | 40921.45 | 41085.5951 | 1 | 41085.5951 | 41124.4236 | 1 | 41124.4236 | 41149.3597 | 1
40850.3333 | 41190.6181 | 0 | 40850.3333 | 40933.4403 | 1 | 40933.4403 | 41109.6083 | 1 | 41109.6083 | 41155.6347 | 1 | 41155.6347 | 41190.6181 | 1
40850.3333 | 41233.6083 | 0 | 40850.3333 | 40940.3868 | 1 | 40940.3868 | 41108.6118 | 1 | 41108.6118 | 41201.3736 | 1 | 41201.3736 | 41233.6083 | 1
40850.3333 | 41142.6319 | 0 | 40850.3333 | 40925.5549 | 1 | 40925.5549 | 41099.5618 | 1 | 41099.5618 | 41142.6319 | 1 | 41142.6319 | 41142.6319 | 1
40850.3333 | 41159.5618 | 0 | 40850.3333 | 40938.4236 | 1 | 40938.4236 | 41085.4333 | 1 | 41085.4333 | 41130.3403 | 1 | 41130.3403 | 41159.5618 | 1
40850.3333 | 41170.4764 | 0 | 40850.3333 | 40921.4333 | 1 | 40921.4333 | 41103.6049 | 1 | 41103.6049 | 41144.3632 | 1 | 41144.3632 | 41170.4764 | 1
40850.3333 | 41183.4736 | 0 | 40850.3333 | 40939.3569 | 1 | 40939.3569 | 41108.5 | 1 | 41108.5417 | 41150.3569 | 1 | 41150.3569 | 41183.4736 | 1
40850.3333 | 41171.5986 | 0 | 40850.3333 | 40941.4368 | 1 | 40941.4368 | 41124.675 | 1 | 41124.675 | 41171.5986 | 1 | 41171.5986 | 41171.5986 | 1
40850.3333 | 41128.675 | 0 | 40850.3333 | 40928.4632 | 1 | 40928.4632 | 41089.4368 | 1 | 41089.4368 | 41128.675 | 1 | 41128.675 | 41128.675 | 1
40850.3333 | 41124.3403 | 0 | 40850.3333 | 40932.5715 | 1 | 40932.5715 | 41080.3868 | 1 | 41080.3868 | 41124.3403 | 1 | 41124.3403 | 41124.3403 | 1
40850.3333 | 41134.6451 | 0 | 40850.3333 | 40931.5951 | 1 | 40931.5951 | 41094.6583 | 1 | 41094.6583 | 41134.6451 | 1 | 41134.6451 | 41134.6451 | 1
40850.3333 | 41166.45 | 0 | 40850.3333 | 40946.3903 | 1 | 40946.3903 | 41123.4132 | 1 | 41123.4132 | 41166.45 | 1 | 41166.45 | 41166.45 | 1
40850.3333 | 41145.4799 | 0 | 40850.3333 | 40935.4368 | 1 | 40935.4368 | 41106.4264 | 1 | 41106.4264 | 41145.4799 | 1 | 41145.4799 | 41145.4799 | 1
40850.3333 | 41187.5549 | 0 | 40850.3333 | 40927.6083 | 1 | 40927.6083 | 41089.4931 | 1 | 41089.4931 | 41187.5549 | 1 | 41187.5549 | 41187.5549 | 1
40850.3333 | 41152.4465 | 0 | 40850.3333 | 40935.6417 | 1 | 40935.6417 | 41107.5451 | 1 | 41107.5451 | 41152.4465 | 1 | 41152.4465 | 41152.4465 | 1
40850.3333 | 41201.6917 | 0 | 40850.3333 | 40948.4535 | 1 | 40948.4535 | 41127.7014 | 1 | 41127.7014 | 41169.4799 | 1 | 41169.4799 | 41201.6917 | 1
40850.3333 | 41158.4431 | 0 | 40850.3333 | 40947.6681 | 1 | 40947.6681 | 41114.6118 | 1 | 41114.6118 | 41158.4431 | 1 | 41158.4431 | 41158.4431 | 1
40850.3333 | 41169.5917 | 0 | 40850.3333 | 40932.4403 | 1 | 40932.4403 | 41103.3764 | 1 | 41103.3764 | 41145.3736 | 1 | 41145.3736 | 41169.5917 | 1
40850.3333 | 41250.4201 | 0 | 40850.3333 | 40935.6618 | 1 | 40935.6618 | 41115.5951 | 1 | 41115.5951 | 41213.4333 | 1 | 41213.4333 | 41250.4201 | 1
40850.3333 | 41138.3833 | 0 | 40850.3333 | 40938.4701 | 1 | 40938.4701 | 41100.5785 | 1 | 41100.5785 | 41138.3833 | 1 | 41138.3833 | 41138.3833 | 1
40850.3333 | 41163.3833 | 0 | 40850.3333 | 40934.3833 | 1 | 40934.3833 | 41087.3667 | 1 | 41087.3667 | 41130.4535 | 1 | 41130.4535 | 41163.3833 | 1
40850.3333 | 41200.6618 | 0 | 40850.3333 | 40939.625 | 1 | 40939.625 | 41115.6215 | 1 | 41115.6215 | 41200.6618 | 1 | 41200.6618 | 41200.6618 | 1
40850.3333 | 41156.6986 | 0 | 40850.3333 | 40942.3903 | 1 | 40942.3903 | 41116.4736 | 1 | 41116.4736 | 41156.6986 | 1 | 41156.6986 | 41156.6986 | 1
40850.3333 | 41164.5951 | 0 | 40850.3333 | 40924.6951 | 1 | 40924.6951 | 41094.6382 | 1 | 41094.6382 | 41136.6014 | 1 | 41136.6014 | 41164.5951 | 1
40850.3333 | 41173.7049 | 0 | 40850.3333 | 40938.4069 | 1 | 40938.4069 | 41106.6785 | 1 | 41106.6785 | 41144.4167 | 1 | 41144.4167 | 41173.7049 | 1
40850.3333 | 41208.5917 | 0 | 40850.3333 | 40942.4403 | 1 | 40942.4403 | 41124.3799 | 1 | 41124.3799 | 41208.5917 | 1 | 41208.5917 | 41208.5917 | 1
40850.3333 | 41163.675 | 0 | 40850.3333 | 40928.6951 | 1 | 40928.6951 | 41087.3764 | 1 | 41087.3764 | 41129.6583 | 1 | 41129.6583 | 41163.675 | 1
40850.3333 | 41134.4264 | 0 | 40850.3333 | 40941.3736 | 1 | 40941.3736 | 41092.4403 | 1 | 41092.4403 | 41134.4264 | 1 | 41134.4264 | 41134.4264 | 1
40850.3333 | 41193.6285 | 0 | 40850.3333 | 40949.5882 | 1 | 40949.5882 | 41127.6618 | 1 | 41127.6618 | 41165.6215 | 1 | 41165.6215 | 41193.6285 | 1
40850.3333 | 41213.7049 | 0 | 40850.3333 | 40934.3535 | 1 | 40934.3535 | 41095.5681 | 1 | 41095.5681 | 41180.3903 | 1 | 41180.3903 | 41213.7049 | 1
40850.3333 | 41162.6681 | 0 | 40850.3333 | 40926.5583 | 1 | 40926.5583 | 41088.4931 | 1 | 41088.4931 | 41162.6681 | 1 | 41162.6681 | 41162.6681 | 1
40850.3333 | 41138.6819 | 0 | 40850.3333 | 40935.5514 | 1 | 40935.5514 | 41099.6882 | 1 | 41099.6882 | 41138.6819 | 1 | 41138.6819 | 41138.6819 | 1
40850.3333 | 41206.5618 | 0 | 40850.3333 | 40941.4701 | 1 | 40941.4701 | 41108.7083 | 1 | 41109.3333 | 41179.4799 | 1 | 41179.4799 | 41206.5618 | 1
40850.3333 | 41192.4236 | 0 | 40850.3333 | 40941.6083 | 1 | 40941.6083 | 41110.5583 | 1 | 41110.5583 | 41158.4667 | 1 | 41158.4667 | 41192.4236 | 1
40850.3333 | 41143.3764 | 0 | 40850.3333 | 40934.6819 | 1 | 40934.6819 | 41099.5715 | 1 | 41099.5715 | 41143.3764 | 1 | 41143.3764 | 41143.3764 | 1
40850.3333 | 41148.6382 | 0 | 40850.3333 | 40933.4903 | 1 | 40933.4903 | 41103.5785 | 1 | 41103.5785 | 41148.6382 | 1 | 41148.6382 | 41148.6382 | 1
40850.3333 | 41120.6319 | 0 | 40850.3333 | 40933.6583 | 1 | 40933.6583 | 41082.4264 | 1 | 41082.4264 | 41120.6319 | 1 | 41120.6319 | 41120.6319 | 1
40850.3333 | 41129.5549 | 0 | 40850.3333 | 40927.6681 | 1 | 40927.6681 | 41087.6549 | 1 | 41087.6549 | 41129.5549 | 1 | 41129.5549 | 41129.5549 | 1
40850.3333 | 41200.5681 | 0 | 40850.3333 | 40935.5986 | 1 | 40935.5986 | 41108.5847 | 1 | 41108.5847 | 41200.5681 | 1 | 41200.5681 | 41200.5681 | 1
40850.3333 | 41157.4535 | 0 | 40850.3333 | 40934.575 | 1 | 40934.575 | 41086.3368 | 1 | 41086.3368 | 41127.4764 | 1 | 41127.4764 | 41157.4535 | 1
40850.3333 | 41162.3868 | 0 | 40850.3333 | 40940.6486 | 1 | 40940.6486 | 41092.4868 | 1 | 41092.4868 | 41131.5653 | 1 | 41131.5653 | 41162.3868 | 1
40850.3333 | 41143.4736 | 0 | 40850.3333 | 40938.3569 | 1 | 40938.3569 | 41102.5951 | 1 | 41102.5951 | 41143.4736 | 1 | 41143.4736 | 41143.4736 | 1
40850.3333 | 41229.4597 | 0 | 40850.3333 | 40931.3632 | 1 | 40931.3632 | 41106.6417 | 1 | 41106.6417 | 41200.6618 | 1 | 41200.6618 | 41229.4597 | 1
40850.3333 | 41136.3535 | 0 | 40850.3333 | 40933.4465 | 1 | 40933.4465 | 41092.5653 | 1 | 41092.5653 | 41136.3535 | 1 | 41136.3535 | 41136.3535 | 1
40850.3333 | 41176.3632 | 0 | 40850.3333 | 40935.5847 | 1 | 40935.5847 | 41103.3931 | 1 | 41103.3931 | 41149.5785 | 1 | 41149.5785 | 41176.3632 | 1
40850.3333 | 41164.4132 | 0 | 40850.3333 | 40933.6181 | 1 | 40933.6181 | 41120.6486 | 1 | 41120.6486 | 41164.4132 | 1 | 41164.4132 | 41164.4132 | 1
40850.3333 | 41148.5951 | 0 | 40850.3333 | 40932.4299 | 1 | 40932.4299 | 41102.6951 | 1 | 41102.6951 | 41148.5951 | 1 | 41148.5951 | 41148.5951 | 1
40850.3333 | 41151.3833 | 0 | 40850.3333 | 40928.3868 | 1 | 40928.3868 | 41080.6382 | 1 | 41080.6382 | 41121.4931 | 1 | 41121.4931 | 41151.3833 | 1
40850.3333 | 41141.5986 | 0 | 40850.3333 | 40927.4833 | 1 | 40927.4833 | 41096.6083 | 1 | 41096.6083 | 41141.5986 | 1 | 41141.5986 | 41141.5986 | 1
40850.3333 | 41142.3931 | 0 | 40850.3333 | 40931.6882 | 1 | 40931.6882 | 41101.4368 | 1 | 41101.4368 | 41142.3931 | 1 | 41142.3931 | 41142.3931 | 1
40850.3333 | 41123.3701 | 0 | 40850.3333 | 40935.3965 | 1 | 40935.3965 | 41080.6653 | 1 | 41080.6653 | 41123.3701 | 1 | 41123.3701 | 41123.3701 | 1
40850.3333 | 41151.6347 | 0 | 40850.3333 | 40928.4097 | 1 | 40928.4097 | 41109.3403 | 1 | 41109.3403 | 41151.6347 | 1 | 41151.6347 | 41151.6347 | 1
40850.3333 | 41165.5583 | 0 | 40850.3333 | 40941.5 | 1 | 40941.5417 | 41101.3632 | 1 | 41101.3632 | 41142.675 | 1 | 41142.675 | 41165.5583 | 1
40850.3333 | 41200.5549 | 0 | 40850.3333 | 40940.6819 | 1 | 40940.6819 | 41122.5882 | 1 | 41122.5882 | 41200.5549 | 1 | 41200.5549 | 41200.5549 | 1
40850.3333 | 41173.5819 | 0 | 40850.3333 | 40938.3403 | 1 | 40938.3403 | 41094.6451 | 1 | 41094.6451 | 41173.5819 | 1 | 41173.5819 | 41173.5819 | 1
40850.3333 | 41138.4236 | 0 | 40850.3333 | 40934.5986 | 1 | 40934.5986 | 41093.6215 | 1 | 41093.6215 | 41138.4236 | 1 | 41138.4236 | 41138.4236 | 1
40850.3333 | 41137.3632 | 0 | 40850.3333 | 40939.3736 | 1 | 40939.3736 | 41094.5618 | 1 | 41094.5618 | 41137.3632 | 1 | 41137.3632 | 41137.3632 | 1
40850.3333 | 41131.35 | 0 | 40850.3333 | 40927.5514 | 1 | 40927.5514 | 41092.6819 | 1 | 41092.6819 | 41131.35 | 1 | 41131.35 | 41131.35 | 1
40850.3333 | 41152.5514 | 0 | 40850.3333 | 40927.6514 | 1 | 40927.6514 | 41108.6653 | 1 | 41108.6653 | 41152.5514 | 1 | 41152.5514 | 41152.5514 | 1
40850.3333 | 41137.5847 | 0 | 40850.3333 | 40934.7049 | 1 | 40934.7049 | 41095.35 | 1 | 41095.35 | 41137.5847 | 1 | 41137.5847 | 41137.5847 | 1
40850.3333 | 41204.6215 | 0 | 40850.3333 | 40941.5882 | 1 | 40941.5882 | 41129.5549 | 1 | 41129.5549 | 41172.3667 | 1 | 41172.3667 | 41204.6215 | 1
40850.3333 | 41159.6951 | 0 | 40850.3333 | 40932.5486 | 1 | 40932.5486 | 41099.4201 | 1 | 41099.4201 | 41136.4465 | 1 | 41136.4465 | 41159.6951 | 1
40850.3333 | 41145.4431 | 0 | 40850.3333 | 40933.3736 | 1 | 40933.3736 | 41100.6986 | 1 | 41100.6986 | 41145.4431 | 1 | 41145.4431 | 41145.4431 | 1
40850.3333 | 41169.3965 | 0 | 40850.3333 | 40928.6514 | 1 | 40928.6514 | 41094.3701 | 1 | 41094.3701 | 41169.3965 | 1 | 41169.3965 | 41169.3965 | 1
40850.3333 | 41192.675 | 0 | 40850.3333 | 40942.3403 | 1 | 40942.3403 | 41095.7049 | 1 | 41095.7049 | 41165.3736 | 1 | 41165.3736 | 41192.675 | 1
40850.3333 | 41159.6049 | 0 | 40850.3333 | 40938.6653 | 1 | 40938.6653 | 41115.625 | 1 | 41115.625 | 41159.6049 | 1 | 41159.6049 | 41159.6049 | 1
40850.3333 | 41144.6382 | 0 | 40850.3333 | 40931.4264 | 1 | 40931.4264 | 41101.6319 | 1 | 41101.6319 | 41144.6382 | 1 | 41144.6382 | 41144.6382 | 1
40850.3333 | 41205.5951 | 0 | 40850.3333 | 40935.3569 | 1 | 40935.3569 | 41114.4764 | 1 | 41114.4764 | 41205.5951 | 1 | 41205.5951 | 41205.5951 | 1
40850.3333 | 41136.4299 | 0 | 40850.3333 | 40938.4632 | 1 | 40938.4632 | 41096.6382 | 1 | 41096.6382 | 41136.4299 | 1 | 41136.4299 | 41136.4299 | 1
40850.3333 | 41169.5917 | 0 | 40850.3333 | 40942.5951 | 1 | 40942.5951 | 41127.4403 | 1 | 41127.4403 | 41169.5917 | 1 | 41169.5917 | 41169.5917 | 1
40850.3333 | 41165.6486 | 0 | 40850.3333 | 40932.6382 | 1 | 40932.6382 | 41089.4299 | 1 | 41089.4299 | 41165.6486 | 1 | 41165.6486 | 41165.6486 | 1
40850.3333 | 41121.5785 | 0 | 40850.3333 | 40928.4264 | 1 | 40928.4264 | 41080.5986 | 1 | 41080.5986 | 41121.5785 | 1 | 41121.5785 | 41121.5785 | 1
40850.3333 | 41169.4236 | 0 | 40850.3333 | 40932.4764 | 1 | 40932.4764 | 41127.3903 | 1 | 41127.3903 | 41169.4236 | 1 | 41169.4236 | 41169.4236 | 1
40850.3333 | 41137.45 | 0 | 40850.3333 | 40938.5715 | 1 | 40938.5715 | 41095.6951 | 1 | 41095.6951 | 41137.45 | 1 | 41137.45 | 41137.45 | 1
40850.3333 | 41191.3597 | 0 | 40850.3333 | 40925.3667 | 1 | 40925.3667 | 41095.6583 | 1 | 41095.6583 | 41164.5549 | 1 | 41164.5549 | 41191.3597 | 1
40850.3333 | 41122.4 | 0 | 40850.3333 | 40928.4931 | 1 | 40928.4931 | 41080.6486 | 1 | 41080.6486 | 41122.4 | 1 | 41122.4 | 41122.4 | 1
40850.3333 | 41187.4403 | 0 | 40850.3333 | 40933.575 | 1 | 40933.575 | 41117.4764 | 1 | 41117.4764 | 41187.4403 | 1 | 41187.4403 | 41187.4403 | 1
40850.3333 | 41169.5951 | 0 | 40850.3333 | 40932.3965 | 1 | 40932.3965 | 41103.4132 | 1 | 41103.4132 | 41143.4535 | 1 | 41143.4535 | 41169.5951 | 1
40850.3333 | 41191.4132 | 0 | 40850.3333 | 40945.3632 | 1 | 40945.3632 | 41123.6347 | 1 | 41123.6347 | 41165.35 | 1 | 41165.35 | 41191.4132 | 1
40850.3333 | 41152.45 | 0 | 40850.3333 | 40925.4736 | 1 | 40925.4736 | 41085.5917 | 1 | 41085.5917 | 41128.5653 | 1 | 41128.5653 | 41152.45 | 1
40850.3333 | 41135.5882 | 0 | 40850.3333 | 40928.575 | 1 | 40928.575 | 41094.4764 | 1 | 41094.4764 | 41135.5882 | 1 | 41135.5882 | 41135.5882 | 1
40850.3333 | 41183.5917 | 0 | 40850.3333 | 40928.6319 | 1 | 40928.6319 | 41109.3736 | 1 | 41109.3736 | 41155.4097 | 1 | 41155.4097 | 41183.5917 | 1
40850.3333 | 41145.4535 | 0 | 40850.3333 | 40940.4097 | 1 | 40940.4097 | 41100.6215 | 1 | 41100.6215 | 41145.4535 | 1 | 41145.4535 | 41145.4535 | 1
40850.3333 | 41141.4569 | 0 | 40850.3333 | 40925.6986 | 1 | 40925.6986 | 41099.625 | 1 | 41099.625 | 41141.4569 | 1 | 41141.4569 | 41141.4569 | 1
40850.3333 | 41169.6549 | 0 | 40850.3333 | 40941.6819 | 1 | 40941.6819 | 41122.3868 | 1 | 41122.3868 | 41169.6549 | 1 | 41169.6549 | 41169.6549 | 1
40850.3333 | 41155.4431 | 0 | 40850.3333 | 40940.4597 | 1 | 40940.4597 | 41110.6118 | 1 | 41110.6118 | 41155.4431 | 1 | 41155.4431 | 41155.4431 | 1
40850.3333 | 41190.4236 | 0 | 40850.3333 | 40928.6181 | 1 | 40928.6181 | 41110.675 | 1 | 41110.675 | 41158.4833 | 1 | 41158.4833 | 41190.4236 | 1
40850.3333 | 41186.3403 | 0 | 40850.3333 | 40945.3799 | 1 | 40945.3799 | 41106.3931 | 1 | 41106.3931 | 41186.3403 | 1 | 41186.3403 | 41186.3403 | 1
40850.3333 | 41144.4903 | 0 | 40850.3333 | 40931.6618 | 1 | 40931.6618 | 41103.5583 | 1 | 41103.5583 | 41144.4903 | 1 | 41144.4903 | 41144.4903 | 1
40850.3333 | 41171.4931 | 0 | 40850.3333 | 40932.5882 | 1 | 40932.5882 | 41088.6014 | 1 | 41088.6014 | 41171.4931 | 1 | 41171.4931 | 41171.4931 | 1
40850.3333 | 41120.7014 | 0 | 40850.3333 | 40926.6083 | 1 | 40926.6083 | 41079.6785 | 1 | 41079.6785 | 41120.7014 | 1 | 41120.7014 | 41120.7014 | 1
40850.3333 | 41234.5583 | 0 | 40850.3333 | 40953.3764 | 1 | 40953.3764 | 41123.5618 | 1 | 41123.5618 | 41205.6618 | 1 | 41205.6618 | 41234.5583 | 1
40850.3333 | 41191.6583 | 0 | 40850.3333 | 40924.6319 | 1 | 40924.6319 | 41078.4903 | 1 | 41078.4903 | 41163.5986 | 1 | 41163.5986 | 41191.6583 | 1
40850.3333 | 41164.5917 | 0 | 40850.3333 | 40939.4965 | 1 | 40939.4965 | 41102.4167 | 1 | 41102.4167 | 41141.5917 | 1 | 41141.5917 | 41164.5917 | 1
40850.3333 | 41163.5785 | 0 | 40850.3333 | 40939.6917 | 1 | 40939.6917 | 41117.4333 | 1 | 41117.4333 | 41163.5785 | 1 | 41163.5785 | 41163.5785 | 1
40850.3333 | 41173.5 | 0 | 40850.3333 | 40939.4069 | 1 | 40939.4069 | 41110.4931 | 1 | 41110.4931 | 41151.6319 | 1 | 41151.6319 | 41173.5 | 1
40850.3333 | 41130.6153 | 0 | 40850.3333 | 40935.4667 | 1 | 40935.4667 | 41093.625 | 1 | 41093.625 | 41130.6153 | 1 | 41130.6153 | 41130.6153 | 1
40850.3333 | 41208.3701 | 0 | 40850.3333 | 40938.3764 | 1 | 40938.3764 | 41113.4035 | 1 | 41113.4035 | 41208.3701 | 1 | 41208.3701 | 41208.3701 | 1
40850.3333 | 41149.4667 | 0 | 40850.3333 | 40927.6917 | 1 | 40927.6917 | 41082.6417 | 1 | 41082.6417 | 41121.4167 | 1 | 41121.4167 | 41149.4667 | 1
40850.3333 | 41157.3535 | 0 | 40850.3333 | 40931.5819 | 1 | 40931.5819 | 41081.6083 | 1 | 41081.6083 | 41124.6319 | 1 | 41124.6319 | 41157.3535 | 1
40850.3333 | 41144.3764 | 0 | 40850.3333 | 40927.3764 | 1 | 40927.3764 | 41101.6882 | 1 | 41101.6882 | 41144.3764 | 1 | 41144.3764 | 41144.3764 | 1
40850.3333 | 41135.6917 | 0 | 40850.3333 | 40927.4569 | 1 | 40927.4569 | 41095.4597 | 1 | 41095.4597 | 41135.6917 | 1 | 41135.6917 | 41135.6917 | 1
40850.3333 | 41134.5986 | 0 | 40850.3333 | 40942.4069 | 1 | 40942.4069 | 41088.5 | 1 | 41088.5417 | 41134.5986 | 1 | 41134.5986 | 41134.5986 | 1
40850.3333 | 41215.3535 | 0 | 40850.3333 | 40927.4132 | 1 | 40927.4132 | 41089.4167 | 1 | 41089.4167 | 41186.4132 | 1 | 41186.4132 | 41215.3535 | 1
40850.3333 | 41180.6153 | 0 | 40850.3333 | 40945.4236 | 1 | 40945.4236 | 41106.4931 | 1 | 41106.4931 | 41150.6882 | 1 | 41150.6882 | 41180.6153 | 1
40850.3333 | 41199.4035 | 0 | 40850.3333 | 40947.5882 | 1 | 40947.5882 | 41124.4069 | 1 | 41124.4069 | 41164.4667 | 1 | 41164.4667 | 41199.4035 | 1
40850.3333 | 41130.5847 | 0 | 40850.3333 | 40926.3597 | 1 | 40926.3597 | 41088.3931 | 1 | 41088.3931 | 41130.5847 | 1 | 41130.5847 | 41130.5847 | 1
40850.3333 | 41190.4569 | 0 | 40850.3333 | 40942.5618 | 1 | 40942.5618 | 41120.3868 | 1 | 41120.3868 | 41162.5618 | 1 | 41162.5618 | 41190.4569 | 1
40850.3333 | 41178.6382 | 0 | 40850.3333 | 40934.3965 | 1 | 40934.3965 | 41100.4701 | 1 | 41100.4701 | 41143.5 | 1 | 41143.5 | 41178.6382 | 1
40850.3333 | 41180.6917 | 0 | 40850.3333 | 40938.6514 | 1 | 40938.6514 | 41110.6986 | 1 | 41110.6986 | 41151.5819 | 1 | 41151.5819 | 41180.6917 | 1
40850.3333 | 41197.4736 | 0 | 40850.3333 | 40933.6049 | 1 | 40933.6049 | 41101.4736 | 1 | 41101.4736 | 41197.4736 | 1 | 41197.4736 | 41197.4736 | 1
40850.3333 | 41129.3403 | 0 | 40850.3333 | 40925.6715 | 1 | 40925.6715 | 41086.6181 | 1 | 41086.6181 | 41129.3403 | 1 | 41129.3403 | 41129.3403 | 1
40850.3333 | 41122.6049 | 0 | 40850.3333 | 40925.5917 | 1 | 40925.5917 | 41081.5514 | 1 | 41081.5514 | 41122.6049 | 1 | 41122.6049 | 41122.6049 | 1
40850.3333 | 41121.5486 | 0 | 40850.3333 | 40924.4833 | 1 | 40924.4833 | 41079.7014 | 1 | 41079.7014 | 41121.5486 | 1 | 41121.5486 | 41121.5486 | 1
40850.3333 | 41197.4535 | 0 | 40850.3333 | 40933.3965 | 1 | 40933.3965 | 41103.3764 | 1 | 41103.3764 | 41197.4535 | 1 | 41197.4535 | 41197.4535 | 1
40850.3333 | 41144.6285 | 0 | 40850.3333 | 40926.4701 | 1 | 40926.4701 | 41100.6118 | 1 | 41100.6118 | 41144.6285 | 1 | 41144.6285 | 41144.6285 | 1
40850.3333 | 41169.6917 | 0 | 40850.3333 | 40925.4 | 1 | 40925.4 | 41092.4069 | 1 | 41092.4069 | 41134.4465 | 1 | 41134.4465 | 41169.6917 | 1
40850.3333 | 41155.5 | 0 | 40850.3333 | 40945.4965 | 1 | 40945.4965 | 41116.675 | 1 | 41116.675 | 41155.5 | 1 | 41155.5 | 41155.5 | 1
40850.3333 | 41143.6181 | 0 | 40850.3333 | 40945.7014 | 1 | 40945.7014 | 41103.6181 | 1 | 41103.6181 | 41143.6181 | 1 | 41143.6181 | 41143.6181 | 1
40850.3333 | 41156.4736 | 0 | 40850.3333 | 40926.625 | 1 | 40926.625 | 41115.4597 | 1 | 41115.4597 | 41156.4736 | 1 | 41156.4736 | 41156.4736 | 1
40850.3333 | 41184.3597 | 0 | 40850.3333 | 40931.7049 | 1 | 40931.7049 | 41096.3597 | 1 | 41096.3597 | 41184.3597 | 1 | 41184.3597 | 41184.3597 | 1
40850.3333 | 41173.5451 | 0 | 40850.3333 | 40938.5486 | 1 | 40938.5486 | 41103.6319 | 1 | 41103.6319 | 41145.5819 | 1 | 41145.5819 | 41173.5451 | 1
40850.3333 | 41169.6014 | 0 | 40850.3333 | 40926.6653 | 1 | 40926.6653 | 41101.4701 | 1 | 41101.4701 | 41142.4 | 1 | 41142.4 | 41169.6014 | 1
40850.3333 | 41190.5819 | 0 | 40850.3333 | 40932.6451 | 1 | 40932.6451 | 41108.35 | 1 | 41108.35 | 41155.5451 | 1 | 41155.5451 | 41190.5819 | 1
40850.3333 | 41131.4201 | 0 | 40850.3333 | 40934.4403 | 1 | 40934.4403 | 41092.6347 | 1 | 41092.6347 | 41131.4201 | 1 | 41131.4201 | 41131.4201 | 1
40850.3333 | 41178.4333 | 0 | 40850.3333 | 40931.4632 | 1 | 40931.4632 | 41085.6451 | 1 | 41085.6451 | 41178.4333 | 1 | 41178.4333 | 41178.4333 | 1
40850.3333 | 41166.6285 | 0 | 40850.3333 | 40928.7083 | 1 | 40931.3333 | 41100.5486 | 1 | 41100.5486 | 41143.3368 | 1 | 41143.3368 | 41166.6285 | 1
40850.3333 | 41162.6014 | 0 | 40850.3333 | 40942.6285 | 1 | 40942.6285 | 41093.5681 | 1 | 41093.5681 | 41136.5653 | 1 | 41136.5653 | 41162.6014 | 1
40850.3333 | 41145.3701 | 0 | 40850.3333 | 40938.7083 | 1 | 40939.3333 | 41103.4903 | 1 | 41103.4903 | 41145.3701 | 1 | 41145.3701 | 41145.3701 | 1
40850.3333 | 41228.6618 | 0 | 40850.3333 | 40933.6882 | 1 | 40933.6882 | 41117.4368 | 1 | 41117.4368 | 41200.6382 | 1 | 41200.6382 | 41228.6618 | 1
40850.3333 | 41218.4201 | 0 | 40850.3333 | 40946.4764 | 1 | 40946.4764 | 41103.4799 | 1 | 41103.4799 | 41191.6215 | 1 | 41191.6215 | 41218.4201 | 1
40850.3333 | 41159.7014 | 0 | 40850.3333 | 40942.6951 | 1 | 40942.6951 | 41116.4 | 1 | 41116.4 | 41159.7014 | 1 | 41159.7014 | 41159.7014 | 1
40850.3333 | 41199.45 | 0 | 40850.3333 | 40945.675 | 1 | 40945.675 | 41127.4569 | 1 | 41127.4569 | 41169.4597 | 1 | 41169.4597 | 41199.45 | 1
40850.3333 | 41183.6583 | 0 | 40850.3333 | 40940.6319 | 1 | 40940.6319 | 41108.3597 | 1 | 41108.3597 | 41151.6382 | 1 | 41151.6382 | 41183.6583 | 1
40850.3333 | 41180.4833 | 0 | 40850.3333 | 40932.6083 | 1 | 40932.6083 | 41110.6014 | 1 | 41110.6014 | 41150.3799 | 1 | 41150.3799 | 41180.4833 | 1
40850.3333 | 41186.4965 | 0 | 40850.3333 | 40946.6882 | 1 | 40946.6882 | 41122.4764 | 1 | 41122.4764 | 41162.6653 | 1 | 41162.6653 | 41186.4965 | 1
40850.3333 | 41200.3931 | 0 | 40850.3333 | 40939.4667 | 1 | 40939.4667 | 41117.6819 | 1 | 41117.6819 | 41159.5451 | 1 | 41159.5451 | 41200.3931 | 1
40850.3333 | 41186.6514 | 0 | 40850.3333 | 40939.5882 | 1 | 40939.5882 | 41114.7049 | 1 | 41114.7049 | 41157.6819 | 1 | 41157.6819 | 41186.6514 | 1
40850.3333 | 41198.5785 | 0 | 40850.3333 | 40945.5681 | 1 | 40945.5681 | 41121.4597 | 1 | 41121.4597 | 41166.4667 | 1 | 41166.4667 | 41198.5785 | 1
40850.3333 | 41143.3833 | 0 | 40850.3333 | 40931.6514 | 1 | 40931.6514 | 41100.45 | 1 | 41100.45 | 41143.3833 | 1 | 41143.3833 | 41143.3833 | 1
40850.3333 | 41178.4868 | 0 | 40850.3333 | 40938.5986 | 1 | 40938.5986 | 41095.4569 | 1 | 41095.4569 | 41143.7083 | 1 | 41143.7083 | 41178.4868 | 1
40850.3333 | 41166.6319 | 0 | 40850.3333 | 40948.4799 | 1 | 40948.4799 | 41127.4799 | 1 | 41127.4799 | 41166.6319 | 1 | 41166.6319 | 41166.6319 | 1
40850.3333 | 41184.6153 | 0 | 40850.3333 | 40931.3903 | 1 | 40931.3903 | 41114.3764 | 1 | 41114.3764 | 41157.4868 | 1 | 41157.4868 | 41184.6153 | 1
40850.3333 | 41191.4069 | 0 | 40850.3333 | 40940.6118 | 1 | 40940.6118 | 41094.6319 | 1 | 41094.6319 | 41191.4069 | 1 | 41191.4069 | 41191.4069 | 1
40850.3333 | 41145.4299 | 0 | 40850.3333 | 40934.4667 | 1 | 40934.4667 | 41108.4465 | 1 | 41108.4465 | 41145.4299 | 1 | 41145.4299 | 41145.4299 | 1
40850.3333 | 41134.7049 | 0 | 40850.3333 | 40940.4701 | 1 | 40940.4701 | 41094.6785 | 1 | 41094.6785 | 41134.7049 | 1 | 41134.7049 | 41134.7049 | 1
40850.3333 | 41148.4597 | 0 | 40850.3333 | 40940.4931 | 1 | 40940.4931 | 41110.6215 | 1 | 41110.6215 | 41148.4597 | 1 | 41148.4597 | 41148.4597 | 1
40850.3333 | 41191.6118 | 0 | 40850.3333 | 40941.6382 | 1 | 40941.6382 | 41116.4069 | 1 | 41116.4069 | 41191.6118 | 1 | 41191.6118 | 41191.6118 | 1
40850.3333 | 41150.4368 | 0 | 40850.3333 | 40940.5618 | 1 | 40940.5618 | 41108.5583 | 1 | 41108.5583 | 41150.4368 | 1 | 41150.4368 | 41150.4368 | 1
40850.3333 | 41178.6715 | 0 | 40850.3333 | 40934.4264 | 1 | 40934.4264 | 41110.45 | 1 | 41110.45 | 41155.4965 | 1 | 41155.4965 | 41178.6715 | 1
40850.3333 | 41186.5583 | 0 | 40850.3333 | 40926.4403 | 1 | 40926.4403 | 41109.3597 | 1 | 41109.3597 | 41186.5583 | 1 | 41186.5583 | 41186.5583 | 1
40850.3333 | 41142.4465 | 0 | 40850.3333 | 40940.3701 | 1 | 40940.3701 | 41106.4868 | 1 | 41106.4868 | 41142.4465 | 1 | 41142.4465 | 41142.4465 | 1
40850.3333 | 41158.6215 | 0 | 40850.3333 | 40935.4132 | 1 | 40935.4132 | 41116.4569 | 1 | 41116.4569 | 41158.6215 | 1 | 41158.6215 | 41158.6215 | 1
40850.3333 | 41138.3764 | 0 | 40850.3333 | 40928.5583 | 1 | 40928.5583 | 41094.5785 | 1 | 41094.5785 | 41138.3764 | 1 | 41138.3764 | 41138.3764 | 1
40850.3333 | 41162.4431 | 0 | 40850.3333 | 40932.3903 | 1 | 40932.3903 | 41117.3403 | 1 | 41117.3403 | 41162.4431 | 1 | 41162.4431 | 41162.4431 | 1
40850.3333 | 41151.3569 | 0 | 40850.3333 | 40932.3597 | 1 | 40932.3597 | 41113.4465 | 1 | 41113.4465 | 41151.3569 | 1 | 41151.3569 | 41151.3569 | 1
40850.3333 | 41185.5514 | 0 | 40850.3333 | 40932.6715 | 1 | 40932.6715 | 41117.3764 | 1 | 41117.3764 | 41159.3903 | 1 | 41159.3903 | 41185.5514 | 1
40850.3333 | 41156.625 | 0 | 40850.3333 | 40934.5549 | 1 | 40934.5549 | 41092.3965 | 1 | 41092.3965 | 41134.4569 | 1 | 41134.4569 | 41156.625 | 1
40850.3333 | 41169.5486 | 0 | 40850.3333 | 40935.5 | 1 | 40935.5417 | 41101.4799 | 1 | 41101.4799 | 41141.35 | 1 | 41141.35 | 41169.5486 | 1
40850.3333 | 41159.4535 | 0 | 40850.3333 | 40945.6014 | 1 | 40945.6014 | 41122.3965 | 1 | 41122.3965 | 41159.4535 | 1 | 41159.4535 | 41159.4535 | 1
40850.3333 | 41179.4264 | 0 | 40850.3333 | 40939.5549 | 1 | 40939.5549 | 41107.6917 | 1 | 41107.6917 | 41149.4236 | 1 | 41149.4236 | 41179.4264 | 1
40850.3333 | 41178.4903 | 0 | 40850.3333 | 40931.4132 | 1 | 40931.4132 | 41096.5847 | 1 | 41096.5847 | 41178.4903 | 1 | 41178.4903 | 41178.4903 | 1
40850.3333 | 41152.6951 | 0 | 40850.3333 | 40946.5951 | 1 | 40946.5951 | 41115.6514 | 1 | 41115.6514 | 41152.6951 | 1 | 41152.6951 | 41152.6951 | 1
40850.3333 | 41191.5681 | 0 | 40850.3333 | 40939.5986 | 1 | 40939.5986 | 41124.4431 | 1 | 41124.4431 | 41163.5583 | 1 | 41163.5583 | 41191.5681 | 1
40850.3333 | 41183.4569 | 0 | 40850.3333 | 40938.6118 | 1 | 40938.6118 | 41115.4799 | 1 | 41115.4799 | 41158.3931 | 1 | 41158.3931 | 41183.4569 | 1
40850.3333 | 41142.4764 | 0 | 40850.3333 | 40934.3431 | 1 | 40934.3431 | 41100.6118 | 1 | 41100.6118 | 41142.4764 | 1 | 41142.4764 | 41142.4764 | 1
40850.3333 | 41128.6951 | 0 | 40850.3333 | 40939.4368 | 1 | 40939.4368 | 41087.4868 | 1 | 41087.4868 | 41128.6951 | 1 | 41128.6951 | 41128.6951 | 1
40850.3333 | 41128.6882 | 0 | 40850.3333 | 40933.4701 | 1 | 40933.4701 | 41088.5653 | 1 | 41088.5653 | 41128.6882 | 1 | 41128.6882 | 41128.6882 | 1
40850.3333 | 41131.3403 | 0 | 40850.3333 | 40933.35 | 1 | 40933.35 | 41092.6083 | 1 | 41092.6083 | 41131.3403 | 1 | 41131.3403 | 41131.3403 | 1
40850.3333 | 41150.3535 | 0 | 40850.3333 | 40947.3597 | 1 | 40947.3597 | 41108.4667 | 1 | 41108.4667 | 41150.3535 | 1 | 41150.3535 | 41150.3535 | 1
40850.3333 | 41157.4299 | 0 | 40850.3333 | 40949.3868 | 1 | 40949.3868 | 41117.4799 | 1 | 41117.4799 | 41157.4299 | 1 | 41157.4299 | 41157.4299 | 1
40850.3333 | 41128.6014 | 0 | 40850.3333 | 40933.5514 | 1 | 40933.5514 | 41088.3833 | 1 | 41088.3833 | 41128.6014 | 1 | 41128.6014 | 41128.6014 | 1
40850.3333 | 41145.6417 | 0 | 40850.3333 | 40939.7083 | 1 | 40940.3333 | 41108.6917 | 1 | 41108.6917 | 41145.6417 | 1 | 41145.6417 | 41145.6417 | 1
40850.3333 | 41178.4632 | 0 | 40850.3333 | 40939.6451 | 1 | 40939.6451 | 41100.3667 | 1 | 41100.3667 | 41141.3667 | 1 | 41141.3667 | 41178.4632 | 1
40850.3333 | 41170.6847 | 0 | 40850.3333 | 40942.4736 | 1 | 40942.4736 | 41131.5917 | 1 | 41131.5917 | 41170.6847 | 1 | 41170.6847 | 41170.6847 | 1
40850.3333 | 41121.4799 | 0 | 40850.3333 | 40935.6986 | 1 | 40935.6986 | 41080.4632 | 1 | 41080.4632 | 41121.4799 | 1 | 41121.4799 | 41121.4799 | 1
40850.3333 | 41165.6583 | 0 | 40850.3333 | 40931.625 | 1 | 40931.625 | 41121.5882 | 1 | 41121.5882 | 41165.6583 | 1 | 41165.6583 | 41165.6583 | 1
40850.3333 | 41145.3736 | 0 | 40850.3333 | 40934.4903 | 1 | 40934.4903 | 41100.3403 | 1 | 41100.3403 | 41145.3736 | 1 | 41145.3736 | 41145.3736 | 1
40850.3333 | 41170.5917 | 0 | 40850.3333 | 40927.3403 | 1 | 40927.3403 | 41110.6986 | 1 | 41110.6986 | 41149.4368 | 1 | 41149.4368 | 41170.5917 | 1
40850.3333 | 41180.4403 | 0 | 40850.3333 | 40931.5486 | 1 | 40931.5486 | 41106.3903 | 1 | 41106.3903 | 41150.3965 | 1 | 41150.3965 | 41180.4403 | 1
40850.3333 | 41179.5847 | 0 | 40850.3333 | 40946.6049 | 1 | 40946.6049 | 41135.3535 | 1 | 41135.3535 | 41179.5847 | 1 | 41179.5847 | 41179.5847 | 1
40850.3333 | 41169.4097 | 0 | 40850.3333 | 40934.6549 | 1 | 40934.6549 | 41100.45 | 1 | 41100.45 | 41142.6451 | 1 | 41142.6451 | 41169.4097 | 1
40850.3333 | 41159.4333 | 0 | 40850.3333 | 40931.4736 | 1 | 40931.4736 | 41095.3632 | 1 | 41095.3632 | 41135.4333 | 1 | 41135.4333 | 41159.4333 | 1
40850.3333 | 41226.3799 | 0 | 40850.3333 | 40947.4764 | 1 | 40947.4764 | 41102.4903 | 1 | 41102.4903 | 41191.4736 | 1 | 41191.4736 | 41226.3799 | 1
40850.3333 | 41136.4132 | 0 | 40850.3333 | 40933.4069 | 1 | 40933.4069 | 41095.6451 | 1 | 41095.6451 | 41136.4132 | 1 | 41136.4132 | 41136.4132 | 1
40850.3333 | 41130.6382 | 0 | 40850.3333 | 40926.3868 | 1 | 40926.3868 | 41087.5583 | 1 | 41087.5583 | 41130.6382 | 1 | 41130.6382 | 41130.6382 | 1
40850.3333 | 41173.3701 | 0 | 40850.3333 | 40927.3667 | 1 | 40927.3667 | 41102.3597 | 1 | 41102.3597 | 41149.4236 | 1 | 41149.4236 | 41173.3701 | 1
40850.3333 | 41180.6347 | 0 | 40850.3333 | 40934.625 | 1 | 40934.625 | 41102.675 | 1 | 41102.675 | 41150.3597 | 1 | 41150.3597 | 41180.6347 | 1
40850.3333 | 41136.6049 | 0 | 40850.3333 | 40932.6951 | 1 | 40932.6951 | 41095.6514 | 1 | 41095.6514 | 41136.6049 | 1 | 41136.6049 | 41136.6049 | 1
40850.3333 | 41173.45 | 0 | 40850.3333 | 40927.5819 | 1 | 40927.5819 | 41092.6014 | 1 | 41092.6014 | 41136.6847 | 1 | 41136.6847 | 41173.45 | 1
40850.3333 | 41159.6785 | 0 | 40850.3333 | 40934.6451 | 1 | 40934.6451 | 41114.5653 | 1 | 41114.5653 | 41159.6785 | 1 | 41159.6785 | 41159.6785 | 1
40850.3333 | 41247.6153 | 0 | 40850.3333 | 40935.3833 | 1 | 40935.3833 | 41122.5785 | 1 | 41122.5785 | 41214.5715 | 1 | 41214.5715 | 41247.6153 | 1
Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1