## Tasks
ID | Indicators | Task Mode | Task Name | Duration | Start | Finish | Predecessors | Resource Names | Unique ID Successors | Unique ID Predecessors | Unique ID
1 |  | Auto Scheduled | Kickoff Meeting | 2 | 2014-04-22 | 2014-04-24 |  |  | 2 |  | 1
2 |  | Auto Scheduled | Project-Analysis | 18 | 2014-04-24 | 2014-05-20 | 1 |  | 3 | 1 | 2
3 |  | Auto Scheduled | Analysis Task 1 | 2 | 14-04-24 | 14-04-28 |  | Consultant | 2 |  | 20971521
4 |  | Auto Scheduled | Analysis Task 2 | 4 | 14-04-28 | 14-05-02 | 1 | Consultant | 3 | 1 | 20971522
5 |  | Auto Scheduled | Analysis Task 3 | 5 | 14-05-02 | 14-05-09 | 2 | Consultant | 4 | 2 | 20971523
6 |  | Auto Scheduled | Analysis Task 4 | 7 | 14-05-09 | 14-05-20 | 3 | Consultant |  | 3 | 20971524
7 |  | Auto Scheduled | Project-Design | 52 | 2014-05-16 | 2014-07-28 | 2 |  | 5 | 2 | 3
8 |  | Auto Scheduled | Design Task 1 | 7 | 14-05-16 | 14-05-26 |  | Consultant | 2 |  | 25165825
9 |  | Auto Scheduled | Design Task 2 | 10 | 14-05-27 | 14-06-09 | 1 | Consultant | 3 | 1 | 25165826
10 |  | Auto Scheduled | Design Task 3 | 15 | 14-06-10 | 14-06-30 | 2 | Consultant | 4 | 2 | 25165827
11 |  | Auto Scheduled | Design Task 4 | 20 | 14-07-01 | 14-07-28 | 3 | Consultant | 5 | 3 | 25165828
12 |  | Auto Scheduled | Design Closed | 0 | 14-07-28 | 14-07-28 | 4 |  |  | 4 | 25165829
13 |  | Auto Scheduled | Project-Implementation | 100 | 2014-07-29 | 2014-12-15 | 3 |  |  | 3 | 5
14 |  | Auto Scheduled | Imp Task 1 | 10 | 14-07-29 | 14-08-11 |  | Dev Team | 2 |  | 29360129
15 |  | Auto Scheduled | Imp Task 2 | 20 | 14-08-12 | 14-09-08 | 1 | Dev Team | 3 | 1 | 29360130
16 |  | Auto Scheduled | Imp Task 3 | 30 | 14-09-09 | 14-10-20 | 2 | Dev Team | 4 | 2 | 29360131
17 |  | Auto Scheduled | Imp Task 4 | 40 | 14-10-21 | 14-12-15 | 3 | Dev Team |  | 3 | 29360132

## Sheet2 (hidden)
ID | Task Name | Deterministic Start | Deterministic Finish
1 | Kickoff Meeting | 2014-04-22 | 2014-04-24
2 | Project-Analysis | 2014-04-24 | 2014-08-04
3 | Analysis Task 1 | 2014-04-24 | 2014-04-28
4 | Analysis Task 2 | 2014-04-28 | 2014-05-02
5 | Analysis Task 3 | 2014-05-02 | 2014-05-09
6 | Analysis Task 4 | 2014-07-24 | 2014-08-04
7 | Project-Design | 2014-05-16 | 2014-07-24
8 | Design Task 1 | 2014-05-16 | 2014-05-26
9 | Design Task 2 | 2014-07-10 | 2014-07-24
10 | Design Task 3 | 2014-06-19 | 2014-07-10
11 | Design Task 4 | 2014-05-22 | 2014-06-19
12 | Design Closed | 2014-05-22 | 2014-05-22
13 | Project-Implementation | 2014-07-29 | 2014-12-15
14 | Imp Task 1 | 2014-07-29 | 2014-08-11
15 | Imp Task 2 | 2014-08-12 | 2014-09-08
16 | Imp Task 3 | 2014-09-09 | 2014-10-20
17 | Imp Task 4 | 2014-10-21 | 2014-12-15

## RiskCritStatData1 (hidden)
KB1647_MasterProject.mpp 1 | KB1647_MasterProject.mpp 1 | KB1647_MasterProject.mpp 1 | KB1647_MasterProject.mpp 2 | KB1647_MasterProject.mpp 2 | KB1647_MasterProject.mpp 2 | KB1647_MasterProject.mpp 8388609 | KB1647_MasterProject.mpp 8388609 | KB1647_MasterProject.mpp 8388609 | KB1647_MasterProject.mpp 8388610 | KB1647_MasterProject.mpp 8388610 | KB1647_MasterProject.mpp 8388610 | KB1647_MasterProject.mpp 8388611 | KB1647_MasterProject.mpp 8388611 | KB1647_MasterProject.mpp 8388611 | KB1647_MasterProject.mpp 8388612 | KB1647_MasterProject.mpp 8388612 | KB1647_MasterProject.mpp 8388612 | KB1647_MasterProject.mpp 3 | KB1647_MasterProject.mpp 3 | KB1647_MasterProject.mpp 3 | KB1647_MasterProject.mpp 12582913 | KB1647_MasterProject.mpp 12582913 | KB1647_MasterProject.mpp 12582913 | KB1647_MasterProject.mpp 12582914 | KB1647_MasterProject.mpp 12582914 | KB1647_MasterProject.mpp 12582914 | KB1647_MasterProject.mpp 12582915 | KB1647_MasterProject.mpp 12582915 | KB1647_MasterProject.mpp 12582915 | KB1647_MasterProject.mpp 12582916 | KB1647_MasterProject.mpp 12582916 | KB1647_MasterProject.mpp 12582916 | KB1647_MasterProject.mpp 12582917 | KB1647_MasterProject.mpp 12582917 | KB1647_MasterProject.mpp 12582917 | KB1647_MasterProject.mpp 5 | KB1647_MasterProject.mpp 5 | KB1647_MasterProject.mpp 5 | KB1647_MasterProject.mpp 16777217 | KB1647_MasterProject.mpp 16777217 | KB1647_MasterProject.mpp 16777217 | KB1647_MasterProject.mpp 16777218 | KB1647_MasterProject.mpp 16777218 | KB1647_MasterProject.mpp 16777218 | KB1647_MasterProject.mpp 16777219 | KB1647_MasterProject.mpp 16777219 | KB1647_MasterProject.mpp 16777219 | KB1647_MasterProject.mpp 16777220 | KB1647_MasterProject.mpp 16777220 | KB1647_MasterProject.mpp 16777220
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3917 | 1 | 41753.375 | 41757.4653 | 1 | 41757.4653 | 41761.4681 | 1 | 41761.4681 | 41768.4215 | 1 | 41768.4215 | 41779.3917 | 1 | 41774.6951 | 41848.6882 | 1 | 41774.6951 | 41785.7917 | 1 | 41786.3333 | 41800.5715 | 1 | 41800.5715 | 41821.5486 | 1 | 41821.5486 | 41848.6882 | 1 | 41848.6882 | 41848.6882 | 1 | 41848.3965 | 42003.4299 | 1 | 41848.3965 | 41862.7917 | 1 | 41863.3333 | 41891.5785 | 1 | 41891.5785 | 41943.4333 | 1 | 41943.4333 | 42003.4299 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3917 | 1 | 41753.375 | 41757.4653 | 1 | 41757.4653 | 41761.4681 | 1 | 41761.4681 | 41768.4215 | 1 | 41768.4215 | 41779.3917 | 1 | 41774.6951 | 41848.6882 | 1 | 41774.6951 | 41785.7917 | 1 | 41786.3333 | 41800.5715 | 1 | 41800.5715 | 41821.5486 | 1 | 41821.5486 | 41848.6882 | 1 | 41848.6882 | 41848.6882 | 1 | 41848.3965 | 42003.4299 | 1 | 41848.3965 | 41862.7917 | 1 | 41863.3333 | 41891.5785 | 1 | 41891.5785 | 41943.4333 | 1 | 41943.4333 | 42003.4299 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5701 | 1 | 41753.375 | 41757.4347 | 1 | 41757.4347 | 41761.3681 | 1 | 41761.3681 | 41767.65 | 1 | 41767.65 | 41779.5701 | 1 | 41774.6819 | 41848.6549 | 1 | 41774.6819 | 41785.7917 | 1 | 41786.3333 | 41800.4764 | 1 | 41800.4764 | 41820.7083 | 1 | 41821.3333 | 41848.6549 | 1 | 41848.6549 | 41848.6549 | 1 | 41845.3736 | 42011.3736 | 1 | 41845.3736 | 41862.7917 | 1 | 41863.3333 | 41891.3569 | 1 | 41891.3569 | 41936.3701 | 1 | 41936.3701 | 42011.3736 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5535 | 1 | 41753.375 | 41757.3583 | 1 | 41757.3583 | 41761.5799 | 1 | 41761.5799 | 41768.6097 | 1 | 41768.6097 | 41779.5535 | 1 | 41774.4431 | 41848.4333 | 1 | 41774.4431 | 41785.7917 | 1 | 41786.3333 | 41799.6715 | 1 | 41799.6715 | 41820.5847 | 1 | 41820.5847 | 41848.4333 | 1 | 41848.4333 | 41848.4333 | 1 | 41848.3431 | 41999.5514 | 1 | 41848.3431 | 41862.7917 | 1 | 41863.3333 | 41893.6681 | 1 | 41893.6681 | 41940.4264 | 1 | 41940.4264 | 41999.5514 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4583 | 1 | 41753.375 | 41757.3715 | 1 | 41757.3715 | 41761.4347 | 1 | 41761.4347 | 41768.5632 | 1 | 41768.5632 | 41779.4583 | 1 | 41774.3667 | 41851.4167 | 1 | 41774.3667 | 41785.7917 | 1 | 41786.3333 | 41801.4035 | 1 | 41801.4035 | 41822.3868 | 1 | 41822.3868 | 41851.4167 | 1 | 41851.4167 | 41851.4167 | 1 | 41844.6382 | 42024.4868 | 1 | 41844.6382 | 41862.7917 | 1 | 41863.3333 | 41893.4465 | 1 | 41893.4465 | 41943.6382 | 1 | 41943.6382 | 42024.4868 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4014 | 1 | 41753.375 | 41757.3653 | 1 | 41757.3653 | 41760.6799 | 1 | 41760.6799 | 41768.3451 | 1 | 41768.3451 | 41779.4014 | 1 | 41774.4965 | 41850.4097 | 1 | 41774.4965 | 41785.7917 | 1 | 41786.3333 | 41799.5882 | 1 | 41799.5882 | 41820.3465 | 1 | 41820.3465 | 41850.4097 | 1 | 41850.4097 | 41850.4097 | 1 | 41842.6882 | 42012.4667 | 1 | 41842.6882 | 41862.7917 | 1 | 41863.3333 | 41891.625 | 1 | 41891.625 | 41935.6382 | 1 | 41935.6382 | 42012.4667 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4583 | 1 | 41753.375 | 41757.4486 | 1 | 41757.4486 | 41761.4847 | 1 | 41761.4847 | 41768.5597 | 1 | 41768.5597 | 41779.4583 | 1 | 41775.3597 | 41845.6319 | 1 | 41775.3597 | 41785.7917 | 1 | 41786.3333 | 41799.3931 | 1 | 41799.3931 | 41817.5882 | 1 | 41817.5882 | 41845.6319 | 1 | 41845.6319 | 41845.6319 | 1 | 41848.6715 | 42012.675 | 1 | 41848.6715 | 41862.7917 | 1 | 41863.3333 | 41891.4569 | 1 | 41891.4569 | 41946.6819 | 1 | 41946.6819 | 42012.675 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5431 | 1 | 41753.375 | 41757.3347 | 1 | 41757.3347 | 41761.3653 | 1 | 41761.3653 | 41768.5799 | 1 | 41768.5799 | 41779.5431 | 1 | 41774.6847 | 41851.3431 | 1 | 41774.6847 | 41785.7917 | 1 | 41786.3333 | 41799.5715 | 1 | 41799.5715 | 41821.5618 | 1 | 41821.5618 | 41851.3431 | 1 | 41851.3431 | 41851.3431 | 1 | 41845.4465 | 42025.6514 | 1 | 41845.4465 | 41862.7917 | 1 | 41863.3333 | 41899.5819 | 1 | 41899.5819 | 41953.3764 | 1 | 41953.3764 | 42025.6514 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4181 | 1 | 41753.375 | 41757.3917 | 1 | 41757.3917 | 41761.4014 | 1 | 41761.4014 | 41768.5597 | 1 | 41768.5597 | 41780.4181 | 1 | 41774.5417 | 41848.5618 | 1 | 41774.5417 | 41785.7917 | 1 | 41786.3333 | 41799.6986 | 1 | 41799.6986 | 41822.3764 | 1 | 41822.3764 | 41848.5618 | 1 | 41848.5618 | 41848.5618 | 1 | 41844.5917 | 42017.4465 | 1 | 41844.5917 | 41862.7917 | 1 | 41863.3333 | 41892.3868 | 1 | 41892.3868 | 41943.3799 | 1 | 41943.3799 | 42017.4465 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6903 | 1 | 41753.375 | 41757.3618 | 1 | 41757.3618 | 41761.3451 | 1 | 41761.3451 | 41768.6333 | 1 | 41768.6333 | 41780.6903 | 1 | 41774.5986 | 41851.4201 | 1 | 41774.5986 | 41785.7917 | 1 | 41786.3333 | 41800.4097 | 1 | 41800.4097 | 41822.4167 | 1 | 41822.4167 | 41851.4201 | 1 | 41851.4201 | 41851.4201 | 1 | 41844.6347 | 42012.6347 | 1 | 41844.6347 | 41862.7917 | 1 | 41863.3333 | 41900.6049 | 1 | 41900.6049 | 41943.3833 | 1 | 41943.3833 | 42012.6347 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6299 | 1 | 41753.375 | 41757.4285 | 1 | 41757.4285 | 41761.5868 | 1 | 41761.5868 | 41771.3417 | 1 | 41771.3417 | 41779.6299 | 1 | 41775.45 | 41851.6347 | 1 | 41775.45 | 41785.7917 | 1 | 41786.3333 | 41800.4597 | 1 | 41800.4597 | 41823.4264 | 1 | 41823.4264 | 41851.6347 | 1 | 41851.6347 | 41851.6347 | 1 | 41843.3764 | 42004.5785 | 1 | 41843.3764 | 41862.7917 | 1 | 41863.3333 | 41893.4236 | 1 | 41893.4236 | 41943.4667 | 1 | 41943.4667 | 42004.5785 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6632 | 1 | 41753.375 | 41757.375 | 1 | 41757.375 | 41761.3681 | 1 | 41761.3681 | 41768.3681 | 1 | 41768.3681 | 41778.6632 | 1 | 41774.3632 | 41855.6514 | 1 | 41774.3632 | 41785.7917 | 1 | 41786.3333 | 41800.7014 | 1 | 41800.7014 | 41823.575 | 1 | 41823.575 | 41855.6514 | 1 | 41855.6514 | 41855.6514 | 1 | 41845.6049 | 42010.3403 | 1 | 41845.6049 | 41862.7917 | 1 | 41863.3333 | 41894.3868 | 1 | 41894.3868 | 41947.6153 | 1 | 41947.6153 | 42010.3403 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4451 | 1 | 41753.375 | 41757.4847 | 1 | 41757.4847 | 41761.3917 | 1 | 41761.3917 | 41768.6465 | 1 | 41768.6465 | 41779.4451 | 1 | 41775.4264 | 41855.4236 | 1 | 41775.4264 | 41785.7917 | 1 | 41786.3333 | 41801.3903 | 1 | 41801.3903 | 41824.5951 | 1 | 41824.5951 | 41855.4236 | 1 | 41855.4236 | 41855.4236 | 1 | 41848.6451 | 41997.6486 | 1 | 41848.6451 | 41862.7917 | 1 | 41863.3333 | 41891.4201 | 1 | 41891.4201 | 41933.5486 | 1 | 41933.5486 | 41997.6486 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3583 | 1 | 41753.375 | 41757.3847 | 1 | 41757.3847 | 41761.4215 | 1 | 41761.4215 | 41768.6431 | 1 | 41768.6431 | 41780.3583 | 1 | 41774.5951 | 41851.3931 | 1 | 41774.5951 | 41785.7917 | 1 | 41786.3333 | 41800.4799 | 1 | 41800.4799 | 41822.4403 | 1 | 41822.4403 | 41851.3931 | 1 | 41851.3931 | 41851.3931 | 1 | 41844.3833 | 42009.6181 | 1 | 41844.3833 | 41862.7917 | 1 | 41863.3333 | 41892.4569 | 1 | 41892.4569 | 41940.5882 | 1 | 41940.5882 | 42009.6181 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6667 | 1 | 41753.375 | 41757.4083 | 1 | 41757.4083 | 41761.6069 | 1 | 41761.6069 | 41768.5903 | 1 | 41768.5903 | 41779.6667 | 1 | 41774.5618 | 41849.6847 | 1 | 41774.5618 | 41785.7917 | 1 | 41786.3333 | 41801.5785 | 1 | 41801.5785 | 41823.4868 | 1 | 41823.4868 | 41849.6847 | 1 | 41849.6847 | 41849.6847 | 1 | 41848.3903 | 42016.4333 | 1 | 41848.3903 | 41862.7917 | 1 | 41863.3333 | 41897.6417 | 1 | 41897.6417 | 41941.4201 | 1 | 41941.4201 | 42016.4333 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3715 | 1 | 41753.375 | 41757.3986 | 1 | 41757.3986 | 41761.4215 | 1 | 41761.4215 | 41768.3451 | 1 | 41768.3451 | 41779.3715 | 1 | 41774.5715 | 41849.6285 | 1 | 41774.5715 | 41785.7917 | 1 | 41786.3333 | 41800.5451 | 1 | 41800.5451 | 41820.5882 | 1 | 41820.5882 | 41849.6285 | 1 | 41849.6285 | 41849.6285 | 1 | 41844.6486 | 42024.3597 | 1 | 41844.6486 | 41862.7917 | 1 | 41863.3333 | 41899.6382 | 1 | 41899.6382 | 41957.6514 | 1 | 41957.6514 | 42024.3597 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3847 | 1 | 41753.375 | 41757.3514 | 1 | 41757.3514 | 41760.7035 | 1 | 41760.7035 | 41768.6403 | 1 | 41768.6403 | 41780.3847 | 1 | 41775.3431 | 41849.675 | 1 | 41775.3431 | 41785.7917 | 1 | 41786.3333 | 41799.5986 | 1 | 41799.5986 | 41820.4965 | 1 | 41820.4965 | 41849.675 | 1 | 41849.675 | 41849.675 | 1 | 41848.3569 | 42020.4368 | 1 | 41848.3569 | 41862.7917 | 1 | 41863.3333 | 41899.5917 | 1 | 41899.5917 | 41941.6083 | 1 | 41941.6083 | 42020.4368 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6299 | 1 | 41753.375 | 41757.4653 | 1 | 41757.4653 | 41761.4653 | 1 | 41761.4653 | 41768.4785 | 1 | 41768.4785 | 41779.6299 | 1 | 41773.6715 | 41844.5549 | 1 | 41773.6715 | 41785.7917 | 1 | 41786.3333 | 41799.4465 | 1 | 41799.4465 | 41820.4333 | 1 | 41820.4333 | 41844.5549 | 1 | 41844.5549 | 41844.5549 | 1 | 41848.4403 | 42004.5715 | 1 | 41848.4403 | 41862.7917 | 1 | 41863.3333 | 41894.4597 | 1 | 41894.4597 | 41946.5986 | 1 | 41946.5986 | 42004.5715 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4049 | 1 | 41753.375 | 41757.3819 | 1 | 41757.3819 | 41761.375 | 1 | 41761.375 | 41768.4319 | 1 | 41768.4319 | 41779.4049 | 1 | 41774.6049 | 41848.3597 | 1 | 41774.6049 | 41785.7917 | 1 | 41786.3333 | 41799.4333 | 1 | 41799.4333 | 41820.3931 | 1 | 41820.3931 | 41848.3597 | 1 | 41848.3597 | 41848.3597 | 1 | 41848.5486 | 42009.4965 | 1 | 41848.5486 | 41862.7917 | 1 | 41863.3333 | 41894.5618 | 1 | 41894.5618 | 41942.7049 | 1 | 41942.7049 | 42009.4965 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6299 | 1 | 41753.375 | 41757.3847 | 1 | 41757.3847 | 41761.3917 | 1 | 41761.3917 | 41768.4285 | 1 | 41768.4285 | 41778.6299 | 1 | 41774.3535 | 41855.5917 | 1 | 41774.3535 | 41785.7917 | 1 | 41786.3333 | 41800.6014 | 1 | 41800.6014 | 41823.6986 | 1 | 41823.6986 | 41855.5917 | 1 | 41855.5917 | 41855.5917 | 1 | 41845.6181 | 42010.3403 | 1 | 41845.6181 | 41862.7917 | 1 | 41863.3333 | 41894.3535 | 1 | 41894.3535 | 41953.6049 | 1 | 41953.6049 | 42010.3403 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6465 | 1 | 41753.375 | 41754.7069 | 1 | 41754.7069 | 41760.6764 | 1 | 41760.6764 | 41767.5833 | 1 | 41767.5833 | 41778.6465 | 1 | 41775.4069 | 41849.3833 | 1 | 41775.4069 | 41785.7917 | 1 | 41786.3333 | 41800.5618 | 1 | 41800.5618 | 41820.5549 | 1 | 41820.5549 | 41849.3833 | 1 | 41849.3833 | 41849.3833 | 1 | 41844.7014 | 42004.4201 | 1 | 41844.7014 | 41862.7917 | 1 | 41863.3333 | 41894.4535 | 1 | 41894.4535 | 41942.4299 | 1 | 41942.4299 | 42004.4201 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6097 | 1 | 41753.375 | 41757.4153 | 1 | 41757.4153 | 41761.475 | 1 | 41761.475 | 41768.5431 | 1 | 41768.5431 | 41779.6097 | 1 | 41775.4264 | 41851.5549 | 1 | 41775.4264 | 41785.7917 | 1 | 41786.3333 | 41801.5882 | 1 | 41801.5882 | 41823.3931 | 1 | 41823.3931 | 41851.5549 | 1 | 41851.5549 | 41851.5549 | 1 | 41844.45 | 42006.5681 | 1 | 41844.45 | 41862.7917 | 1 | 41863.3333 | 41898.575 | 1 | 41898.575 | 41947.4264 | 1 | 41947.4264 | 42006.5681 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4715 | 1 | 41753.375 | 41757.4153 | 1 | 41757.4153 | 41761.6167 | 1 | 41761.6167 | 41771.3986 | 1 | 41771.3986 | 41780.4715 | 1 | 41774.5681 | 41850.5583 | 1 | 41774.5681 | 41785.7917 | 1 | 41786.3333 | 41800.6181 | 1 | 41800.6181 | 41822.4333 | 1 | 41822.4333 | 41850.5583 | 1 | 41850.5583 | 41850.5583 | 1 | 41845.4403 | 42002.5986 | 1 | 41845.4403 | 41862.7917 | 1 | 41863.3333 | 41891.575 | 1 | 41891.575 | 41941.4465 | 1 | 41941.4465 | 42002.5986 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4486 | 1 | 41753.375 | 41757.4181 | 1 | 41757.4181 | 41761.4347 | 1 | 41761.4347 | 41768.5833 | 1 | 41768.5833 | 41779.4486 | 1 | 41774.6514 | 41851.3535 | 1 | 41774.6514 | 41785.7917 | 1 | 41786.3333 | 41801.3868 | 1 | 41801.3868 | 41822.6715 | 1 | 41822.6715 | 41851.3535 | 1 | 41851.3535 | 41851.3535 | 1 | 41845.4167 | 42010.5951 | 1 | 41845.4167 | 41862.7917 | 1 | 41863.3333 | 41894.3931 | 1 | 41894.3931 | 41936.6083 | 1 | 41936.6083 | 42010.5951 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6132 | 1 | 41753.375 | 41757.3917 | 1 | 41757.3917 | 41761.4715 | 1 | 41761.4715 | 41768.6 | 1 | 41768.6 | 41779.6132 | 1 | 41774.6417 | 41852.4569 | 1 | 41774.6417 | 41785.7917 | 1 | 41786.3333 | 41799.4903 | 1 | 41799.4903 | 41820.5451 | 1 | 41820.5451 | 41852.4569 | 1 | 41852.4569 | 41852.4569 | 1 | 41843.5653 | 42005.6049 | 1 | 41843.5653 | 41862.7917 | 1 | 41863.3333 | 41897.4201 | 1 | 41897.4201 | 41946.6382 | 1 | 41946.6382 | 42005.6049 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5833 | 1 | 41753.375 | 41757.4382 | 1 | 41757.4382 | 41761.5535 | 1 | 41761.5535 | 41768.6465 | 1 | 41768.6465 | 41779.5833 | 1 | 41775.4333 | 41848.6118 | 1 | 41775.4333 | 41785.7917 | 1 | 41786.3333 | 41800.3597 | 1 | 41800.3597 | 41820.5 | 1 | 41820.5417 | 41848.6118 | 1 | 41848.6118 | 41848.6118 | 1 | 41845.4201 | 42006.5917 | 1 | 41845.4201 | 41862.7917 | 1 | 41863.3333 | 41901.3931 | 1 | 41901.3931 | 41943.6153 | 1 | 41943.6153 | 42006.5917 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5903 | 1 | 41753.375 | 41757.3451 | 1 | 41757.3451 | 41760.6931 | 1 | 41760.6931 | 41768.4347 | 1 | 41768.4347 | 41779.5903 | 1 | 41775.3903 | 41848.4465 | 1 | 41775.3903 | 41785.7917 | 1 | 41786.3333 | 41799.575 | 1 | 41799.575 | 41821.4333 | 1 | 41821.4333 | 41848.4465 | 1 | 41848.4465 | 41848.4465 | 1 | 41848.4535 | 42011.5618 | 1 | 41848.4535 | 41862.7917 | 1 | 41863.3333 | 41892.5847 | 1 | 41892.5847 | 41935.6417 | 1 | 41935.6417 | 42011.5618 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6903 | 1 | 41753.375 | 41754.7 | 1 | 41754.7 | 41760.6264 | 1 | 41760.6264 | 41768.4319 | 1 | 41768.4319 | 41779.6903 | 1 | 41775.3535 | 41851.6514 | 1 | 41775.3535 | 41785.7917 | 1 | 41786.3333 | 41799.7083 | 1 | 41800.3333 | 41823.4201 | 1 | 41823.4201 | 41851.6514 | 1 | 41851.6514 | 41851.6514 | 1 | 41844.4 | 42018.5715 | 1 | 41844.4 | 41862.7917 | 1 | 41863.3333 | 41897.5882 | 1 | 41897.5882 | 41946.6215 | 1 | 41946.6215 | 42018.5715 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41781.4014 | 1 | 41753.375 | 41757.4785 | 1 | 41757.4785 | 41761.4917 | 1 | 41761.4917 | 41771.425 | 1 | 41771.425 | 41781.4014 | 1 | 41774.6083 | 41851.3903 | 1 | 41774.6083 | 41785.7917 | 1 | 41786.3333 | 41800.5514 | 1 | 41800.5514 | 41822.6819 | 1 | 41822.6819 | 41851.3903 | 1 | 41851.3903 | 41851.3903 | 1 | 41848.6451 | 42004.4701 | 1 | 41848.6451 | 41862.7917 | 1 | 41863.3333 | 41892.4264 | 1 | 41892.4264 | 41939.4 | 1 | 41939.4 | 42004.4701 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4215 | 1 | 41753.375 | 41757.3819 | 1 | 41757.3819 | 41761.3653 | 1 | 41761.3653 | 41768.4181 | 1 | 41768.4181 | 41779.4215 | 1 | 41775.4465 | 41848.5819 | 1 | 41775.4465 | 41785.7917 | 1 | 41786.3333 | 41800.6417 | 1 | 41800.6417 | 41820.5583 | 1 | 41820.5583 | 41848.5819 | 1 | 41848.5819 | 41848.5819 | 1 | 41844.6819 | 42025.5917 | 1 | 41844.6819 | 41862.7917 | 1 | 41863.3333 | 41898.45 | 1 | 41898.45 | 41949.3799 | 1 | 41949.3799 | 42025.5917 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4382 | 1 | 41753.375 | 41757.3715 | 1 | 41757.3715 | 41761.3514 | 1 | 41761.3514 | 41768.4618 | 1 | 41768.4618 | 41780.4382 | 1 | 41774.6917 | 41851.4069 | 1 | 41774.6917 | 41785.7917 | 1 | 41786.3333 | 41800.3597 | 1 | 41800.3597 | 41822.6951 | 1 | 41822.6951 | 41851.4069 | 1 | 41851.4069 | 41851.4069 | 1 | 41845.7049 | 42002.7014 | 1 | 41845.7049 | 41862.7917 | 1 | 41863.3333 | 41893.5882 | 1 | 41893.5882 | 41939.6486 | 1 | 41939.6486 | 42002.7014 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.65 | 1 | 41753.375 | 41757.3715 | 1 | 41757.3715 | 41760.6764 | 1 | 41760.6764 | 41767.6569 | 1 | 41767.6569 | 41778.65 | 1 | 41775.3799 | 41856.5 | 1 | 41775.3799 | 41785.7917 | 1 | 41786.3333 | 41800.5715 | 1 | 41800.5715 | 41823.3833 | 1 | 41823.3833 | 41856.5 | 1 | 41856.5 | 41856.5 | 1 | 41848.3833 | 42004.5681 | 1 | 41848.3833 | 41862.7917 | 1 | 41863.3333 | 41891.675 | 1 | 41891.675 | 41935.4431 | 1 | 41935.4431 | 42004.5681 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.5799 | 1 | 41753.375 | 41757.4417 | 1 | 41757.4417 | 41761.5833 | 1 | 41761.5833 | 41771.3618 | 1 | 41771.3618 | 41780.5799 | 1 | 41774.5653 | 41852.3833 | 1 | 41774.5653 | 41785.7917 | 1 | 41786.3333 | 41801.3431 | 1 | 41801.3431 | 41824.675 | 1 | 41824.675 | 41852.3833 | 1 | 41852.3833 | 41852.3833 | 1 | 41843.4764 | 42006.4465 | 1 | 41843.4764 | 41862.7917 | 1 | 41863.3333 | 41894.3799 | 1 | 41894.3799 | 41936.4965 | 1 | 41936.4965 | 42006.4465 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.5931 | 1 | 41753.375 | 41757.3917 | 1 | 41757.3917 | 41761.425 | 1 | 41761.425 | 41768.7 | 1 | 41768.7 | 41780.5931 | 1 | 41774.4931 | 41848.5583 | 1 | 41774.4931 | 41785.7917 | 1 | 41786.3333 | 41800.6014 | 1 | 41800.6014 | 41821.4368 | 1 | 41821.4368 | 41848.5583 | 1 | 41848.5583 | 41848.5583 | 1 | 41848.6083 | 42004.4132 | 1 | 41848.6083 | 41862.7917 | 1 | 41863.3333 | 41891.4132 | 1 | 41891.4132 | 41941.4736 | 1 | 41941.4736 | 42004.4132 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6632 | 1 | 41753.375 | 41757.4917 | 1 | 41757.4917 | 41761.4153 | 1 | 41761.4153 | 41767.6632 | 1 | 41767.6632 | 41779.6632 | 1 | 41774.5618 | 41850.3931 | 1 | 41774.5618 | 41785.7917 | 1 | 41786.3333 | 41800.5618 | 1 | 41800.5618 | 41822.6819 | 1 | 41822.6819 | 41850.3931 | 1 | 41850.3931 | 41850.3931 | 1 | 41845.5986 | 42003.6514 | 1 | 41845.5986 | 41862.7917 | 1 | 41863.3333 | 41892.6785 | 1 | 41892.6785 | 41943.4167 | 1 | 41943.4167 | 42003.6514 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.5764 | 1 | 41753.375 | 41757.4347 | 1 | 41757.4347 | 41761.3917 | 1 | 41761.3917 | 41767.6201 | 1 | 41767.6201 | 41778.5764 | 1 | 41774.6549 | 41850.3569 | 1 | 41774.6549 | 41785.7917 | 1 | 41786.3333 | 41799.5618 | 1 | 41799.5618 | 41823.4132 | 1 | 41823.4132 | 41850.3569 | 1 | 41850.3569 | 41850.3569 | 1 | 41848.3701 | 42013.675 | 1 | 41848.3701 | 41862.7917 | 1 | 41863.3333 | 41893.3403 | 1 | 41893.3403 | 41940.3965 | 1 | 41940.3965 | 42013.675 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3347 | 1 | 41753.375 | 41757.4049 | 1 | 41757.4049 | 41761.4382 | 1 | 41761.4382 | 41767.7035 | 1 | 41767.7035 | 41779.3347 | 1 | 41774.4799 | 41850.4799 | 1 | 41774.4799 | 41785.7917 | 1 | 41786.3333 | 41801.4201 | 1 | 41801.4201 | 41822.4965 | 1 | 41822.4965 | 41850.4799 | 1 | 41850.4799 | 41850.4799 | 1 | 41848.3736 | 42012.6681 | 1 | 41848.3736 | 41862.7917 | 1 | 41863.3333 | 41891.3535 | 1 | 41891.3535 | 41942.4632 | 1 | 41942.4632 | 42012.6681 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6597 | 1 | 41753.375 | 41757.4347 | 1 | 41757.4347 | 41761.4819 | 1 | 41761.4819 | 41768.6035 | 1 | 41768.6035 | 41779.6597 | 1 | 41774.4132 | 41852.5715 | 1 | 41774.4132 | 41785.7917 | 1 | 41786.3333 | 41801.5986 | 1 | 41801.5986 | 41824.5951 | 1 | 41824.5951 | 41852.5715 | 1 | 41852.5715 | 41852.5715 | 1 | 41843.4299 | 41997.4368 | 1 | 41843.4299 | 41862.7917 | 1 | 41863.3333 | 41898.5882 | 1 | 41898.5882 | 41940.6882 | 1 | 41940.6882 | 41997.4368 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3882 | 1 | 41753.375 | 41757.3819 | 1 | 41757.3819 | 41761.4049 | 1 | 41761.4049 | 41768.6167 | 1 | 41768.6167 | 41780.3882 | 1 | 41774.5451 | 41851.5882 | 1 | 41774.5451 | 41785.7917 | 1 | 41786.3333 | 41800.4799 | 1 | 41800.4799 | 41821.6451 | 1 | 41821.6451 | 41851.5882 | 1 | 41851.5882 | 41851.5882 | 1 | 41848.6382 | 42002.3931 | 1 | 41848.6382 | 41862.7917 | 1 | 41863.3333 | 41891.5951 | 1 | 41891.5951 | 41939.5653 | 1 | 41939.5653 | 42002.3931 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4653 | 1 | 41753.375 | 41757.375 | 1 | 41757.375 | 41760.6736 | 1 | 41760.6736 | 41768.4917 | 1 | 41768.4917 | 41780.4653 | 1 | 41774.4764 | 41848.4 | 1 | 41774.4764 | 41785.7917 | 1 | 41786.3333 | 41800.4736 | 1 | 41800.4736 | 41820.4535 | 1 | 41820.4535 | 41848.4 | 1 | 41848.4 | 41848.4 | 1 | 41844.6215 | 42011.5618 | 1 | 41844.6215 | 41862.7917 | 1 | 41863.3333 | 41893.3465 | 1 | 41893.3465 | 41943.4736 | 1 | 41943.4736 | 42011.5618 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6833 | 1 | 41753.375 | 41757.4319 | 1 | 41757.4319 | 41761.6833 | 1 | 41761.6833 | 41771.3382 | 1 | 41771.3382 | 41779.6833 | 1 | 41775.4299 | 41852.5847 | 1 | 41775.4299 | 41785.7917 | 1 | 41786.3333 | 41800.5486 | 1 | 41800.5486 | 41822.4431 | 1 | 41822.4431 | 41852.5847 | 1 | 41852.5847 | 41852.5847 | 1 | 41844.6486 | 41999.6417 | 1 | 41844.6486 | 41862.7917 | 1 | 41863.3333 | 41897.4035 | 1 | 41897.4035 | 41941.6285 | 1 | 41941.6285 | 41999.6417 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6069 | 1 | 41753.375 | 41757.3847 | 1 | 41757.3847 | 41761.6167 | 1 | 41761.6167 | 41768.6035 | 1 | 41768.6035 | 41780.6069 | 1 | 41774.4667 | 41856.3368 | 1 | 41774.4667 | 41785.7917 | 1 | 41786.3333 | 41800.6917 | 1 | 41800.6917 | 41824.5715 | 1 | 41824.5715 | 41856.3368 | 1 | 41856.3368 | 41856.3368 | 1 | 41845.3799 | 42010.3535 | 1 | 41845.3799 | 41862.7917 | 1 | 41863.3333 | 41891.4299 | 1 | 41891.4299 | 41946.5653 | 1 | 41946.5653 | 42010.3535 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6097 | 1 | 41753.375 | 41757.4417 | 1 | 41757.4417 | 41761.5965 | 1 | 41761.5965 | 41768.6167 | 1 | 41768.6167 | 41779.6097 | 1 | 41774.4167 | 41850.4764 | 1 | 41774.4167 | 41785.7917 | 1 | 41786.3333 | 41799.5819 | 1 | 41799.5819 | 41820.6451 | 1 | 41820.6451 | 41850.4764 | 1 | 41850.4764 | 41850.4764 | 1 | 41842.6549 | 41998.675 | 1 | 41842.6549 | 41862.7917 | 1 | 41863.3333 | 41892.6882 | 1 | 41892.6882 | 41939.4431 | 1 | 41939.4431 | 41998.675 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6799 | 1 | 41753.375 | 41757.4549 | 1 | 41757.4549 | 41761.4785 | 1 | 41761.4785 | 41768.4819 | 1 | 41768.4819 | 41779.6799 | 1 | 41773.6951 | 41850.4597 | 1 | 41773.6951 | 41785.7917 | 1 | 41786.3333 | 41799.5486 | 1 | 41799.5486 | 41821.3535 | 1 | 41821.3535 | 41850.4597 | 1 | 41850.4597 | 41850.4597 | 1 | 41843.4368 | 42010.6951 | 1 | 41843.4368 | 41862.7917 | 1 | 41863.3333 | 41901.625 | 1 | 41901.625 | 41948.7014 | 1 | 41948.7014 | 42010.6951 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4347 | 1 | 41753.375 | 41757.4118 | 1 | 41757.4118 | 41761.6 | 1 | 41761.6 | 41768.6465 | 1 | 41768.6465 | 41779.4347 | 1 | 41774.6986 | 41850.6583 | 1 | 41774.6986 | 41785.7917 | 1 | 41786.3333 | 41800.4264 | 1 | 41800.4264 | 41822.625 | 1 | 41822.625 | 41850.6583 | 1 | 41850.6583 | 41850.6583 | 1 | 41844.3632 | 42016.5785 | 1 | 41844.3632 | 41862.7917 | 1 | 41863.3333 | 41899.6653 | 1 | 41899.6653 | 41948.6049 | 1 | 41948.6049 | 42016.5785 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6236 | 1 | 41753.375 | 41757.3715 | 1 | 41757.3715 | 41761.4882 | 1 | 41761.4882 | 41768.6764 | 1 | 41768.6764 | 41779.6236 | 1 | 41774.4236 | 41845.6319 | 1 | 41774.4236 | 41785.7917 | 1 | 41786.3333 | 41799.6319 | 1 | 41799.6319 | 41820.6215 | 1 | 41820.6215 | 41845.6319 | 1 | 41845.6319 | 41845.6319 | 1 | 41848.4632 | 42009.6014 | 1 | 41848.4632 | 41862.7917 | 1 | 41863.3333 | 41891.4097 | 1 | 41891.4097 | 41935.5951 | 1 | 41935.5951 | 42009.6014 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6965 | 1 | 41753.375 | 41757.3681 | 1 | 41757.3681 | 41761.4917 | 1 | 41761.4917 | 41768.5431 | 1 | 41768.5431 | 41779.6965 | 1 | 41775.4097 | 41849.4201 | 1 | 41775.4097 | 41785.7917 | 1 | 41786.3333 | 41799.625 | 1 | 41799.625 | 41821.4597 | 1 | 41821.4597 | 41849.4201 | 1 | 41849.4201 | 41849.4201 | 1 | 41845.4903 | 42017.5 | 1 | 41845.4903 | 41862.7917 | 1 | 41863.3333 | 41891.6618 | 1 | 41891.6618 | 41935.4333 | 1 | 41935.4333 | 42017.5 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3715 | 1 | 41753.375 | 41757.3715 | 1 | 41757.3715 | 41761.5569 | 1 | 41761.5569 | 41768.4215 | 1 | 41768.4215 | 41780.3715 | 1 | 41774.5486 | 41852.3403 | 1 | 41774.5486 | 41785.7917 | 1 | 41786.3333 | 41799.6951 | 1 | 41799.6951 | 41822.6347 | 1 | 41822.6347 | 41852.3403 | 1 | 41852.3403 | 41852.3403 | 1 | 41844.4931 | 42017.3833 | 1 | 41844.4931 | 41862.7917 | 1 | 41863.3333 | 41893.3931 | 1 | 41893.3931 | 41948.5681 | 1 | 41948.5681 | 42017.3833 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4285 | 1 | 41753.375 | 41754.7069 | 1 | 41754.7069 | 41761.4319 | 1 | 41761.4319 | 41768.3451 | 1 | 41768.3451 | 41779.4285 | 1 | 41774.4764 | 41851.3764 | 1 | 41774.4764 | 41785.7917 | 1 | 41786.3333 | 41800.4465 | 1 | 41800.4465 | 41821.6583 | 1 | 41821.6583 | 41851.3764 | 1 | 41851.3764 | 41851.3764 | 1 | 41842.5917 | 42010.4465 | 1 | 41842.5917 | 41862.7917 | 1 | 41863.3333 | 41900.3465 | 1 | 41900.3465 | 41947.5681 | 1 | 41947.5681 | 42010.4465 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3653 | 1 | 41753.375 | 41757.4014 | 1 | 41757.4014 | 41761.6097 | 1 | 41761.6097 | 41768.5965 | 1 | 41768.5965 | 41780.3653 | 1 | 41774.6118 | 41850.6819 | 1 | 41774.6118 | 41785.7917 | 1 | 41786.3333 | 41800.6153 | 1 | 41800.6153 | 41822.3931 | 1 | 41822.3931 | 41850.6819 | 1 | 41850.6819 | 41850.6819 | 1 | 41845.6319 | 42002.3701 | 1 | 41845.6319 | 41862.7917 | 1 | 41863.3333 | 41893.3799 | 1 | 41893.3799 | 41943.45 | 1 | 41943.45 | 42002.3701 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.7 | 1 | 41753.375 | 41757.4417 | 1 | 41757.4417 | 41761.5597 | 1 | 41761.5597 | 41768.5764 | 1 | 41768.5764 | 41778.7 | 1 | 41774.4035 | 41848.3569 | 1 | 41774.4035 | 41785.7917 | 1 | 41786.3333 | 41800.3868 | 1 | 41800.3868 | 41820.6583 | 1 | 41820.6583 | 41848.3569 | 1 | 41848.3569 | 41848.3569 | 1 | 41843.5653 | 42012.3868 | 1 | 41843.5653 | 41862.7917 | 1 | 41863.3333 | 41892.3701 | 1 | 41892.3701 | 41943.6514 | 1 | 41943.6514 | 42012.3868 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4514 | 1 | 41753.375 | 41757.3451 | 1 | 41757.3451 | 41761.4486 | 1 | 41761.4486 | 41768.5535 | 1 | 41768.5535 | 41779.4514 | 1 | 41775.5514 | 41852.6986 | 1 | 41775.5514 | 41785.7917 | 1 | 41786.3333 | 41801.3632 | 1 | 41801.3632 | 41824.4799 | 1 | 41824.4799 | 41852.6986 | 1 | 41852.6986 | 41852.6986 | 1 | 41848.6549 | 42011.575 | 1 | 41848.6549 | 41862.7917 | 1 | 41863.3333 | 41891.4799 | 1 | 41891.4799 | 41939.6014 | 1 | 41939.6014 | 42011.575 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4917 | 1 | 41753.375 | 41757.4049 | 1 | 41757.4049 | 41761.4847 | 1 | 41761.4847 | 41768.3583 | 1 | 41768.3583 | 41779.4917 | 1 | 41775.4465 | 41849.6319 | 1 | 41775.4465 | 41785.7917 | 1 | 41786.3333 | 41799.5451 | 1 | 41799.5451 | 41820.7049 | 1 | 41820.7049 | 41849.6319 | 1 | 41849.6319 | 41849.6319 | 1 | 41848.6486 | 41996.5986 | 1 | 41848.6486 | 41862.7917 | 1 | 41863.3333 | 41891.6549 | 1 | 41891.6549 | 41934.7014 | 1 | 41934.7014 | 41996.5986 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6569 | 1 | 41753.375 | 41757.375 | 1 | 41757.375 | 41761.4417 | 1 | 41761.4417 | 41768.4882 | 1 | 41768.4882 | 41779.6569 | 1 | 41775.35 | 41848.6118 | 1 | 41775.35 | 41785.7917 | 1 | 41786.3333 | 41800.3833 | 1 | 41800.3833 | 41820.5618 | 1 | 41820.5618 | 41848.6118 | 1 | 41848.6118 | 41848.6118 | 1 | 41848.4132 | 42018.3931 | 1 | 41848.4132 | 41862.7917 | 1 | 41863.3333 | 41899.5618 | 1 | 41899.5618 | 41953.3465 | 1 | 41953.3465 | 42018.3931 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4181 | 1 | 41753.375 | 41757.4549 | 1 | 41757.4549 | 41761.4285 | 1 | 41761.4285 | 41768.4951 | 1 | 41768.4951 | 41779.4181 | 1 | 41774.6049 | 41849.6215 | 1 | 41774.6049 | 41785.7917 | 1 | 41786.3333 | 41801.4632 | 1 | 41801.4632 | 41822.4299 | 1 | 41822.4299 | 41849.6215 | 1 | 41849.6215 | 41849.6215 | 1 | 41843.6917 | 42002.4868 | 1 | 41843.6917 | 41862.7917 | 1 | 41863.3333 | 41897.35 | 1 | 41897.35 | 41940.4465 | 1 | 41940.4465 | 42002.4868 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6403 | 1 | 41753.375 | 41757.3882 | 1 | 41757.3882 | 41761.6736 | 1 | 41761.6736 | 41768.6903 | 1 | 41768.6903 | 41779.6403 | 1 | 41774.3535 | 41852.4701 | 1 | 41774.3535 | 41785.7917 | 1 | 41786.3333 | 41799.7049 | 1 | 41799.7049 | 41822.4465 | 1 | 41822.4465 | 41852.4701 | 1 | 41852.4701 | 41852.4701 | 1 | 41848.3368 | 42003.4264 | 1 | 41848.3368 | 41862.7917 | 1 | 41863.3333 | 41891.3465 | 1 | 41891.3465 | 41939.4431 | 1 | 41939.4431 | 42003.4264 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3819 | 1 | 41753.375 | 41757.3917 | 1 | 41757.3917 | 41761.4986 | 1 | 41761.4986 | 41768.4917 | 1 | 41768.4917 | 41779.3819 | 1 | 41774.6917 | 41855.3736 | 1 | 41774.6917 | 41785.7917 | 1 | 41786.3333 | 41801.3535 | 1 | 41801.3535 | 41824.4931 | 1 | 41824.4931 | 41855.3736 | 1 | 41855.3736 | 41855.3736 | 1 | 41848.6653 | 42009.5486 | 1 | 41848.6653 | 41862.7917 | 1 | 41863.3333 | 41901.6681 | 1 | 41901.6681 | 41949.6181 | 1 | 41949.6181 | 42009.5486 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5764 | 1 | 41753.375 | 41757.4083 | 1 | 41757.4083 | 41761.4285 | 1 | 41761.4285 | 41768.4514 | 1 | 41768.4514 | 41779.5764 | 1 | 41774.4833 | 41849.4 | 1 | 41774.4833 | 41785.7917 | 1 | 41786.3333 | 41800.3465 | 1 | 41800.3465 | 41821.4368 | 1 | 41821.4368 | 41849.4 | 1 | 41849.4 | 41849.4 | 1 | 41848.4 | 42018.3667 | 1 | 41848.4 | 41862.7917 | 1 | 41863.3333 | 41893.6847 | 1 | 41893.6847 | 41942.3368 | 1 | 41942.3368 | 42018.3667 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6701 | 1 | 41753.375 | 41757.3715 | 1 | 41757.3715 | 41761.4514 | 1 | 41761.4514 | 41768.6903 | 1 | 41768.6903 | 41779.6701 | 1 | 41775.4236 | 41852.4868 | 1 | 41775.4236 | 41785.7917 | 1 | 41786.3333 | 41800.4299 | 1 | 41800.4299 | 41821.5951 | 1 | 41821.5951 | 41852.4868 | 1 | 41852.4868 | 41852.4868 | 1 | 41843.4965 | 42032.3799 | 1 | 41843.4965 | 41862.7917 | 1 | 41863.3333 | 41898.4764 | 1 | 41898.4764 | 41955.6083 | 1 | 41955.6083 | 42032.3799 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3486 | 1 | 41753.375 | 41757.3618 | 1 | 41757.3618 | 41761.4681 | 1 | 41761.4681 | 41768.4986 | 1 | 41768.4986 | 41780.3486 | 1 | 41774.5785 | 41850.4597 | 1 | 41774.5785 | 41785.7917 | 1 | 41786.3333 | 41800.4431 | 1 | 41800.4431 | 41822.4632 | 1 | 41822.4632 | 41850.4597 | 1 | 41850.4597 | 41850.4597 | 1 | 41848.3764 | 42012.4632 | 1 | 41848.3764 | 41862.7917 | 1 | 41863.3333 | 41893.3632 | 1 | 41893.3632 | 41943.4 | 1 | 41943.4 | 42012.4632 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6931 | 1 | 41753.375 | 41757.3951 | 1 | 41757.3951 | 41761.4153 | 1 | 41761.4153 | 41768.4153 | 1 | 41768.4153 | 41778.6931 | 1 | 41775.3333 | 41849.6285 | 1 | 41775.3333 | 41785.7917 | 1 | 41786.3333 | 41799.3868 | 1 | 41799.3868 | 41820.3903 | 1 | 41820.3903 | 41849.6285 | 1 | 41849.6285 | 41849.6285 | 1 | 41848.6986 | 42011.3799 | 1 | 41848.6986 | 41862.7917 | 1 | 41863.3333 | 41897.4368 | 1 | 41897.4368 | 41941.4431 | 1 | 41941.4431 | 42011.3799 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6431 | 1 | 41753.375 | 41757.4382 | 1 | 41757.4382 | 41761.6465 | 1 | 41761.6465 | 41771.4118 | 1 | 41771.4118 | 41780.6431 | 1 | 41774.4035 | 41851.6417 | 1 | 41774.4035 | 41785.7917 | 1 | 41786.3333 | 41799.4236 | 1 | 41799.4236 | 41820.6049 | 1 | 41820.6049 | 41851.6417 | 1 | 41851.6417 | 41851.6417 | 1 | 41845.6681 | 42010.6882 | 1 | 41845.6681 | 41862.7917 | 1 | 41863.3333 | 41894.5514 | 1 | 41894.5514 | 41941.4097 | 1 | 41941.4097 | 42010.6882 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4618 | 1 | 41753.375 | 41757.3847 | 1 | 41757.3847 | 41761.3951 | 1 | 41761.3951 | 41768.375 | 1 | 41768.375 | 41779.4618 | 1 | 41774.6549 | 41848.6118 | 1 | 41774.6549 | 41785.7917 | 1 | 41786.3333 | 41799.675 | 1 | 41799.675 | 41821.4035 | 1 | 41821.4035 | 41848.6118 | 1 | 41848.6118 | 41848.6118 | 1 | 41845.6917 | 42006.5618 | 1 | 41845.6917 | 41862.7917 | 1 | 41863.3333 | 41894.4 | 1 | 41894.4 | 41949.6715 | 1 | 41949.6715 | 42006.5618 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3514 | 1 | 41753.375 | 41757.425 | 1 | 41757.425 | 41761.6299 | 1 | 41761.6299 | 41768.6569 | 1 | 41768.6569 | 41780.3514 | 1 | 41774.6583 | 41850.4736 | 1 | 41774.6583 | 41785.7917 | 1 | 41786.3333 | 41799.7049 | 1 | 41799.7049 | 41822.4236 | 1 | 41822.4236 | 41850.4736 | 1 | 41850.4736 | 41850.4736 | 1 | 41848.6583 | 41992.4535 | 1 | 41848.6583 | 41862.7917 | 1 | 41863.3333 | 41891.4833 | 1 | 41891.4833 | 41936.3597 | 1 | 41936.3597 | 41992.4535 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4986 | 1 | 41753.375 | 41757.3451 | 1 | 41757.3451 | 41760.6569 | 1 | 41760.6569 | 41767.6368 | 1 | 41767.6368 | 41779.4986 | 1 | 41774.6681 | 41849.6951 | 1 | 41774.6681 | 41785.7917 | 1 | 41786.3333 | 41799.4403 | 1 | 41799.4403 | 41821.5785 | 1 | 41821.5785 | 41849.6951 | 1 | 41849.6951 | 41849.6951 | 1 | 41848.6514 | 42027.3535 | 1 | 41848.6514 | 41862.7917 | 1 | 41863.3333 | 41899.35 | 1 | 41899.35 | 41949.3431 | 1 | 41949.3431 | 42027.3535 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4382 | 1 | 41753.375 | 41757.3917 | 1 | 41757.3917 | 41760.6799 | 1 | 41760.6799 | 41768.4181 | 1 | 41768.4181 | 41779.4382 | 1 | 41773.6653 | 41850.4403 | 1 | 41773.6653 | 41785.7917 | 1 | 41786.3333 | 41801.6451 | 1 | 41801.6451 | 41822.3403 | 1 | 41822.3403 | 41850.4403 | 1 | 41850.4403 | 41850.4403 | 1 | 41848.6549 | 41996.6882 | 1 | 41848.6549 | 41862.7917 | 1 | 41863.3333 | 41891.6986 | 1 | 41891.6986 | 41940.4299 | 1 | 41940.4299 | 41996.6882 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4618 | 1 | 41753.375 | 41757.4215 | 1 | 41757.4215 | 41761.3514 | 1 | 41761.3514 | 41768.3917 | 1 | 41768.3917 | 41780.4618 | 1 | 41774.6986 | 41855.4035 | 1 | 41774.6986 | 41785.7917 | 1 | 41786.3333 | 41799.3736 | 1 | 41799.3736 | 41822.3931 | 1 | 41822.3931 | 41855.4035 | 1 | 41855.4035 | 41855.4035 | 1 | 41845.6715 | 41995.6681 | 1 | 41845.6715 | 41862.7917 | 1 | 41863.3333 | 41891.3931 | 1 | 41891.3931 | 41933.4764 | 1 | 41933.4764 | 41995.6681 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6764 | 1 | 41753.375 | 41757.3681 | 1 | 41757.3681 | 41761.4882 | 1 | 41761.4882 | 41768.6035 | 1 | 41768.6035 | 41779.6764 | 1 | 41774.6819 | 41844.4535 | 1 | 41774.6819 | 41785.7917 | 1 | 41786.3333 | 41799.3431 | 1 | 41799.3431 | 41817.675 | 1 | 41817.675 | 41844.4535 | 1 | 41844.4535 | 41844.4535 | 1 | 41843.6549 | 42025.6583 | 1 | 41843.6549 | 41862.7917 | 1 | 41863.3333 | 41899.5 | 1 | 41899.5417 | 41955.6451 | 1 | 41955.6451 | 42025.6583 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4347 | 1 | 41753.375 | 41757.3847 | 1 | 41757.3847 | 41761.4986 | 1 | 41761.4986 | 41768.4285 | 1 | 41768.4285 | 41780.4347 | 1 | 41774.3903 | 41852.575 | 1 | 41774.3903 | 41785.7917 | 1 | 41786.3333 | 41801.4931 | 1 | 41801.4931 | 41822.7014 | 1 | 41822.7014 | 41852.575 | 1 | 41852.575 | 41852.575 | 1 | 41848.6319 | 42004.4264 | 1 | 41848.6319 | 41862.7917 | 1 | 41863.3333 | 41900.4965 | 1 | 41900.4965 | 41947.6715 | 1 | 41947.6715 | 42004.4264 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.5597 | 1 | 41753.375 | 41757.3549 | 1 | 41757.3549 | 41761.3583 | 1 | 41761.3583 | 41768.6632 | 1 | 41768.6632 | 41780.5597 | 1 | 41774.5819 | 41849.6451 | 1 | 41774.5819 | 41785.7917 | 1 | 41786.3333 | 41800.4299 | 1 | 41800.4299 | 41821.6049 | 1 | 41821.6049 | 41849.6451 | 1 | 41849.6451 | 41849.6451 | 1 | 41844.4431 | 42020.4333 | 1 | 41844.4431 | 41862.7917 | 1 | 41863.3333 | 41900.5715 | 1 | 41900.5715 | 41948.6951 | 1 | 41948.6951 | 42020.4333 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6701 | 1 | 41753.375 | 41754.7 | 1 | 41754.7 | 41760.6236 | 1 | 41760.6236 | 41767.6 | 1 | 41767.6 | 41778.6701 | 1 | 41774.7014 | 41849.3965 | 1 | 41774.7014 | 41785.7917 | 1 | 41786.3333 | 41799.6181 | 1 | 41799.6181 | 41820.6681 | 1 | 41820.6681 | 41849.3965 | 1 | 41849.3965 | 41849.3965 | 1 | 41845.6785 | 42002.4264 | 1 | 41845.6785 | 41862.7917 | 1 | 41863.3333 | 41899.4868 | 1 | 41899.4868 | 41943.3799 | 1 | 41943.3799 | 42002.4264 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.5701 | 1 | 41753.375 | 41757.4486 | 1 | 41757.4486 | 41761.6201 | 1 | 41761.6201 | 41771.3715 | 1 | 41771.3715 | 41780.5701 | 1 | 41774.6951 | 41849.6347 | 1 | 41774.6951 | 41785.7917 | 1 | 41786.3333 | 41800.5583 | 1 | 41800.5583 | 41820.4431 | 1 | 41820.4431 | 41849.6347 | 1 | 41849.6347 | 41849.6347 | 1 | 41845.7014 | 42018.3736 | 1 | 41845.7014 | 41862.7917 | 1 | 41863.3333 | 41891.6819 | 1 | 41891.6819 | 41949.4903 | 1 | 41949.4903 | 42018.3736 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3681 | 1 | 41753.375 | 41757.3819 | 1 | 41757.3819 | 41760.6264 | 1 | 41760.6264 | 41767.6764 | 1 | 41767.6764 | 41779.3681 | 1 | 41775.3931 | 41851.4097 | 1 | 41775.3931 | 41785.7917 | 1 | 41786.3333 | 41801.4333 | 1 | 41801.4333 | 41823.5917 | 1 | 41823.5917 | 41851.4097 | 1 | 41851.4097 | 41851.4097 | 1 | 41845.4069 | 41996.3931 | 1 | 41845.4069 | 41862.7917 | 1 | 41863.3333 | 41897.4 | 1 | 41897.4 | 41939.4535 | 1 | 41939.4535 | 41996.3931 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.65 | 1 | 41753.375 | 41757.3486 | 1 | 41757.3486 | 41761.4882 | 1 | 41761.4882 | 41768.6069 | 1 | 41768.6069 | 41779.65 | 1 | 41775.35 | 41850.3535 | 1 | 41775.35 | 41785.7917 | 1 | 41786.3333 | 41800.3833 | 1 | 41800.3833 | 41822.6215 | 1 | 41822.6215 | 41850.3535 | 1 | 41850.3535 | 41850.3535 | 1 | 41848.3833 | 42009.6583 | 1 | 41848.3833 | 41862.7917 | 1 | 41863.3333 | 41893.3764 | 1 | 41893.3764 | 41940.6486 | 1 | 41940.6486 | 42009.6583 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4819 | 1 | 41753.375 | 41757.3951 | 1 | 41757.3951 | 41761.4083 | 1 | 41761.4083 | 41768.5701 | 1 | 41768.5701 | 41779.4819 | 1 | 41775.4236 | 41855.4597 | 1 | 41775.4236 | 41785.7917 | 1 | 41786.3333 | 41800.6451 | 1 | 41800.6451 | 41822.6785 | 1 | 41822.6785 | 41855.4597 | 1 | 41855.4597 | 41855.4597 | 1 | 41844.5951 | 42006.4903 | 1 | 41844.5951 | 41862.7917 | 1 | 41863.3333 | 41891.4868 | 1 | 41891.4868 | 41935.6882 | 1 | 41935.6882 | 42006.4903 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6632 | 1 | 41753.375 | 41757.4549 | 1 | 41757.4549 | 41761.4514 | 1 | 41761.4514 | 41768.4549 | 1 | 41768.4549 | 41778.6632 | 1 | 41774.5986 | 41850.5819 | 1 | 41774.5986 | 41785.7917 | 1 | 41786.3333 | 41799.6986 | 1 | 41799.6986 | 41820.5681 | 1 | 41820.5681 | 41850.5819 | 1 | 41850.5819 | 41850.5819 | 1 | 41845.4264 | 42012.4868 | 1 | 41845.4264 | 41862.7917 | 1 | 41863.3333 | 41891.5486 | 1 | 41891.5486 | 41947.3931 | 1 | 41947.3931 | 42012.4868 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6597 | 1 | 41753.375 | 41757.3951 | 1 | 41757.3951 | 41761.5465 | 1 | 41761.5465 | 41768.7 | 1 | 41768.7 | 41779.6597 | 1 | 41774.6681 | 41849.5514 | 1 | 41774.6681 | 41785.7917 | 1 | 41786.3333 | 41800.4167 | 1 | 41800.4167 | 41821.4236 | 1 | 41821.4236 | 41849.5514 | 1 | 41849.5514 | 41849.5514 | 1 | 41848.3333 | 42016.3799 | 1 | 41848.3333 | 41862.7917 | 1 | 41863.3333 | 41898.4833 | 1 | 41898.4833 | 41949.3667 | 1 | 41949.3667 | 42016.3799 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6931 | 1 | 41753.375 | 41757.4347 | 1 | 41757.4347 | 41761.4618 | 1 | 41761.4618 | 41768.3986 | 1 | 41768.3986 | 41778.6931 | 1 | 41774.4868 | 41849.4132 | 1 | 41774.4868 | 41785.7917 | 1 | 41786.3333 | 41800.4965 | 1 | 41800.4965 | 41821.4931 | 1 | 41821.4931 | 41849.4132 | 1 | 41849.4132 | 41849.4132 | 1 | 41845.4764 | 42004.4597 | 1 | 41845.4764 | 41862.7917 | 1 | 41863.3333 | 41898.6986 | 1 | 41898.6986 | 41943.6014 | 1 | 41943.6014 | 42004.4597 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.375 | 1 | 41753.375 | 41757.3486 | 1 | 41757.3486 | 41760.6264 | 1 | 41760.6264 | 41767.6931 | 1 | 41767.6931 | 41779.375 | 1 | 41774.6819 | 41848.6181 | 1 | 41774.6819 | 41785.7917 | 1 | 41786.3333 | 41800.6882 | 1 | 41800.6882 | 41821.4299 | 1 | 41821.4299 | 41848.6181 | 1 | 41848.6181 | 41848.6181 | 1 | 41844.6153 | 41990.6014 | 1 | 41844.6153 | 41862.7917 | 1 | 41863.3333 | 41891.3701 | 1 | 41891.3701 | 41934.4569 | 1 | 41934.4569 | 41990.6014 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3347 | 1 | 41753.375 | 41754.6965 | 1 | 41754.6965 | 41761.3382 | 1 | 41761.3382 | 41767.6 | 1 | 41767.6 | 41779.3347 | 1 | 41774.6583 | 41850.6785 | 1 | 41774.6583 | 41785.7917 | 1 | 41786.3333 | 41800.5549 | 1 | 41800.5549 | 41822.4167 | 1 | 41822.4167 | 41850.6785 | 1 | 41850.6785 | 41850.6785 | 1 | 41844.3931 | 42013.6715 | 1 | 41844.3931 | 41862.7917 | 1 | 41863.3333 | 41891.5681 | 1 | 41891.5681 | 41948.3465 | 1 | 41948.3465 | 42013.6715 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4382 | 1 | 41753.375 | 41757.4681 | 1 | 41757.4681 | 41761.4618 | 1 | 41761.4618 | 41771.3882 | 1 | 41771.3882 | 41780.4382 | 1 | 41775.4764 | 41856.4965 | 1 | 41775.4764 | 41785.7917 | 1 | 41786.3333 | 41800.575 | 1 | 41800.575 | 41824.35 | 1 | 41824.35 | 41856.4965 | 1 | 41856.4965 | 41856.4965 | 1 | 41848.5618 | 41999.5 | 1 | 41848.5618 | 41862.7917 | 1 | 41863.3333 | 41897.6951 | 1 | 41897.6951 | 41940.4431 | 1 | 41940.4431 | 41999.5 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6764 | 1 | 41753.375 | 41757.4785 | 1 | 41757.4785 | 41761.6167 | 1 | 41761.6167 | 41771.3417 | 1 | 41771.3417 | 41780.6764 | 1 | 41775.4236 | 41848.3736 | 1 | 41775.4236 | 41785.7917 | 1 | 41786.3333 | 41800.45 | 1 | 41800.45 | 41820.3903 | 1 | 41820.3903 | 41848.3736 | 1 | 41848.3736 | 41848.3736 | 1 | 41845.4368 | 42013.6118 | 1 | 41845.4368 | 41862.7917 | 1 | 41863.3333 | 41898.3431 | 1 | 41898.3431 | 41947.675 | 1 | 41947.675 | 42013.6118 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5903 | 1 | 41753.375 | 41757.425 | 1 | 41757.425 | 41761.3653 | 1 | 41761.3653 | 41768.6868 | 1 | 41768.6868 | 41779.5903 | 1 | 41775.3569 | 41850.5951 | 1 | 41775.3569 | 41785.7917 | 1 | 41786.3333 | 41800.3632 | 1 | 41800.3632 | 41822.6181 | 1 | 41822.6181 | 41850.5951 | 1 | 41850.5951 | 41850.5951 | 1 | 41844.5653 | 42003.5951 | 1 | 41844.5653 | 41862.7917 | 1 | 41863.3333 | 41897.6514 | 1 | 41897.6514 | 41943.6451 | 1 | 41943.6451 | 42003.5951 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5736 | 1 | 41753.375 | 41757.3549 | 1 | 41757.3549 | 41761.3382 | 1 | 41761.3382 | 41768.4847 | 1 | 41768.4847 | 41779.5736 | 1 | 41774.6785 | 41848.6285 | 1 | 41774.6785 | 41785.7917 | 1 | 41786.3333 | 41799.6882 | 1 | 41799.6882 | 41820.5618 | 1 | 41820.5618 | 41848.6285 | 1 | 41848.6285 | 41848.6285 | 1 | 41848.5986 | 42010.3868 | 1 | 41848.5986 | 41862.7917 | 1 | 41863.3333 | 41897.4167 | 1 | 41897.4167 | 41941.4097 | 1 | 41941.4097 | 42010.3868 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4618 | 1 | 41753.375 | 41757.3549 | 1 | 41757.3549 | 41761.4181 | 1 | 41761.4181 | 41768.6465 | 1 | 41768.6465 | 41780.4618 | 1 | 41775.5618 | 41856.5618 | 1 | 41775.5618 | 41785.7917 | 1 | 41786.3333 | 41800.5653 | 1 | 41800.5653 | 41823.6382 | 1 | 41823.6382 | 41856.5618 | 1 | 41856.5618 | 41856.5618 | 1 | 41842.6451 | 42018.3965 | 1 | 41842.6451 | 41862.7917 | 1 | 41863.3333 | 41893.3903 | 1 | 41893.3903 | 41947.6618 | 1 | 41947.6618 | 42018.3965 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6764 | 1 | 41753.375 | 41757.4451 | 1 | 41757.4451 | 41761.6264 | 1 | 41761.6264 | 41771.4347 | 1 | 41771.4347 | 41779.6764 | 1 | 41775.4333 | 41851.6951 | 1 | 41775.4333 | 41785.7917 | 1 | 41786.3333 | 41799.5 | 1 | 41799.5417 | 41821.4035 | 1 | 41821.4035 | 41851.6951 | 1 | 41851.6951 | 41851.6951 | 1 | 41845.6215 | 42012.6049 | 1 | 41845.6215 | 41862.7917 | 1 | 41863.3333 | 41894.4667 | 1 | 41894.4667 | 41950.4903 | 1 | 41950.4903 | 42012.6049 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6368 | 1 | 41753.375 | 41757.4882 | 1 | 41757.4882 | 41761.4882 | 1 | 41761.4882 | 41768.6799 | 1 | 41768.6799 | 41780.6368 | 1 | 41775.3431 | 41848.6653 | 1 | 41775.3431 | 41785.7917 | 1 | 41786.3333 | 41800.4931 | 1 | 41800.4931 | 41821.3632 | 1 | 41821.3632 | 41848.6653 | 1 | 41848.6653 | 41848.6653 | 1 | 41844.6451 | 42024.6049 | 1 | 41844.6451 | 41862.7917 | 1 | 41863.3333 | 41892.4403 | 1 | 41892.4403 | 41949.3965 | 1 | 41949.3965 | 42024.6049 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4951 | 1 | 41753.375 | 41757.3847 | 1 | 41757.3847 | 41761.3382 | 1 | 41761.3382 | 41768.3882 | 1 | 41768.3882 | 41779.4951 | 1 | 41775.3764 | 41849.4035 | 1 | 41775.3764 | 41785.7917 | 1 | 41786.3333 | 41800.6486 | 1 | 41800.6486 | 41821.6819 | 1 | 41821.6819 | 41849.4035 | 1 | 41849.4035 | 41849.4035 | 1 | 41844.35 | 42013.45 | 1 | 41844.35 | 41862.7917 | 1 | 41863.3333 | 41900.6215 | 1 | 41900.6215 | 41947.4264 | 1 | 41947.4264 | 42013.45 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5597 | 1 | 41753.375 | 41757.3819 | 1 | 41757.3819 | 41761.5931 | 1 | 41761.5931 | 41768.5833 | 1 | 41768.5833 | 41779.5597 | 1 | 41774.4201 | 41850.5653 | 1 | 41774.4201 | 41785.7917 | 1 | 41786.3333 | 41799.6382 | 1 | 41799.6382 | 41821.7014 | 1 | 41821.7014 | 41850.5653 | 1 | 41850.5653 | 41850.5653 | 1 | 41848.6417 | 42013.5 | 1 | 41848.6417 | 41862.7917 | 1 | 41863.3333 | 41891.4333 | 1 | 41891.4333 | 41947.6785 | 1 | 41947.6785 | 42013.5 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4819 | 1 | 41753.375 | 41757.4049 | 1 | 41757.4049 | 41761.4986 | 1 | 41761.4986 | 41768.6535 | 1 | 41768.6535 | 41780.4819 | 1 | 41774.6847 | 41845.6486 | 1 | 41774.6847 | 41785.7917 | 1 | 41786.3333 | 41799.6319 | 1 | 41799.6319 | 41820.3833 | 1 | 41820.3833 | 41845.6486 | 1 | 41845.6486 | 41845.6486 | 1 | 41843.3403 | 42005.3535 | 1 | 41843.3403 | 41862.7917 | 1 | 41863.3333 | 41894.4799 | 1 | 41894.4799 | 41943.4632 | 1 | 41943.4632 | 42005.3535 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3715 | 1 | 41753.375 | 41757.3715 | 1 | 41757.3715 | 41761.3882 | 1 | 41761.3882 | 41768.6368 | 1 | 41768.6368 | 41780.3715 | 1 | 41774.4632 | 41849.6118 | 1 | 41774.4632 | 41785.7917 | 1 | 41786.3333 | 41799.6882 | 1 | 41799.6882 | 41821.4069 | 1 | 41821.4069 | 41849.6118 | 1 | 41849.6118 | 41849.6118 | 1 | 41848.4701 | 42002.3368 | 1 | 41848.4701 | 41862.7917 | 1 | 41863.3333 | 41892.4667 | 1 | 41892.4667 | 41935.6014 | 1 | 41935.6014 | 42002.3368 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6799 | 1 | 41753.375 | 41757.425 | 1 | 41757.425 | 41761.475 | 1 | 41761.475 | 41768.4382 | 1 | 41768.4382 | 41778.6799 | 1 | 41774.6285 | 41851.4632 | 1 | 41774.6285 | 41785.7917 | 1 | 41786.3333 | 41800.6583 | 1 | 41800.6583 | 41822.575 | 1 | 41822.575 | 41851.4632 | 1 | 41851.4632 | 41851.4632 | 1 | 41844.3333 | 42016.3667 | 1 | 41844.3333 | 41862.7917 | 1 | 41863.3333 | 41900.6319 | 1 | 41900.6319 | 41943.5583 | 1 | 41943.5583 | 42016.3667 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.55 | 1 | 41753.375 | 41757.4819 | 1 | 41757.4819 | 41761.4785 | 1 | 41761.4785 | 41768.475 | 1 | 41768.475 | 41779.55 | 1 | 41774.6118 | 41850.4569 | 1 | 41774.6118 | 41785.7917 | 1 | 41786.3333 | 41801.5583 | 1 | 41801.5583 | 41822.3368 | 1 | 41822.3368 | 41850.4569 | 1 | 41850.4569 | 41850.4569 | 1 | 41845.4368 | 42002.6819 | 1 | 41845.4368 | 41862.7917 | 1 | 41863.3333 | 41893.4833 | 1 | 41893.4833 | 41943.4632 | 1 | 41943.4632 | 42002.6819 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.5764 | 1 | 41753.375 | 41757.3715 | 1 | 41757.3715 | 41760.6931 | 1 | 41760.6931 | 41768.3514 | 1 | 41768.3514 | 41778.5764 | 1 | 41774.6847 | 41851.4368 | 1 | 41774.6847 | 41785.7917 | 1 | 41786.3333 | 41801.4569 | 1 | 41801.4569 | 41822.675 | 1 | 41822.675 | 41851.4368 | 1 | 41851.4368 | 41851.4368 | 1 | 41845.6083 | 42002.3403 | 1 | 41845.6083 | 41862.7917 | 1 | 41863.3333 | 41892.5653 | 1 | 41892.5653 | 41942.3403 | 1 | 41942.3403 | 42002.3403 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4514 | 1 | 41753.375 | 41757.4083 | 1 | 41757.4083 | 41761.6403 | 1 | 41761.6403 | 41771.4951 | 1 | 41771.4951 | 41780.4514 | 1 | 41774.675 | 41856.6382 | 1 | 41774.675 | 41785.7917 | 1 | 41786.3333 | 41801.4868 | 1 | 41801.4868 | 41824.3535 | 1 | 41824.3535 | 41856.6382 | 1 | 41856.6382 | 41856.6382 | 1 | 41845.4299 | 42004.5951 | 1 | 41845.4299 | 41862.7917 | 1 | 41863.3333 | 41891.5847 | 1 | 41891.5847 | 41942.5917 | 1 | 41942.5917 | 42004.5951 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6264 | 1 | 41753.375 | 41757.3847 | 1 | 41757.3847 | 41761.5931 | 1 | 41761.5931 | 41768.6931 | 1 | 41768.6931 | 41779.6264 | 1 | 41774.6882 | 41851.6181 | 1 | 41774.6882 | 41785.7917 | 1 | 41786.3333 | 41801.6618 | 1 | 41801.6618 | 41823.3701 | 1 | 41823.3701 | 41851.6181 | 1 | 41851.6181 | 41851.6181 | 1 | 41845.5549 | 42018.3965 | 1 | 41845.5549 | 41862.7917 | 1 | 41863.3333 | 41897.6014 | 1 | 41897.6014 | 41957.4 | 1 | 41957.4 | 42018.3965 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6299 | 1 | 41753.375 | 41757.3417 | 1 | 41757.3417 | 41761.3951 | 1 | 41761.3951 | 41768.3451 | 1 | 41768.3451 | 41778.6299 | 1 | 41774.6347 | 41850.6847 | 1 | 41774.6347 | 41785.7917 | 1 | 41786.3333 | 41800.6451 | 1 | 41800.6451 | 41824.3736 | 1 | 41824.3736 | 41850.6847 | 1 | 41850.6847 | 41850.6847 | 1 | 41843.3903 | 42010.5785 | 1 | 41843.3903 | 41862.7917 | 1 | 41863.3333 | 41893.4333 | 1 | 41893.4333 | 41942.6882 | 1 | 41942.6882 | 42010.5785 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4785 | 1 | 41753.375 | 41757.3681 | 1 | 41757.3681 | 41761.4882 | 1 | 41761.4882 | 41768.4785 | 1 | 41768.4785 | 41779.4785 | 1 | 41774.4597 | 41852.3431 | 1 | 41774.4597 | 41785.7917 | 1 | 41786.3333 | 41800.5486 | 1 | 41800.5486 | 41822.3569 | 1 | 41822.3569 | 41852.3431 | 1 | 41852.3431 | 41852.3431 | 1 | 41848.4264 | 42018.4403 | 1 | 41848.4264 | 41862.7917 | 1 | 41863.3333 | 41891.6681 | 1 | 41891.6681 | 41946.4931 | 1 | 41946.4931 | 42018.4403 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6465 | 1 | 41753.375 | 41757.4382 | 1 | 41757.4382 | 41761.5965 | 1 | 41761.5965 | 41771.475 | 1 | 41771.475 | 41780.6465 | 1 | 41775.4569 | 41850.6882 | 1 | 41775.4569 | 41785.7917 | 1 | 41786.3333 | 41799.3632 | 1 | 41799.3632 | 41820.6785 | 1 | 41820.6785 | 41850.6882 | 1 | 41850.6882 | 41850.6882 | 1 | 41845.3632 | 42002.3833 | 1 | 41845.3632 | 41862.7917 | 1 | 41863.3333 | 41898.3667 | 1 | 41898.3667 | 41943.4535 | 1 | 41943.4535 | 42002.3833 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4382 | 1 | 41753.375 | 41757.4347 | 1 | 41757.4347 | 41761.3382 | 1 | 41761.3382 | 41768.4417 | 1 | 41768.4417 | 41779.4382 | 1 | 41775.5451 | 41850.4035 | 1 | 41775.5451 | 41785.7917 | 1 | 41786.3333 | 41800.4799 | 1 | 41800.4799 | 41822.4236 | 1 | 41822.4236 | 41850.4035 | 1 | 41850.4035 | 41850.4035 | 1 | 41848.4597 | 42017.5583 | 1 | 41848.4597 | 41862.7917 | 1 | 41863.3333 | 41901.5 | 1 | 41901.5417 | 41946.4132 | 1 | 41946.4132 | 42017.5583 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6597 | 1 | 41753.375 | 41757.3951 | 1 | 41757.3951 | 41761.4986 | 1 | 41761.4986 | 41768.4653 | 1 | 41768.4653 | 41778.6597 | 1 | 41773.6486 | 41849.5847 | 1 | 41773.6486 | 41785.7917 | 1 | 41786.3333 | 41799.6014 | 1 | 41799.6014 | 41820.3597 | 1 | 41820.3597 | 41849.5847 | 1 | 41849.5847 | 41849.5847 | 1 | 41848.3535 | 42012.5583 | 1 | 41848.3535 | 41862.7917 | 1 | 41863.3333 | 41891.5917 | 1 | 41891.5917 | 41942.5514 | 1 | 41942.5514 | 42012.5583 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4819 | 1 | 41753.375 | 41757.3549 | 1 | 41757.3549 | 41760.6701 | 1 | 41760.6701 | 41768.3882 | 1 | 41768.3882 | 41779.4819 | 1 | 41774.4868 | 41849.675 | 1 | 41774.4868 | 41785.7917 | 1 | 41786.3333 | 41801.5681 | 1 | 41801.5681 | 41822.5 | 1 | 41822.5417 | 41849.675 | 1 | 41849.675 | 41849.675 | 1 | 41842.5549 | 42030.6618 | 1 | 41842.5549 | 41862.7917 | 1 | 41863.3333 | 41898.5583 | 1 | 41898.5583 | 41947.3931 | 1 | 41947.3931 | 42030.6618 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.475 | 1 | 41753.375 | 41754.6965 | 1 | 41754.6965 | 41760.6736 | 1 | 41760.6736 | 41768.6132 | 1 | 41768.6132 | 41779.475 | 1 | 41774.6549 | 41848.4069 | 1 | 41774.6549 | 41785.7917 | 1 | 41786.3333 | 41800.4236 | 1 | 41800.4236 | 41821.4736 | 1 | 41821.4736 | 41848.4069 | 1 | 41848.4069 | 41848.4069 | 1 | 41844.7014 | 42024.4833 | 1 | 41844.7014 | 41862.7917 | 1 | 41863.3333 | 41898.5514 | 1 | 41898.5514 | 41955.4431 | 1 | 41955.4431 | 42024.4833 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4951 | 1 | 41753.375 | 41757.425 | 1 | 41757.425 | 41761.4382 | 1 | 41761.4382 | 41768.4319 | 1 | 41768.4319 | 41780.4951 | 1 | 41774.4535 | 41848.625 | 1 | 41774.4535 | 41785.7917 | 1 | 41786.3333 | 41800.575 | 1 | 41800.575 | 41821.6083 | 1 | 41821.6083 | 41848.625 | 1 | 41848.625 | 41848.625 | 1 | 41844.7049 | 42010.6514 | 1 | 41844.7049 | 41862.7917 | 1 | 41863.3333 | 41894.5819 | 1 | 41894.5819 | 41941.5 | 1 | 41941.5417 | 42010.6514 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5903 | 1 | 41753.375 | 41757.4014 | 1 | 41757.4014 | 41761.4014 | 1 | 41761.4014 | 41768.5535 | 1 | 41768.5535 | 41779.5903 | 1 | 41774.3465 | 41850.6653 | 1 | 41774.3465 | 41785.7917 | 1 | 41786.3333 | 41799.6382 | 1 | 41799.6382 | 41822.4097 | 1 | 41822.4097 | 41850.6653 | 1 | 41850.6653 | 41850.6653 | 1 | 41842.6319 | 41999.4201 | 1 | 41842.6319 | 41862.7917 | 1 | 41863.3333 | 41893.6181 | 1 | 41893.6181 | 41939.4965 | 1 | 41939.4965 | 41999.4201 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4917 | 1 | 41753.375 | 41757.4319 | 1 | 41757.4319 | 41761.4847 | 1 | 41761.4847 | 41768.5931 | 1 | 41768.5931 | 41780.4917 | 1 | 41775.3597 | 41855.4833 | 1 | 41775.3597 | 41785.7917 | 1 | 41786.3333 | 41800.3736 | 1 | 41800.3736 | 41822.4833 | 1 | 41822.4833 | 41855.4833 | 1 | 41855.4833 | 41855.4833 | 1 | 41845.5715 | 42017.3597 | 1 | 41845.5715 | 41862.7917 | 1 | 41863.3333 | 41898.35 | 1 | 41898.35 | 41950.6882 | 1 | 41950.6882 | 42017.3597 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4215 | 1 | 41753.375 | 41757.3951 | 1 | 41757.3951 | 41761.375 | 1 | 41761.375 | 41767.6736 | 1 | 41767.6736 | 41779.4215 | 1 | 41774.5486 | 41849.5785 | 1 | 41774.5486 | 41785.7917 | 1 | 41786.3333 | 41800.4333 | 1 | 41800.4333 | 41821.3667 | 1 | 41821.3667 | 41849.5785 | 1 | 41849.5785 | 41849.5785 | 1 | 41843.6618 | 42011.4701 | 1 | 41843.6618 | 41862.7917 | 1 | 41863.3333 | 41893.4097 | 1 | 41893.4097 | 41948.6118 | 1 | 41948.6118 | 42011.4701 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3514 | 1 | 41753.375 | 41757.3653 | 1 | 41757.3653 | 41760.7 | 1 | 41760.7 | 41768.3417 | 1 | 41768.3417 | 41779.3514 | 1 | 41774.6549 | 41852.3764 | 1 | 41774.6549 | 41785.7917 | 1 | 41786.3333 | 41800.5785 | 1 | 41800.5785 | 41823.3764 | 1 | 41823.3764 | 41852.3764 | 1 | 41852.3764 | 41852.3764 | 1 | 41848.4799 | 42005.4236 | 1 | 41848.4799 | 41862.7917 | 1 | 41863.3333 | 41893.4764 | 1 | 41893.4764 | 41941.5819 | 1 | 41941.5819 | 42005.4236 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4319 | 1 | 41753.375 | 41757.4715 | 1 | 41757.4715 | 41761.4215 | 1 | 41761.4215 | 41768.4514 | 1 | 41768.4514 | 41779.4319 | 1 | 41774.4965 | 41850.6917 | 1 | 41774.4965 | 41785.7917 | 1 | 41786.3333 | 41801.4903 | 1 | 41801.4903 | 41822.6882 | 1 | 41822.6882 | 41850.6917 | 1 | 41850.6917 | 41850.6917 | 1 | 41848.4903 | 42024.6153 | 1 | 41848.4903 | 41862.7917 | 1 | 41863.3333 | 41892.3736 | 1 | 41892.3736 | 41947.4868 | 1 | 41947.4868 | 42024.6153 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6931 | 1 | 41753.375 | 41757.4285 | 1 | 41757.4285 | 41764.3549 | 1 | 41764.3549 | 41768.7 | 1 | 41768.7 | 41780.6931 | 1 | 41774.6951 | 41851.6618 | 1 | 41774.6951 | 41785.7917 | 1 | 41786.3333 | 41800.4965 | 1 | 41800.4965 | 41822.6986 | 1 | 41822.6986 | 41851.6618 | 1 | 41851.6618 | 41851.6618 | 1 | 41848.4264 | 42002.4097 | 1 | 41848.4264 | 41862.7917 | 1 | 41863.3333 | 41897.5514 | 1 | 41897.5514 | 41941.6451 | 1 | 41941.6451 | 42002.4097 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6736 | 1 | 41753.375 | 41757.4319 | 1 | 41757.4319 | 41761.4785 | 1 | 41761.4785 | 41768.65 | 1 | 41768.65 | 41779.6736 | 1 | 41775.3632 | 41852.6285 | 1 | 41775.3632 | 41785.7917 | 1 | 41786.3333 | 41801.3736 | 1 | 41801.3736 | 41824.4368 | 1 | 41824.4368 | 41852.6285 | 1 | 41852.6285 | 41852.6285 | 1 | 41848.4333 | 42002.3632 | 1 | 41848.4333 | 41862.7917 | 1 | 41863.3333 | 41897.3597 | 1 | 41897.3597 | 41939.6917 | 1 | 41939.6917 | 42002.3632 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6069 | 1 | 41753.375 | 41757.4083 | 1 | 41757.4083 | 41761.3583 | 1 | 41761.3583 | 41768.5965 | 1 | 41768.5965 | 41780.6069 | 1 | 41775.4069 | 41852.4431 | 1 | 41775.4069 | 41785.7917 | 1 | 41786.3333 | 41800.4 | 1 | 41800.4 | 41821.3368 | 1 | 41821.3368 | 41852.4431 | 1 | 41852.4431 | 41852.4431 | 1 | 41845.6819 | 41999.6486 | 1 | 41845.6819 | 41862.7917 | 1 | 41863.3333 | 41897.6583 | 1 | 41897.6583 | 41942.6514 | 1 | 41942.6514 | 41999.6486 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3486 | 1 | 41753.375 | 41757.3549 | 1 | 41757.3549 | 41761.3583 | 1 | 41761.3583 | 41768.4486 | 1 | 41768.4486 | 41779.3486 | 1 | 41774.6847 | 41851.4069 | 1 | 41774.6847 | 41785.7917 | 1 | 41786.3333 | 41800.5 | 1 | 41800.5417 | 41821.3368 | 1 | 41821.3368 | 41851.4069 | 1 | 41851.4069 | 41851.4069 | 1 | 41848.3903 | 42004.4097 | 1 | 41848.3903 | 41862.7917 | 1 | 41863.3333 | 41892.625 | 1 | 41892.625 | 41940.6847 | 1 | 41940.6847 | 42004.4097 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5799 | 1 | 41753.375 | 41757.4215 | 1 | 41757.4215 | 41761.475 | 1 | 41761.475 | 41768.6597 | 1 | 41768.6597 | 41779.5799 | 1 | 41774.7049 | 41851.6819 | 1 | 41774.7049 | 41785.7917 | 1 | 41786.3333 | 41799.6681 | 1 | 41799.6681 | 41823.4167 | 1 | 41823.4167 | 41851.6819 | 1 | 41851.6819 | 41851.6819 | 1 | 41845.5583 | 42012.6653 | 1 | 41845.5583 | 41862.7917 | 1 | 41863.3333 | 41892.4069 | 1 | 41892.4069 | 41943.4632 | 1 | 41943.4632 | 42012.6653 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6569 | 1 | 41753.375 | 41757.3819 | 1 | 41757.3819 | 41760.6868 | 1 | 41760.6868 | 41768.4382 | 1 | 41768.4382 | 41779.6569 | 1 | 41775.5653 | 41848.6083 | 1 | 41775.5653 | 41785.7917 | 1 | 41786.3333 | 41800.3431 | 1 | 41800.3431 | 41820.7049 | 1 | 41820.7049 | 41848.6083 | 1 | 41848.6083 | 41848.6083 | 1 | 41842.4167 | 42016.4597 | 1 | 41842.4167 | 41862.7917 | 1 | 41863.3333 | 41897.6653 | 1 | 41897.6653 | 41948.6917 | 1 | 41948.6917 | 42016.4597 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.4951 | 1 | 41753.375 | 41754.7035 | 1 | 41754.7035 | 41760.6931 | 1 | 41760.6931 | 41767.5597 | 1 | 41767.5597 | 41778.4951 | 1 | 41775.3431 | 41851.7049 | 1 | 41775.3431 | 41785.7917 | 1 | 41786.3333 | 41801.4736 | 1 | 41801.4736 | 41824.3431 | 1 | 41824.3431 | 41851.7049 | 1 | 41851.7049 | 41851.7049 | 1 | 41845.4236 | 42009.6681 | 1 | 41845.4236 | 41862.7917 | 1 | 41863.3333 | 41893.3868 | 1 | 41893.3868 | 41940.4569 | 1 | 41940.4569 | 42009.6681 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6097 | 1 | 41753.375 | 41757.4014 | 1 | 41757.4014 | 41761.4785 | 1 | 41761.4785 | 41768.6431 | 1 | 41768.6431 | 41779.6097 | 1 | 41774.675 | 41851.4431 | 1 | 41774.675 | 41785.7917 | 1 | 41786.3333 | 41799.4535 | 1 | 41799.4535 | 41822.6819 | 1 | 41822.6819 | 41851.4431 | 1 | 41851.4431 | 41851.4431 | 1 | 41848.6819 | 42003.6083 | 1 | 41848.6819 | 41862.7917 | 1 | 41863.3333 | 41891.4264 | 1 | 41891.4264 | 41934.7049 | 1 | 41934.7049 | 42003.6083 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3847 | 1 | 41753.375 | 41757.4153 | 1 | 41757.4153 | 41761.3618 | 1 | 41761.3618 | 41768.3986 | 1 | 41768.3986 | 41779.3847 | 1 | 41775.4833 | 41855.6549 | 1 | 41775.4833 | 41785.7917 | 1 | 41786.3333 | 41800.4035 | 1 | 41800.4035 | 41822.4333 | 1 | 41822.4333 | 41855.6549 | 1 | 41855.6549 | 41855.6549 | 1 | 41848.4597 | 42013.6382 | 1 | 41848.4597 | 41862.7917 | 1 | 41863.3333 | 41894.5986 | 1 | 41894.5986 | 41936.675 | 1 | 41936.675 | 42013.6382 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4583 | 1 | 41753.375 | 41757.3882 | 1 | 41757.3882 | 41760.7 | 1 | 41760.7 | 41767.5632 | 1 | 41767.5632 | 41779.4583 | 1 | 41774.4465 | 41849.6118 | 1 | 41774.4465 | 41785.7917 | 1 | 41786.3333 | 41800.3403 | 1 | 41800.3403 | 41821.4597 | 1 | 41821.4597 | 41849.6118 | 1 | 41849.6118 | 41849.6118 | 1 | 41845.6819 | 42013.6514 | 1 | 41845.6819 | 41862.7917 | 1 | 41863.3333 | 41898.4868 | 1 | 41898.4868 | 41947.5715 | 1 | 41947.5715 | 42013.6514 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4653 | 1 | 41753.375 | 41757.4118 | 1 | 41757.4118 | 41761.4618 | 1 | 41761.4618 | 41768.4347 | 1 | 41768.4347 | 41779.4653 | 1 | 41773.6285 | 41852.6785 | 1 | 41773.6285 | 41785.7917 | 1 | 41786.3333 | 41800.6986 | 1 | 41800.6986 | 41822.35 | 1 | 41822.35 | 41852.6785 | 1 | 41852.6785 | 41852.6785 | 1 | 41848.5653 | 42019.6785 | 1 | 41848.5653 | 41862.7917 | 1 | 41863.3333 | 41897.6847 | 1 | 41897.6847 | 41953.4597 | 1 | 41953.4597 | 42019.6785 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4083 | 1 | 41753.375 | 41757.3882 | 1 | 41757.3882 | 41761.4083 | 1 | 41761.4083 | 41768.5632 | 1 | 41768.5632 | 41779.4083 | 1 | 41774.6882 | 41850.3903 | 1 | 41774.6882 | 41785.7917 | 1 | 41786.3333 | 41800.3535 | 1 | 41800.3535 | 41822.4965 | 1 | 41822.4965 | 41850.3903 | 1 | 41850.3903 | 41850.3903 | 1 | 41848.5681 | 41997.4833 | 1 | 41848.5681 | 41862.7917 | 1 | 41863.3333 | 41891.6118 | 1 | 41891.6118 | 41934.675 | 1 | 41934.675 | 41997.4833 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4382 | 1 | 41753.375 | 41757.3951 | 1 | 41757.3951 | 41761.4549 | 1 | 41761.4549 | 41768.4451 | 1 | 41768.4451 | 41779.4382 | 1 | 41774.3569 | 41852.6986 | 1 | 41774.3569 | 41785.7917 | 1 | 41786.3333 | 41799.7083 | 1 | 41800.3333 | 41823.3799 | 1 | 41823.3799 | 41852.6986 | 1 | 41852.6986 | 41852.6986 | 1 | 41848.3632 | 42003.4431 | 1 | 41848.3632 | 41862.7917 | 1 | 41863.3333 | 41891.6847 | 1 | 41891.6847 | 41942.4701 | 1 | 41942.4701 | 42003.4431 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.425 | 1 | 41753.375 | 41757.3882 | 1 | 41757.3882 | 41761.4153 | 1 | 41761.4153 | 41768.4715 | 1 | 41768.4715 | 41779.425 | 1 | 41774.4264 | 41851.4931 | 1 | 41774.4264 | 41785.7917 | 1 | 41786.3333 | 41800.5847 | 1 | 41800.5847 | 41823.4 | 1 | 41823.4 | 41851.4931 | 1 | 41851.4931 | 41851.4931 | 1 | 41844.4833 | 42006.5451 | 1 | 41844.4833 | 41862.7917 | 1 | 41863.3333 | 41891.6417 | 1 | 41891.6417 | 41941.6618 | 1 | 41941.6618 | 42006.5451 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6403 | 1 | 41753.375 | 41757.3653 | 1 | 41757.3653 | 41761.4347 | 1 | 41761.4347 | 41768.3382 | 1 | 41768.3382 | 41779.6403 | 1 | 41774.6986 | 41852.3868 | 1 | 41774.6986 | 41785.7917 | 1 | 41786.3333 | 41801.3431 | 1 | 41801.3431 | 41824.35 | 1 | 41824.35 | 41852.3868 | 1 | 41852.3868 | 41852.3868 | 1 | 41842.45 | 42004.4069 | 1 | 41842.45 | 41862.7917 | 1 | 41863.3333 | 41893.6583 | 1 | 41893.6583 | 41946.575 | 1 | 41946.575 | 42004.4069 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6069 | 1 | 41753.375 | 41754.7069 | 1 | 41754.7069 | 41761.475 | 1 | 41761.475 | 41771.3417 | 1 | 41771.3417 | 41780.6069 | 1 | 41774.4833 | 41851.4833 | 1 | 41774.4833 | 41785.7917 | 1 | 41786.3333 | 41799.6819 | 1 | 41799.6819 | 41822.6118 | 1 | 41822.6118 | 41851.4833 | 1 | 41851.4833 | 41851.4833 | 1 | 41845.4035 | 41998.3868 | 1 | 41845.4035 | 41862.7917 | 1 | 41863.3333 | 41894.5847 | 1 | 41894.5847 | 41936.6486 | 1 | 41936.6486 | 41998.3868 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3917 | 1 | 41753.375 | 41757.4181 | 1 | 41757.4181 | 41761.6333 | 1 | 41761.6333 | 41768.6903 | 1 | 41768.6903 | 41780.3917 | 1 | 41774.6715 | 41851.4764 | 1 | 41774.6715 | 41785.7917 | 1 | 41786.3333 | 41800.6347 | 1 | 41800.6347 | 41822.4069 | 1 | 41822.4069 | 41851.4764 | 1 | 41851.4764 | 41851.4764 | 1 | 41844.6882 | 42013.3736 | 1 | 41844.6882 | 41862.7917 | 1 | 41863.3333 | 41901.7014 | 1 | 41901.7014 | 41947.3465 | 1 | 41947.3465 | 42013.3736 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.5965 | 1 | 41753.375 | 41757.4118 | 1 | 41757.4118 | 41761.5799 | 1 | 41761.5799 | 41768.6097 | 1 | 41768.6097 | 41780.5965 | 1 | 41775.4368 | 41850.7083 | 1 | 41775.4368 | 41785.7917 | 1 | 41786.3333 | 41799.5653 | 1 | 41799.5653 | 41821.6451 | 1 | 41821.6451 | 41850.7083 | 1 | 41850.7083 | 41850.7083 | 1 | 41845.6882 | 42012.4403 | 1 | 41845.6882 | 41862.7917 | 1 | 41863.3333 | 41897.575 | 1 | 41897.575 | 41939.6118 | 1 | 41939.6118 | 42012.4403 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4215 | 1 | 41753.375 | 41757.3819 | 1 | 41757.3819 | 41761.4486 | 1 | 41761.4486 | 41768.55 | 1 | 41768.55 | 41780.4215 | 1 | 41774.6847 | 41849.5583 | 1 | 41774.6847 | 41785.7917 | 1 | 41786.3333 | 41800.4632 | 1 | 41800.4632 | 41822.3535 | 1 | 41822.3535 | 41849.5583 | 1 | 41849.5583 | 41849.5583 | 1 | 41848.4035 | 41998.5549 | 1 | 41848.4035 | 41862.7917 | 1 | 41863.3333 | 41897.6083 | 1 | 41897.6083 | 41942.45 | 1 | 41942.45 | 41998.5549 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3819 | 1 | 41753.375 | 41757.3417 | 1 | 41757.3417 | 41761.3681 | 1 | 41761.3681 | 41768.4549 | 1 | 41768.4549 | 41779.3819 | 1 | 41774.4736 | 41850.6583 | 1 | 41774.4736 | 41785.7917 | 1 | 41786.3333 | 41799.4799 | 1 | 41799.4799 | 41821.4465 | 1 | 41821.4465 | 41850.6583 | 1 | 41850.6583 | 41850.6583 | 1 | 41845.6417 | 42013.6417 | 1 | 41845.6417 | 41862.7917 | 1 | 41863.3333 | 41900.3736 | 1 | 41900.3736 | 41954.3569 | 1 | 41954.3569 | 42013.6417 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4049 | 1 | 41753.375 | 41757.3583 | 1 | 41757.3583 | 41761.375 | 1 | 41761.375 | 41771.3382 | 1 | 41771.3382 | 41780.4049 | 1 | 41774.45 | 41849.6583 | 1 | 41774.45 | 41785.7917 | 1 | 41786.3333 | 41800.4333 | 1 | 41800.4333 | 41822.4931 | 1 | 41822.4931 | 41849.6583 | 1 | 41849.6583 | 41849.6583 | 1 | 41843.6118 | 41996.3736 | 1 | 41843.6118 | 41862.7917 | 1 | 41863.3333 | 41893.7014 | 1 | 41893.7014 | 41939.3868 | 1 | 41939.3868 | 41996.3736 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.7035 | 1 | 41753.375 | 41757.3681 | 1 | 41757.3681 | 41761.3882 | 1 | 41761.3882 | 41768.6597 | 1 | 41768.6597 | 41779.7035 | 1 | 41775.3701 | 41851.6181 | 1 | 41775.3701 | 41785.7917 | 1 | 41786.3333 | 41800.3632 | 1 | 41800.3632 | 41822.3569 | 1 | 41822.3569 | 41851.6181 | 1 | 41851.6181 | 41851.6181 | 1 | 41845.6951 | 42011.45 | 1 | 41845.6951 | 41862.7917 | 1 | 41863.3333 | 41898.3569 | 1 | 41898.3569 | 41940.675 | 1 | 41940.675 | 42011.45 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6667 | 1 | 41753.375 | 41757.4083 | 1 | 41757.4083 | 41761.5465 | 1 | 41761.5465 | 41768.6535 | 1 | 41768.6535 | 41779.6667 | 1 | 41775.45 | 41845.6285 | 1 | 41775.45 | 41785.7917 | 1 | 41786.3333 | 41800.4201 | 1 | 41800.4201 | 41820.5681 | 1 | 41820.5681 | 41845.6285 | 1 | 41845.6285 | 41845.6285 | 1 | 41845.6486 | 42024.6715 | 1 | 41845.6486 | 41862.7917 | 1 | 41863.3333 | 41893.5986 | 1 | 41893.5986 | 41950.5715 | 1 | 41950.5715 | 42024.6715 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.7069 | 1 | 41753.375 | 41757.4549 | 1 | 41757.4549 | 41761.55 | 1 | 41761.55 | 41768.6264 | 1 | 41768.6264 | 41779.7069 | 1 | 41774.6785 | 41851.5451 | 1 | 41774.6785 | 41785.7917 | 1 | 41786.3333 | 41801.6118 | 1 | 41801.6118 | 41824.5583 | 1 | 41824.5583 | 41851.5451 | 1 | 41851.5451 | 41851.5451 | 1 | 41844.4132 | 42006.5847 | 1 | 41844.4132 | 41862.7917 | 1 | 41863.3333 | 41893.3632 | 1 | 41893.3632 | 41947.6549 | 1 | 41947.6549 | 42006.5847 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3514 | 1 | 41753.375 | 41757.3653 | 1 | 41757.3653 | 41761.4451 | 1 | 41761.4451 | 41768.6368 | 1 | 41768.6368 | 41780.3514 | 1 | 41773.6549 | 41852.4465 | 1 | 41773.6549 | 41785.7917 | 1 | 41786.3333 | 41801.3764 | 1 | 41801.3764 | 41823.4236 | 1 | 41823.4236 | 41852.4465 | 1 | 41852.4465 | 41852.4465 | 1 | 41844.6014 | 42004.3833 | 1 | 41844.6014 | 41862.7917 | 1 | 41863.3333 | 41892.3931 | 1 | 41892.3931 | 41939.6215 | 1 | 41939.6215 | 42004.3833 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4951 | 1 | 41753.375 | 41757.3847 | 1 | 41757.3847 | 41761.3917 | 1 | 41761.3917 | 41768.4653 | 1 | 41768.4653 | 41779.4951 | 1 | 41774.6319 | 41850.6382 | 1 | 41774.6319 | 41785.7917 | 1 | 41786.3333 | 41800.4931 | 1 | 41800.4931 | 41822.3431 | 1 | 41822.3431 | 41850.6382 | 1 | 41850.6382 | 41850.6382 | 1 | 41848.4 | 42010.35 | 1 | 41848.4 | 41862.7917 | 1 | 41863.3333 | 41899.3403 | 1 | 41899.3403 | 41943.4236 | 1 | 41943.4236 | 42010.35 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4917 | 1 | 41753.375 | 41757.3583 | 1 | 41757.3583 | 41760.6965 | 1 | 41760.6965 | 41767.6667 | 1 | 41767.6667 | 41779.4917 | 1 | 41775.4965 | 41855.6382 | 1 | 41775.4965 | 41785.7917 | 1 | 41786.3333 | 41801.4236 | 1 | 41801.4236 | 41822.4333 | 1 | 41822.4333 | 41855.6382 | 1 | 41855.6382 | 41855.6382 | 1 | 41848.575 | 42002.4201 | 1 | 41848.575 | 41862.7917 | 1 | 41863.3333 | 41891.6785 | 1 | 41891.6785 | 41939.6083 | 1 | 41939.6083 | 42002.4201 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6535 | 1 | 41753.375 | 41757.3785 | 1 | 41757.3785 | 41761.5431 | 1 | 41761.5431 | 41768.4715 | 1 | 41768.4715 | 41779.6535 | 1 | 41774.5785 | 41851.625 | 1 | 41774.5785 | 41785.7917 | 1 | 41786.3333 | 41799.5583 | 1 | 41799.5583 | 41821.6347 | 1 | 41821.6347 | 41851.625 | 1 | 41851.625 | 41851.625 | 1 | 41844.6618 | 42016.6083 | 1 | 41844.6618 | 41862.7917 | 1 | 41863.3333 | 41900.5882 | 1 | 41900.5882 | 41949.6153 | 1 | 41949.6153 | 42016.6083 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3986 | 1 | 41753.375 | 41757.3417 | 1 | 41757.3417 | 41760.6632 | 1 | 41760.6632 | 41767.5799 | 1 | 41767.5799 | 41779.3986 | 1 | 41775.5486 | 41852.6181 | 1 | 41775.5486 | 41785.7917 | 1 | 41786.3333 | 41799.4 | 1 | 41799.4 | 41822.7049 | 1 | 41822.7049 | 41852.6181 | 1 | 41852.6181 | 41852.6181 | 1 | 41848.6653 | 42004.3632 | 1 | 41848.6653 | 41862.7917 | 1 | 41863.3333 | 41891.5653 | 1 | 41891.5653 | 41934.4701 | 1 | 41934.4701 | 42004.3632 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.7 | 1 | 41753.375 | 41757.3486 | 1 | 41757.3486 | 41761.4715 | 1 | 41761.4715 | 41768.4049 | 1 | 41768.4049 | 41778.7 | 1 | 41774.4097 | 41850.6917 | 1 | 41774.4097 | 41785.7917 | 1 | 41786.3333 | 41800.5819 | 1 | 41800.5819 | 41821.4597 | 1 | 41821.4597 | 41850.6917 | 1 | 41850.6917 | 41850.6917 | 1 | 41848.6549 | 42005.4 | 1 | 41848.6549 | 41862.7917 | 1 | 41863.3333 | 41892.5819 | 1 | 41892.5819 | 41943.6153 | 1 | 41943.6153 | 42005.4 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3847 | 1 | 41753.375 | 41757.4986 | 1 | 41757.4986 | 41761.6465 | 1 | 41761.6465 | 41771.3882 | 1 | 41771.3882 | 41780.3847 | 1 | 41775.4535 | 41852.4569 | 1 | 41775.4535 | 41785.7917 | 1 | 41786.3333 | 41800.4236 | 1 | 41800.4236 | 41822.6819 | 1 | 41822.6819 | 41852.4569 | 1 | 41852.4569 | 41852.4569 | 1 | 41848.4931 | 42012.5681 | 1 | 41848.4931 | 41862.7917 | 1 | 41863.3333 | 41894.6819 | 1 | 41894.6819 | 41949.3931 | 1 | 41949.3931 | 42012.5681 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6535 | 1 | 41753.375 | 41757.4486 | 1 | 41757.4486 | 41761.4451 | 1 | 41761.4451 | 41768.6201 | 1 | 41768.6201 | 41779.6535 | 1 | 41774.4597 | 41850.5847 | 1 | 41774.4597 | 41785.7917 | 1 | 41786.3333 | 41799.4833 | 1 | 41799.4833 | 41821.4569 | 1 | 41821.4569 | 41850.5847 | 1 | 41850.5847 | 41850.5847 | 1 | 41845.4201 | 42017.3431 | 1 | 41845.4201 | 41862.7917 | 1 | 41863.3333 | 41899.4167 | 1 | 41899.4167 | 41941.5583 | 1 | 41941.5583 | 42017.3431 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5465 | 1 | 41753.375 | 41757.3917 | 1 | 41757.3917 | 41761.4653 | 1 | 41761.4653 | 41768.5965 | 1 | 41768.5965 | 41779.5465 | 1 | 41775.3431 | 41850.5986 | 1 | 41775.3431 | 41785.7917 | 1 | 41786.3333 | 41800.4931 | 1 | 41800.4931 | 41821.6049 | 1 | 41821.6049 | 41850.5986 | 1 | 41850.5986 | 41850.5986 | 1 | 41845.4799 | 42011.6653 | 1 | 41845.4799 | 41862.7917 | 1 | 41863.3333 | 41892.6451 | 1 | 41892.6451 | 41950.6347 | 1 | 41950.6347 | 42011.6653 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4951 | 1 | 41753.375 | 41757.3847 | 1 | 41757.3847 | 41761.3917 | 1 | 41761.3917 | 41768.3986 | 1 | 41768.3986 | 41780.4951 | 1 | 41774.6153 | 41851.4431 | 1 | 41774.6153 | 41785.7917 | 1 | 41786.3333 | 41801.4569 | 1 | 41801.4569 | 41823.4736 | 1 | 41823.4736 | 41851.4431 | 1 | 41851.4431 | 41851.4431 | 1 | 41844.3597 | 41992.3833 | 1 | 41844.3597 | 41862.7917 | 1 | 41863.3333 | 41891.4736 | 1 | 41891.4736 | 41934.5486 | 1 | 41934.5486 | 41992.3833 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5535 | 1 | 41753.375 | 41757.3785 | 1 | 41757.3785 | 41761.3882 | 1 | 41761.3882 | 41768.375 | 1 | 41768.375 | 41779.5535 | 1 | 41774.575 | 41851.4 | 1 | 41774.575 | 41785.7917 | 1 | 41786.3333 | 41801.3368 | 1 | 41801.3368 | 41823.4264 | 1 | 41823.4264 | 41851.4 | 1 | 41851.4 | 41851.4 | 1 | 41844.5549 | 42009.4431 | 1 | 41844.5549 | 41862.7917 | 1 | 41863.3333 | 41891.6382 | 1 | 41891.6382 | 41935.6049 | 1 | 41935.6049 | 42009.4431 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.5667 | 1 | 41753.375 | 41757.4549 | 1 | 41757.4549 | 41761.7 | 1 | 41761.7 | 41768.6333 | 1 | 41768.6333 | 41780.5667 | 1 | 41774.4701 | 41849.7014 | 1 | 41774.4701 | 41785.7917 | 1 | 41786.3333 | 41799.5451 | 1 | 41799.5451 | 41817.675 | 1 | 41817.675 | 41849.7014 | 1 | 41849.7014 | 41849.7014 | 1 | 41844.6319 | 42006.4264 | 1 | 41844.6319 | 41862.7917 | 1 | 41863.3333 | 41894.6951 | 1 | 41894.6951 | 41939.4667 | 1 | 41939.4667 | 42006.4264 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4347 | 1 | 41753.375 | 41757.4618 | 1 | 41757.4618 | 41761.3618 | 1 | 41761.3618 | 41767.6799 | 1 | 41767.6799 | 41779.4347 | 1 | 41774.6951 | 41852.3701 | 1 | 41774.6951 | 41785.7917 | 1 | 41786.3333 | 41799.625 | 1 | 41799.625 | 41820.6618 | 1 | 41820.6618 | 41852.3701 | 1 | 41852.3701 | 41852.3701 | 1 | 41844.3903 | 42010.6153 | 1 | 41844.3903 | 41862.7917 | 1 | 41863.3333 | 41897.6285 | 1 | 41897.6285 | 41953.5 | 1 | 41953.5417 | 42010.6153 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4181 | 1 | 41753.375 | 41757.4514 | 1 | 41757.4514 | 41761.6632 | 1 | 41761.6632 | 41768.6868 | 1 | 41768.6868 | 41780.4181 | 1 | 41774.6153 | 41852.3431 | 1 | 41774.6153 | 41785.7917 | 1 | 41786.3333 | 41800.45 | 1 | 41800.45 | 41823.4201 | 1 | 41823.4201 | 41852.3431 | 1 | 41852.3431 | 41852.3431 | 1 | 41848.6715 | 42004.4299 | 1 | 41848.6715 | 41862.7917 | 1 | 41863.3333 | 41894.3632 | 1 | 41894.3632 | 41942.6514 | 1 | 41942.6514 | 42004.4299 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.5569 | 1 | 41753.375 | 41757.3583 | 1 | 41757.3583 | 41761.3451 | 1 | 41761.3451 | 41768.6535 | 1 | 41768.6535 | 41780.5569 | 1 | 41775.4333 | 41848.5715 | 1 | 41775.4333 | 41785.7917 | 1 | 41786.3333 | 41800.6618 | 1 | 41800.6618 | 41820.6653 | 1 | 41820.6653 | 41848.5715 | 1 | 41848.5715 | 41848.5715 | 1 | 41848.5986 | 42020.5951 | 1 | 41848.5986 | 41862.7917 | 1 | 41863.3333 | 41892.4035 | 1 | 41892.4035 | 41942.4965 | 1 | 41942.4965 | 42020.5951 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.7035 | 1 | 41753.375 | 41757.3618 | 1 | 41757.3618 | 41761.5431 | 1 | 41761.5431 | 41768.4451 | 1 | 41768.4451 | 41778.7035 | 1 | 41774.6486 | 41849.6382 | 1 | 41774.6486 | 41785.7917 | 1 | 41786.3333 | 41799.5514 | 1 | 41799.5514 | 41821.7014 | 1 | 41821.7014 | 41849.6382 | 1 | 41849.6382 | 41849.6382 | 1 | 41845.5653 | 42002.4299 | 1 | 41845.5653 | 41862.7917 | 1 | 41863.3333 | 41899.4799 | 1 | 41899.4799 | 41942.5618 | 1 | 41942.5618 | 42002.4299 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3514 | 1 | 41753.375 | 41757.375 | 1 | 41757.375 | 41761.5597 | 1 | 41761.5597 | 41768.6632 | 1 | 41768.6632 | 41780.3514 | 1 | 41774.4236 | 41851.6486 | 1 | 41774.4236 | 41785.7917 | 1 | 41786.3333 | 41801.3368 | 1 | 41801.3368 | 41823.5 | 1 | 41823.5417 | 41851.6486 | 1 | 41851.6486 | 41851.6486 | 1 | 41842.5819 | 42020.4132 | 1 | 41842.5819 | 41862.7917 | 1 | 41863.3333 | 41897.6451 | 1 | 41897.6451 | 41946.5715 | 1 | 41946.5715 | 42020.4132 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6167 | 1 | 41753.375 | 41757.475 | 1 | 41757.475 | 41761.6201 | 1 | 41761.6201 | 41768.6069 | 1 | 41768.6069 | 41779.6167 | 1 | 41774.3833 | 41848.4167 | 1 | 41774.3833 | 41785.7917 | 1 | 41786.3333 | 41800.5819 | 1 | 41800.5819 | 41822.3535 | 1 | 41822.3535 | 41848.4167 | 1 | 41848.4167 | 41848.4167 | 1 | 41845.6451 | 42017.3701 | 1 | 41845.6451 | 41862.7917 | 1 | 41863.3333 | 41891.4 | 1 | 41891.4 | 41941.6417 | 1 | 41941.6417 | 42017.3701 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5569 | 1 | 41753.375 | 41757.4451 | 1 | 41757.4451 | 41761.425 | 1 | 41761.425 | 41768.6931 | 1 | 41768.6931 | 41779.5569 | 1 | 41774.6785 | 41852.4201 | 1 | 41774.6785 | 41785.7917 | 1 | 41786.3333 | 41800.3764 | 1 | 41800.3764 | 41820.6514 | 1 | 41820.6514 | 41852.4201 | 1 | 41852.4201 | 41852.4201 | 1 | 41848.5583 | 42004.4333 | 1 | 41848.5583 | 41862.7917 | 1 | 41863.3333 | 41892.45 | 1 | 41892.45 | 41936.6951 | 1 | 41936.6951 | 42004.4333 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5764 | 1 | 41753.375 | 41757.4014 | 1 | 41757.4014 | 41761.3785 | 1 | 41761.3785 | 41767.6931 | 1 | 41767.6931 | 41779.5764 | 1 | 41775.3569 | 41848.3701 | 1 | 41775.3569 | 41785.7917 | 1 | 41786.3333 | 41800.4667 | 1 | 41800.4667 | 41820.5715 | 1 | 41820.5715 | 41848.3701 | 1 | 41848.3701 | 41848.3701 | 1 | 41844.6653 | 41992.6514 | 1 | 41844.6653 | 41862.7917 | 1 | 41863.3333 | 41891.4569 | 1 | 41891.4569 | 41934.6083 | 1 | 41934.6083 | 41992.6514 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3847 | 1 | 41753.375 | 41757.4181 | 1 | 41757.4181 | 41761.5632 | 1 | 41761.5632 | 41768.4986 | 1 | 41768.4986 | 41780.3847 | 1 | 41775.3632 | 41855.6681 | 1 | 41775.3632 | 41785.7917 | 1 | 41786.3333 | 41801.5653 | 1 | 41801.5653 | 41823.5549 | 1 | 41823.5549 | 41855.6681 | 1 | 41855.6681 | 41855.6681 | 1 | 41848.6049 | 42005.6417 | 1 | 41848.6049 | 41862.7917 | 1 | 41863.3333 | 41893.6118 | 1 | 41893.6118 | 41940.6215 | 1 | 41940.6215 | 42005.6417 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3653 | 1 | 41753.375 | 41757.4514 | 1 | 41757.4514 | 41761.6132 | 1 | 41761.6132 | 41768.6403 | 1 | 41768.6403 | 41780.3653 | 1 | 41774.7014 | 41850.4368 | 1 | 41774.7014 | 41785.7917 | 1 | 41786.3333 | 41800.4833 | 1 | 41800.4833 | 41822.6951 | 1 | 41822.6951 | 41850.4368 | 1 | 41850.4368 | 41850.4368 | 1 | 41848.5917 | 42013.5785 | 1 | 41848.5917 | 41862.7917 | 1 | 41863.3333 | 41891.3431 | 1 | 41891.3431 | 41942.7083 | 1 | 41943.3333 | 42013.5785 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6201 | 1 | 41753.375 | 41757.4583 | 1 | 41757.4583 | 41761.3951 | 1 | 41761.3951 | 41768.4215 | 1 | 41768.4215 | 41778.6201 | 1 | 41774.4368 | 41850.4333 | 1 | 41774.4368 | 41785.7917 | 1 | 41786.3333 | 41800.6319 | 1 | 41800.6319 | 41822.3701 | 1 | 41822.3701 | 41850.4333 | 1 | 41850.4333 | 41850.4333 | 1 | 41843.7014 | 42027.6583 | 1 | 41843.7014 | 41862.7917 | 1 | 41863.3333 | 41900.3632 | 1 | 41900.3632 | 41955.3632 | 1 | 41955.3632 | 42027.6583 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6403 | 1 | 41753.375 | 41757.3549 | 1 | 41757.3549 | 41761.425 | 1 | 41761.425 | 41771.3486 | 1 | 41771.3486 | 41779.6403 | 1 | 41774.6417 | 41851.6986 | 1 | 41774.6417 | 41785.7917 | 1 | 41786.3333 | 41800.5 | 1 | 41800.5417 | 41822.4931 | 1 | 41822.4931 | 41851.6986 | 1 | 41851.6986 | 41851.6986 | 1 | 41844.6049 | 42009.3465 | 1 | 41844.6049 | 41862.7917 | 1 | 41863.3333 | 41892.4368 | 1 | 41892.4368 | 41947.6618 | 1 | 41947.6618 | 42009.3465 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4653 | 1 | 41753.375 | 41757.4181 | 1 | 41757.4181 | 41761.6167 | 1 | 41761.6167 | 41768.6569 | 1 | 41768.6569 | 41779.4653 | 1 | 41774.6715 | 41850.5514 | 1 | 41774.6715 | 41785.7917 | 1 | 41786.3333 | 41801.3667 | 1 | 41801.3667 | 41821.6049 | 1 | 41821.6049 | 41850.5514 | 1 | 41850.5514 | 41850.5514 | 1 | 41845.3931 | 41999.4701 | 1 | 41845.3931 | 41862.7917 | 1 | 41863.3333 | 41893.6382 | 1 | 41893.6382 | 41940.4535 | 1 | 41940.4535 | 41999.4701 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5965 | 1 | 41753.375 | 41757.4014 | 1 | 41757.4014 | 41761.6403 | 1 | 41761.6403 | 41771.3618 | 1 | 41771.3618 | 41779.5965 | 1 | 41775.3764 | 41849.3535 | 1 | 41775.3764 | 41785.7917 | 1 | 41786.3333 | 41800.3535 | 1 | 41800.3535 | 41821.4132 | 1 | 41821.4132 | 41849.3535 | 1 | 41849.3535 | 41849.3535 | 1 | 41848.5917 | 42017.4333 | 1 | 41848.5917 | 41862.7917 | 1 | 41863.3333 | 41891.3903 | 1 | 41891.3903 | 41936.4333 | 1 | 41936.4333 | 42017.4333 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4583 | 1 | 41753.375 | 41757.3681 | 1 | 41757.3681 | 41761.3618 | 1 | 41761.3618 | 41768.7035 | 1 | 41768.7035 | 41780.4583 | 1 | 41775.3632 | 41848.6319 | 1 | 41775.3632 | 41785.7917 | 1 | 41786.3333 | 41800.3431 | 1 | 41800.3431 | 41821.4132 | 1 | 41821.4132 | 41848.6319 | 1 | 41848.6319 | 41848.6319 | 1 | 41845.4667 | 41995.7049 | 1 | 41845.4667 | 41862.7917 | 1 | 41863.3333 | 41891.6882 | 1 | 41891.6882 | 41934.4465 | 1 | 41934.4465 | 41995.7049 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6931 | 1 | 41753.375 | 41757.4014 | 1 | 41757.4014 | 41761.4285 | 1 | 41761.4285 | 41768.5736 | 1 | 41768.5736 | 41779.6931 | 1 | 41774.4431 | 41849.6514 | 1 | 41774.4431 | 41785.7917 | 1 | 41786.3333 | 41799.6181 | 1 | 41799.6181 | 41820.6847 | 1 | 41820.6847 | 41849.6514 | 1 | 41849.6514 | 41849.6514 | 1 | 41844.6917 | 42011.5 | 1 | 41844.6917 | 41862.7917 | 1 | 41863.3333 | 41894.6347 | 1 | 41894.6347 | 41950.5583 | 1 | 41950.5583 | 42011.5 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5465 | 1 | 41753.375 | 41754.7 | 1 | 41754.7 | 41761.4049 | 1 | 41761.4049 | 41768.6167 | 1 | 41768.6167 | 41779.5465 | 1 | 41774.7049 | 41852.4903 | 1 | 41774.7049 | 41785.7917 | 1 | 41786.3333 | 41800.675 | 1 | 41800.675 | 41821.7014 | 1 | 41821.7014 | 41852.4903 | 1 | 41852.4903 | 41852.4903 | 1 | 41848.6847 | 42010.6285 | 1 | 41848.6847 | 41862.7917 | 1 | 41863.3333 | 41892.6986 | 1 | 41892.6986 | 41941.4597 | 1 | 41941.4597 | 42010.6285 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4285 | 1 | 41753.375 | 41757.3347 | 1 | 41757.3347 | 41761.3681 | 1 | 41761.3681 | 41768.4382 | 1 | 41768.4382 | 41779.4285 | 1 | 41775.4403 | 41850.6382 | 1 | 41775.4403 | 41785.7917 | 1 | 41786.3333 | 41800.6215 | 1 | 41800.6215 | 41822.3535 | 1 | 41822.3535 | 41850.6382 | 1 | 41850.6382 | 41850.6382 | 1 | 41843.3333 | 42006.3632 | 1 | 41843.3333 | 41862.7917 | 1 | 41863.3333 | 41898.6083 | 1 | 41898.6083 | 41942.3965 | 1 | 41942.3965 | 42006.3632 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.5465 | 1 | 41753.375 | 41757.4583 | 1 | 41757.4583 | 41761.4847 | 1 | 41761.4847 | 41771.3882 | 1 | 41771.3882 | 41780.5465 | 1 | 41775.3667 | 41851.4465 | 1 | 41775.3667 | 41785.7917 | 1 | 41786.3333 | 41801.4368 | 1 | 41801.4368 | 41824.4201 | 1 | 41824.4201 | 41851.4465 | 1 | 41851.4465 | 41851.4465 | 1 | 41845.5681 | 42026.4035 | 1 | 41845.5681 | 41862.7917 | 1 | 41863.3333 | 41900.4833 | 1 | 41900.4833 | 41957.6583 | 1 | 41957.6583 | 42026.4035 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3347 | 1 | 41753.375 | 41757.425 | 1 | 41757.425 | 41761.3653 | 1 | 41761.3653 | 41768.3653 | 1 | 41768.3653 | 41780.3347 | 1 | 41774.5486 | 41850.6917 | 1 | 41774.5486 | 41785.7917 | 1 | 41786.3333 | 41799.6951 | 1 | 41799.6951 | 41821.6153 | 1 | 41821.6153 | 41850.6917 | 1 | 41850.6917 | 41850.6917 | 1 | 41848.3868 | 42013.6819 | 1 | 41848.3868 | 41862.7917 | 1 | 41863.3333 | 41900.3431 | 1 | 41900.3431 | 41955.7014 | 1 | 41955.7014 | 42013.6819 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6097 | 1 | 41753.375 | 41757.4951 | 1 | 41757.4951 | 41761.5799 | 1 | 41761.5799 | 41768.4319 | 1 | 41768.4319 | 41779.6097 | 1 | 41774.7014 | 41850.4764 | 1 | 41774.7014 | 41785.7917 | 1 | 41786.3333 | 41801.3569 | 1 | 41801.3569 | 41823.4431 | 1 | 41823.4431 | 41850.4764 | 1 | 41850.4764 | 41850.4764 | 1 | 41848.6486 | 42031.4569 | 1 | 41848.6486 | 41862.7917 | 1 | 41863.3333 | 41892.7083 | 1 | 41893.3333 | 41949.5 | 1 | 41949.5417 | 42031.4569 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6736 | 1 | 41753.375 | 41757.3986 | 1 | 41757.3986 | 41761.6701 | 1 | 41761.6701 | 41768.5833 | 1 | 41768.5833 | 41779.6736 | 1 | 41774.4569 | 41848.5618 | 1 | 41774.4569 | 41785.7917 | 1 | 41786.3333 | 41800.3667 | 1 | 41800.3667 | 41821.3868 | 1 | 41821.3868 | 41848.5618 | 1 | 41848.5618 | 41848.5618 | 1 | 41843.6319 | 42012.3903 | 1 | 41843.6319 | 41862.7917 | 1 | 41863.3333 | 41892.3931 | 1 | 41892.3931 | 41936.3368 | 1 | 41936.3368 | 42012.3903 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41775.6931 | 1 | 41753.375 | 41757.3549 | 1 | 41757.3549 | 41760.65 | 1 | 41760.65 | 41767.5597 | 1 | 41767.5597 | 41775.6931 | 1 | 41775.45 | 41845.4431 | 1 | 41775.45 | 41785.7917 | 1 | 41786.3333 | 41799.4764 | 1 | 41799.4764 | 41820.4868 | 1 | 41820.4868 | 41845.4431 | 1 | 41845.4431 | 41845.4431 | 1 | 41844.6847 | 42017.6118 | 1 | 41844.6847 | 41862.7917 | 1 | 41863.3333 | 41901.4035 | 1 | 41901.4035 | 41948.5451 | 1 | 41948.5451 | 42017.6118 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41781.4014 | 1 | 41753.375 | 41757.4014 | 1 | 41757.4014 | 41761.5701 | 1 | 41761.5701 | 41771.3681 | 1 | 41771.3681 | 41781.4014 | 1 | 41775.4236 | 41848.5549 | 1 | 41775.4236 | 41785.7917 | 1 | 41786.3333 | 41799.6847 | 1 | 41799.6847 | 41817.5951 | 1 | 41817.5951 | 41848.5549 | 1 | 41848.5549 | 41848.5549 | 1 | 41845.5653 | 42012.4667 | 1 | 41845.5653 | 41862.7917 | 1 | 41863.3333 | 41901.4403 | 1 | 41901.4403 | 41947.4403 | 1 | 41947.4403 | 42012.4667 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4951 | 1 | 41753.375 | 41757.4049 | 1 | 41757.4049 | 41760.6965 | 1 | 41760.6965 | 41768.3451 | 1 | 41768.3451 | 41779.4951 | 1 | 41774.6215 | 41852.3403 | 1 | 41774.6215 | 41785.7917 | 1 | 41786.3333 | 41801.45 | 1 | 41801.45 | 41822.6653 | 1 | 41822.6653 | 41852.3403 | 1 | 41852.3403 | 41852.3403 | 1 | 41845.6382 | 42010.5653 | 1 | 41845.6382 | 41862.7917 | 1 | 41863.3333 | 41891.3833 | 1 | 41891.3833 | 41935.5951 | 1 | 41935.5951 | 42010.5653 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5701 | 1 | 41753.375 | 41754.7069 | 1 | 41754.7069 | 41760.7035 | 1 | 41760.7035 | 41768.4847 | 1 | 41768.4847 | 41779.5701 | 1 | 41774.5715 | 41848.6083 | 1 | 41774.5715 | 41785.7917 | 1 | 41786.3333 | 41800.3667 | 1 | 41800.3667 | 41822.4368 | 1 | 41822.4368 | 41848.6083 | 1 | 41848.6083 | 41848.6083 | 1 | 41845.3764 | 42005.6347 | 1 | 41845.3764 | 41862.7917 | 1 | 41863.3333 | 41899.4632 | 1 | 41899.4632 | 41942.6785 | 1 | 41942.6785 | 42005.6347 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6299 | 1 | 41753.375 | 41757.3618 | 1 | 41757.3618 | 41760.6903 | 1 | 41760.6903 | 41768.3451 | 1 | 41768.3451 | 41778.6299 | 1 | 41774.4597 | 41850.6153 | 1 | 41774.4597 | 41785.7917 | 1 | 41786.3333 | 41800.3431 | 1 | 41800.3431 | 41822.4701 | 1 | 41822.4701 | 41850.6153 | 1 | 41850.6153 | 41850.6153 | 1 | 41844.6951 | 42005.6486 | 1 | 41844.6951 | 41862.7917 | 1 | 41863.3333 | 41894.4132 | 1 | 41894.4132 | 41940.5653 | 1 | 41940.5653 | 42005.6486 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4549 | 1 | 41753.375 | 41757.4417 | 1 | 41757.4417 | 41761.3549 | 1 | 41761.3549 | 41768.6403 | 1 | 41768.6403 | 41779.4549 | 1 | 41774.675 | 41848.5451 | 1 | 41774.675 | 41785.7917 | 1 | 41786.3333 | 41800.6715 | 1 | 41800.6715 | 41820.6986 | 1 | 41820.6986 | 41848.5451 | 1 | 41848.5451 | 41848.5451 | 1 | 41845.4764 | 42020.7049 | 1 | 41845.4764 | 41862.7917 | 1 | 41863.3333 | 41899.6681 | 1 | 41899.6681 | 41955.3667 | 1 | 41955.3667 | 42020.7049 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.4382 | 1 | 41753.375 | 41757.3847 | 1 | 41757.3847 | 41761.3986 | 1 | 41761.3986 | 41767.6833 | 1 | 41767.6833 | 41778.4382 | 1 | 41774.5847 | 41849.6285 | 1 | 41774.5847 | 41785.7917 | 1 | 41786.3333 | 41799.6417 | 1 | 41799.6417 | 41820.3569 | 1 | 41820.3569 | 41849.6285 | 1 | 41849.6285 | 41849.6285 | 1 | 41848.6681 | 42005.4736 | 1 | 41848.6681 | 41862.7917 | 1 | 41863.3333 | 41894.4201 | 1 | 41894.4201 | 41941.4667 | 1 | 41941.4667 | 42005.4736 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6868 | 1 | 41753.375 | 41757.3847 | 1 | 41757.3847 | 41761.4951 | 1 | 41761.4951 | 41768.5597 | 1 | 41768.5597 | 41779.6868 | 1 | 41775.3833 | 41850.5486 | 1 | 41775.3833 | 41785.7917 | 1 | 41786.3333 | 41799.6882 | 1 | 41799.6882 | 41820.4597 | 1 | 41820.4597 | 41850.5486 | 1 | 41850.5486 | 41850.5486 | 1 | 41848.3667 | 42004.4799 | 1 | 41848.3667 | 41862.7917 | 1 | 41863.3333 | 41893.4597 | 1 | 41893.4597 | 41947.5549 | 1 | 41947.5549 | 42004.4799 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4847 | 1 | 41753.375 | 41757.4118 | 1 | 41757.4118 | 41761.3382 | 1 | 41761.3382 | 41768.4153 | 1 | 41768.4153 | 41780.4847 | 1 | 41775.4 | 41850.3931 | 1 | 41775.4 | 41785.7917 | 1 | 41786.3333 | 41799.5653 | 1 | 41799.5653 | 41821.5847 | 1 | 41821.5847 | 41850.3931 | 1 | 41850.3931 | 41850.3931 | 1 | 41845.5514 | 42017.4667 | 1 | 41845.5514 | 41862.7917 | 1 | 41863.3333 | 41891.3431 | 1 | 41891.3431 | 41934.4736 | 1 | 41934.4736 | 42017.4667 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6201 | 1 | 41753.375 | 41757.3715 | 1 | 41757.3715 | 41761.4819 | 1 | 41761.4819 | 41768.4785 | 1 | 41768.4785 | 41779.6201 | 1 | 41774.6882 | 41848.6819 | 1 | 41774.6882 | 41785.7917 | 1 | 41786.3333 | 41800.4368 | 1 | 41800.4368 | 41822.4736 | 1 | 41822.4736 | 41848.6819 | 1 | 41848.6819 | 41848.6819 | 1 | 41844.6181 | 41996.6618 | 1 | 41844.6181 | 41862.7917 | 1 | 41863.3333 | 41892.6819 | 1 | 41892.6819 | 41936.5451 | 1 | 41936.5451 | 41996.6618 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4382 | 1 | 41753.375 | 41757.3451 | 1 | 41757.3451 | 41761.4514 | 1 | 41761.4514 | 41768.6368 | 1 | 41768.6368 | 41779.4382 | 1 | 41774.4368 | 41851.5917 | 1 | 41774.4368 | 41785.7917 | 1 | 41786.3333 | 41801.4097 | 1 | 41801.4097 | 41822.5486 | 1 | 41822.5486 | 41851.5917 | 1 | 41851.5917 | 41851.5917 | 1 | 41845.4035 | 42009.4569 | 1 | 41845.4035 | 41862.7917 | 1 | 41863.3333 | 41893.4299 | 1 | 41893.4299 | 41941.6417 | 1 | 41941.6417 | 42009.4569 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6965 | 1 | 41753.375 | 41754.6965 | 1 | 41754.6965 | 41760.65 | 1 | 41760.65 | 41768.4049 | 1 | 41768.4049 | 41778.6965 | 1 | 41775.4868 | 41850.4299 | 1 | 41775.4868 | 41785.7917 | 1 | 41786.3333 | 41801.3965 | 1 | 41801.3965 | 41822.4 | 1 | 41822.4 | 41850.4299 | 1 | 41850.4299 | 41850.4299 | 1 | 41844.6417 | 42010.5618 | 1 | 41844.6417 | 41862.7917 | 1 | 41863.3333 | 41894.5715 | 1 | 41894.5715 | 41953.5819 | 1 | 41953.5819 | 42010.5618 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.65 | 1 | 41753.375 | 41757.4451 | 1 | 41757.4451 | 41761.4847 | 1 | 41761.4847 | 41768.5868 | 1 | 41768.5868 | 41779.65 | 1 | 41774.625 | 41852.6153 | 1 | 41774.625 | 41785.7917 | 1 | 41786.3333 | 41800.6118 | 1 | 41800.6118 | 41823.625 | 1 | 41823.625 | 41852.6153 | 1 | 41852.6153 | 41852.6153 | 1 | 41842.6215 | 42027.4236 | 1 | 41842.6215 | 41862.7917 | 1 | 41863.3333 | 41891.6083 | 1 | 41891.6083 | 41948.6285 | 1 | 41948.6285 | 42027.4236 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4951 | 1 | 41753.375 | 41757.4215 | 1 | 41757.4215 | 41761.4347 | 1 | 41761.4347 | 41768.4715 | 1 | 41768.4715 | 41780.4951 | 1 | 41774.6486 | 41850.4597 | 1 | 41774.6486 | 41785.7917 | 1 | 41786.3333 | 41800.5785 | 1 | 41800.5785 | 41820.5681 | 1 | 41820.5681 | 41850.4597 | 1 | 41850.4597 | 41850.4597 | 1 | 41845.4299 | 42003.3465 | 1 | 41845.4299 | 41862.7917 | 1 | 41863.3333 | 41893.675 | 1 | 41893.675 | 41946.6486 | 1 | 41946.6486 | 42003.3465 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.5632 | 1 | 41753.375 | 41757.4917 | 1 | 41757.4917 | 41761.6799 | 1 | 41761.6799 | 41771.5868 | 1 | 41771.5868 | 41780.5632 | 1 | 41774.6514 | 41852.4632 | 1 | 41774.6514 | 41785.7917 | 1 | 41786.3333 | 41801.5451 | 1 | 41801.5451 | 41823.3632 | 1 | 41823.3632 | 41852.4632 | 1 | 41852.4632 | 41852.4632 | 1 | 41844.5715 | 42026.4069 | 1 | 41844.5715 | 41862.7917 | 1 | 41863.3333 | 41897.5653 | 1 | 41897.5653 | 41955.6514 | 1 | 41955.6514 | 42026.4069 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4785 | 1 | 41753.375 | 41757.4319 | 1 | 41757.4319 | 41761.4917 | 1 | 41761.4917 | 41768.4951 | 1 | 41768.4951 | 41779.4785 | 1 | 41774.35 | 41855.3833 | 1 | 41774.35 | 41785.7917 | 1 | 41786.3333 | 41799.6049 | 1 | 41799.6049 | 41822.4833 | 1 | 41822.4833 | 41855.3833 | 1 | 41855.3833 | 41855.3833 | 1 | 41845.45 | 42020.3903 | 1 | 41845.45 | 41862.7917 | 1 | 41863.3333 | 41899.5951 | 1 | 41899.5951 | 41947.5917 | 1 | 41947.5917 | 42020.3903 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5632 | 1 | 41753.375 | 41757.4382 | 1 | 41757.4382 | 41761.5903 | 1 | 41761.5903 | 41768.4882 | 1 | 41768.4882 | 41779.5632 | 1 | 41775.3764 | 41855.4035 | 1 | 41775.3764 | 41785.7917 | 1 | 41786.3333 | 41800.7014 | 1 | 41800.7014 | 41823.6347 | 1 | 41823.6347 | 41855.4035 | 1 | 41855.4035 | 41855.4035 | 1 | 41843.4236 | 42017.3535 | 1 | 41843.4236 | 41862.7917 | 1 | 41863.3333 | 41892.4903 | 1 | 41892.4903 | 41948.4299 | 1 | 41948.4299 | 42017.3535 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5569 | 1 | 41753.375 | 41757.3514 | 1 | 41757.3514 | 41761.5535 | 1 | 41761.5535 | 41768.6035 | 1 | 41768.6035 | 41779.5569 | 1 | 41774.6118 | 41851.4736 | 1 | 41774.6118 | 41785.7917 | 1 | 41786.3333 | 41801.4035 | 1 | 41801.4035 | 41822.5819 | 1 | 41822.5819 | 41851.4736 | 1 | 41851.4736 | 41851.4736 | 1 | 41844.3799 | 42019.3931 | 1 | 41844.3799 | 41862.7917 | 1 | 41863.3333 | 41893.4 | 1 | 41893.4 | 41947.4667 | 1 | 41947.4667 | 42019.3931 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4785 | 1 | 41753.375 | 41757.3681 | 1 | 41757.3681 | 41761.5667 | 1 | 41761.5667 | 41768.5569 | 1 | 41768.5569 | 41780.4785 | 1 | 41775.4903 | 41849.6715 | 1 | 41775.4903 | 41785.7917 | 1 | 41786.3333 | 41800.4132 | 1 | 41800.4132 | 41821.675 | 1 | 41821.675 | 41849.6715 | 1 | 41849.6715 | 41849.6715 | 1 | 41848.3597 | 41991.6917 | 1 | 41848.3597 | 41862.7917 | 1 | 41863.3333 | 41892.6583 | 1 | 41892.6583 | 41934.6653 | 1 | 41934.6653 | 41991.6917 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4618 | 1 | 41753.375 | 41757.3882 | 1 | 41757.3882 | 41761.5764 | 1 | 41761.5764 | 41768.6403 | 1 | 41768.6403 | 41780.4618 | 1 | 41774.6083 | 41848.6847 | 1 | 41774.6083 | 41785.7917 | 1 | 41786.3333 | 41799.6847 | 1 | 41799.6847 | 41822.575 | 1 | 41822.575 | 41848.6847 | 1 | 41848.6847 | 41848.6847 | 1 | 41848.6917 | 42018.4701 | 1 | 41848.6917 | 41862.7917 | 1 | 41863.3333 | 41892.4431 | 1 | 41892.4431 | 41942.4736 | 1 | 41942.4736 | 42018.4701 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4514 | 1 | 41753.375 | 41757.3549 | 1 | 41757.3549 | 41761.4083 | 1 | 41761.4083 | 41768.3917 | 1 | 41768.3917 | 41779.4514 | 1 | 41774.6417 | 41849.3965 | 1 | 41774.6417 | 41785.7917 | 1 | 41786.3333 | 41800.4569 | 1 | 41800.4569 | 41821.5715 | 1 | 41821.5715 | 41849.3965 | 1 | 41849.3965 | 41849.3965 | 1 | 41845.5583 | 42010.4201 | 1 | 41845.5583 | 41862.7917 | 1 | 41863.3333 | 41897.4069 | 1 | 41897.4069 | 41940.3736 | 1 | 41940.3736 | 42010.4201 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3847 | 1 | 41753.375 | 41757.3653 | 1 | 41757.3653 | 41760.7069 | 1 | 41760.7069 | 41768.3451 | 1 | 41768.3451 | 41779.3847 | 1 | 41773.6681 | 41850.6514 | 1 | 41773.6681 | 41785.7917 | 1 | 41786.3333 | 41799.4965 | 1 | 41799.4965 | 41821.4097 | 1 | 41821.4097 | 41850.6514 | 1 | 41850.6514 | 41850.6514 | 1 | 41848.6583 | 42003.5486 | 1 | 41848.6583 | 41862.7917 | 1 | 41863.3333 | 41898.4667 | 1 | 41898.4667 | 41943.3597 | 1 | 41943.3597 | 42003.5486 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6431 | 1 | 41753.375 | 41757.3785 | 1 | 41757.3785 | 41761.5535 | 1 | 41761.5535 | 41768.5632 | 1 | 41768.5632 | 41780.6431 | 1 | 41773.6819 | 41851.3833 | 1 | 41773.6819 | 41785.7917 | 1 | 41786.3333 | 41800.3868 | 1 | 41800.3868 | 41821.5451 | 1 | 41821.5451 | 41851.3833 | 1 | 41851.3833 | 41851.3833 | 1 | 41844.5917 | 42030.4167 | 1 | 41844.5917 | 41862.7917 | 1 | 41863.3333 | 41901.4667 | 1 | 41901.4667 | 41949.6681 | 1 | 41949.6681 | 42030.4167 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3951 | 1 | 41753.375 | 41754.6903 | 1 | 41754.6903 | 41760.6333 | 1 | 41760.6333 | 41767.7 | 1 | 41767.7 | 41779.3951 | 1 | 41774.5819 | 41852.3632 | 1 | 41774.5819 | 41785.7917 | 1 | 41786.3333 | 41800.3903 | 1 | 41800.3903 | 41821.6882 | 1 | 41821.6882 | 41852.3632 | 1 | 41852.3632 | 41852.3632 | 1 | 41848.7014 | 42012.6549 | 1 | 41848.7014 | 41862.7917 | 1 | 41863.3333 | 41900.5819 | 1 | 41900.5819 | 41955.6014 | 1 | 41955.6014 | 42012.6549 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6931 | 1 | 41753.375 | 41757.4118 | 1 | 41757.4118 | 41761.3653 | 1 | 41761.3653 | 41768.375 | 1 | 41768.375 | 41778.6931 | 1 | 41774.6319 | 41850.3368 | 1 | 41774.6319 | 41785.7917 | 1 | 41786.3333 | 41799.6715 | 1 | 41799.6715 | 41821.4965 | 1 | 41821.4965 | 41850.3368 | 1 | 41850.3368 | 41850.3368 | 1 | 41842.6049 | 42011.6153 | 1 | 41842.6049 | 41862.7917 | 1 | 41863.3333 | 41893.4035 | 1 | 41893.4035 | 41943.575 | 1 | 41943.575 | 42011.6153 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4514 | 1 | 41753.375 | 41757.375 | 1 | 41757.375 | 41761.3785 | 1 | 41761.3785 | 41768.5868 | 1 | 41768.5868 | 41780.4514 | 1 | 41774.6819 | 41850.4333 | 1 | 41774.6819 | 41785.7917 | 1 | 41786.3333 | 41800.4903 | 1 | 41800.4903 | 41821.5715 | 1 | 41821.5715 | 41850.4333 | 1 | 41850.4333 | 41850.4333 | 1 | 41843.6882 | 42018.6319 | 1 | 41843.6882 | 41862.7917 | 1 | 41863.3333 | 41894.4 | 1 | 41894.4 | 41948.5951 | 1 | 41948.5951 | 42018.6319 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6597 | 1 | 41753.375 | 41757.3583 | 1 | 41757.3583 | 41761.4486 | 1 | 41761.4486 | 41768.55 | 1 | 41768.55 | 41779.6597 | 1 | 41775.3632 | 41848.675 | 1 | 41775.3632 | 41785.7917 | 1 | 41786.3333 | 41800.5951 | 1 | 41800.5951 | 41821.4632 | 1 | 41821.4632 | 41848.675 | 1 | 41848.675 | 41848.675 | 1 | 41843.4465 | 42004.3465 | 1 | 41843.4465 | 41862.7917 | 1 | 41863.3333 | 41893.4736 | 1 | 41893.4736 | 41943.3403 | 1 | 41943.3403 | 42004.3465 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.5632 | 1 | 41753.375 | 41754.6903 | 1 | 41754.6903 | 41760.6701 | 1 | 41760.6701 | 41767.6701 | 1 | 41767.6701 | 41778.5632 | 1 | 41774.6285 | 41855.3535 | 1 | 41774.6285 | 41785.7917 | 1 | 41786.3333 | 41800.4069 | 1 | 41800.4069 | 41823.625 | 1 | 41823.625 | 41855.3535 | 1 | 41855.3535 | 41855.3535 | 1 | 41844.575 | 42018.3465 | 1 | 41844.575 | 41862.7917 | 1 | 41863.3333 | 41898.6215 | 1 | 41898.6215 | 41942.4035 | 1 | 41942.4035 | 42018.3465 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4049 | 1 | 41753.375 | 41757.3653 | 1 | 41757.3653 | 41761.4014 | 1 | 41761.4014 | 41768.6069 | 1 | 41768.6069 | 41780.4049 | 1 | 41774.6451 | 41848.3403 | 1 | 41774.6451 | 41785.7917 | 1 | 41786.3333 | 41799.6653 | 1 | 41799.6653 | 41821.3368 | 1 | 41821.3368 | 41848.3403 | 1 | 41848.3403 | 41848.3403 | 1 | 41845.3931 | 42006.3535 | 1 | 41845.3931 | 41862.7917 | 1 | 41863.3333 | 41894.4931 | 1 | 41894.4931 | 41948.575 | 1 | 41948.575 | 42006.3535 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6535 | 1 | 41753.375 | 41757.3549 | 1 | 41757.3549 | 41761.425 | 1 | 41761.425 | 41768.6569 | 1 | 41768.6569 | 41780.6535 | 1 | 41775.3833 | 41850.4764 | 1 | 41775.3833 | 41785.7917 | 1 | 41786.3333 | 41799.4035 | 1 | 41799.4035 | 41822.4535 | 1 | 41822.4535 | 41850.4764 | 1 | 41850.4764 | 41850.4764 | 1 | 41848.3465 | 42005.3903 | 1 | 41848.3465 | 41862.7917 | 1 | 41863.3333 | 41893.4965 | 1 | 41893.4965 | 41941.5785 | 1 | 41941.5785 | 42005.3903 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6201 | 1 | 41753.375 | 41757.3847 | 1 | 41757.3847 | 41761.475 | 1 | 41761.475 | 41771.3451 | 1 | 41771.3451 | 41780.6201 | 1 | 41774.6514 | 41855.6882 | 1 | 41774.6514 | 41785.7917 | 1 | 41786.3333 | 41800.3632 | 1 | 41800.3632 | 41823.4201 | 1 | 41823.4201 | 41855.6882 | 1 | 41855.6882 | 41855.6882 | 1 | 41845.4431 | 42005.6715 | 1 | 41845.4431 | 41862.7917 | 1 | 41863.3333 | 41891.5951 | 1 | 41891.5951 | 41948.4632 | 1 | 41948.4632 | 42005.6715 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.7035 | 1 | 41753.375 | 41757.3819 | 1 | 41757.3819 | 41761.4181 | 1 | 41761.4181 | 41768.375 | 1 | 41768.375 | 41778.7035 | 1 | 41774.3403 | 41851.4569 | 1 | 41774.3403 | 41785.7917 | 1 | 41786.3333 | 41799.7083 | 1 | 41800.3333 | 41822.3368 | 1 | 41822.3368 | 41851.4569 | 1 | 41851.4569 | 41851.4569 | 1 | 41848.6181 | 42019.3931 | 1 | 41848.6181 | 41862.7917 | 1 | 41863.3333 | 41901.3764 | 1 | 41901.3764 | 41961.4035 | 1 | 41961.4035 | 42019.3931 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4049 | 1 | 41753.375 | 41757.3951 | 1 | 41757.3951 | 41761.4181 | 1 | 41761.4181 | 41768.4215 | 1 | 41768.4215 | 41780.4049 | 1 | 41775.4403 | 41850.35 | 1 | 41775.4403 | 41785.7917 | 1 | 41786.3333 | 41800.5653 | 1 | 41800.5653 | 41821.6715 | 1 | 41821.6715 | 41850.35 | 1 | 41850.35 | 41850.35 | 1 | 41848.5785 | 41998.3799 | 1 | 41848.5785 | 41862.7917 | 1 | 41863.3333 | 41898.4201 | 1 | 41898.4201 | 41940.4535 | 1 | 41940.4535 | 41998.3799 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5764 | 1 | 41753.375 | 41757.3785 | 1 | 41757.3785 | 41760.6736 | 1 | 41760.6736 | 41767.5597 | 1 | 41767.5597 | 41779.5764 | 1 | 41775.3736 | 41855.5847 | 1 | 41775.3736 | 41785.7917 | 1 | 41786.3333 | 41799.6083 | 1 | 41799.6083 | 41823.4264 | 1 | 41823.4264 | 41855.5847 | 1 | 41855.5847 | 41855.5847 | 1 | 41844.675 | 42013.3667 | 1 | 41844.675 | 41862.7917 | 1 | 41863.3333 | 41892.6653 | 1 | 41892.6653 | 41940.6049 | 1 | 41940.6049 | 42013.3667 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3986 | 1 | 41753.375 | 41757.4153 | 1 | 41757.4153 | 41761.475 | 1 | 41761.475 | 41768.4715 | 1 | 41768.4715 | 41779.3986 | 1 | 41774.5583 | 41850.4201 | 1 | 41774.5583 | 41785.7917 | 1 | 41786.3333 | 41799.6347 | 1 | 41799.6347 | 41821.6319 | 1 | 41821.6319 | 41850.4201 | 1 | 41850.4201 | 41850.4201 | 1 | 41844.675 | 42026.6882 | 1 | 41844.675 | 41862.7917 | 1 | 41863.3333 | 41894.5451 | 1 | 41894.5451 | 41947.4069 | 1 | 41947.4069 | 42026.6882 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.425 | 1 | 41753.375 | 41757.375 | 1 | 41757.375 | 41760.6569 | 1 | 41760.6569 | 41768.4417 | 1 | 41768.4417 | 41779.425 | 1 | 41774.6181 | 41849.4632 | 1 | 41774.6181 | 41785.7917 | 1 | 41786.3333 | 41800.3833 | 1 | 41800.3833 | 41822.6583 | 1 | 41822.6583 | 41849.4632 | 1 | 41849.4632 | 41849.4632 | 1 | 41848.3965 | 42019.6917 | 1 | 41848.3965 | 41862.7917 | 1 | 41863.3333 | 41898.5 | 1 | 41898.5417 | 41954.6319 | 1 | 41954.6319 | 42019.6917 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.5965 | 1 | 41753.375 | 41757.4847 | 1 | 41757.4847 | 41761.5931 | 1 | 41761.5931 | 41771.3882 | 1 | 41771.3882 | 41780.5965 | 1 | 41775.3535 | 41848.6847 | 1 | 41775.3535 | 41785.7917 | 1 | 41786.3333 | 41800.4597 | 1 | 41800.4597 | 41820.6653 | 1 | 41820.6653 | 41848.6847 | 1 | 41848.6847 | 41848.6847 | 1 | 41848.4403 | 42006.6583 | 1 | 41848.4403 | 41862.7917 | 1 | 41863.3333 | 41891.3569 | 1 | 41891.3569 | 41948.5549 | 1 | 41948.5549 | 42006.6583 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5701 | 1 | 41753.375 | 41757.3347 | 1 | 41757.3347 | 41761.3549 | 1 | 41761.3549 | 41768.4819 | 1 | 41768.4819 | 41779.5701 | 1 | 41775.3764 | 41851.7014 | 1 | 41775.3764 | 41785.7917 | 1 | 41786.3333 | 41801.4333 | 1 | 41801.4333 | 41824.3764 | 1 | 41824.3764 | 41851.7014 | 1 | 41851.7014 | 41851.7014 | 1 | 41844.6882 | 42006.4236 | 1 | 41844.6882 | 41862.7917 | 1 | 41863.3333 | 41897.7083 | 1 | 41898.3333 | 41942.6215 | 1 | 41942.6215 | 42006.4236 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4715 | 1 | 41753.375 | 41757.4382 | 1 | 41757.4382 | 41761.4285 | 1 | 41761.4285 | 41768.4549 | 1 | 41768.4549 | 41779.4715 | 1 | 41774.3569 | 41850.35 | 1 | 41774.3569 | 41785.7917 | 1 | 41786.3333 | 41800.5618 | 1 | 41800.5618 | 41821.3868 | 1 | 41821.3868 | 41850.35 | 1 | 41850.35 | 41850.35 | 1 | 41844.4333 | 42024.4868 | 1 | 41844.4333 | 41862.7917 | 1 | 41863.3333 | 41900.5514 | 1 | 41900.5514 | 41960.4299 | 1 | 41960.4299 | 42024.4868 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6597 | 1 | 41753.375 | 41757.4153 | 1 | 41757.4153 | 41761.4917 | 1 | 41761.4917 | 41768.375 | 1 | 41768.375 | 41779.6597 | 1 | 41774.3465 | 41850.3833 | 1 | 41774.3465 | 41785.7917 | 1 | 41786.3333 | 41799.6681 | 1 | 41799.6681 | 41821.6319 | 1 | 41821.6319 | 41850.3833 | 1 | 41850.3833 | 41850.3833 | 1 | 41848.6382 | 42016.5917 | 1 | 41848.6382 | 41862.7917 | 1 | 41863.3333 | 41901.5618 | 1 | 41901.5618 | 41947.6785 | 1 | 41947.6785 | 42016.5917 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5431 | 1 | 41753.375 | 41757.4181 | 1 | 41757.4181 | 41761.4153 | 1 | 41761.4153 | 41768.3417 | 1 | 41768.3417 | 41779.5431 | 1 | 41773.6382 | 41850.5549 | 1 | 41773.6382 | 41785.7917 | 1 | 41786.3333 | 41799.4965 | 1 | 41799.4965 | 41820.4799 | 1 | 41820.4799 | 41850.5549 | 1 | 41850.5549 | 41850.5549 | 1 | 41848.6882 | 42005.6618 | 1 | 41848.6882 | 41862.7917 | 1 | 41863.3333 | 41892.5681 | 1 | 41892.5681 | 41936.6681 | 1 | 41936.6681 | 42005.6618 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6132 | 1 | 41753.375 | 41757.3583 | 1 | 41757.3583 | 41761.6069 | 1 | 41761.6069 | 41768.6799 | 1 | 41768.6799 | 41779.6132 | 1 | 41775.4569 | 41848.5549 | 1 | 41775.4569 | 41785.7917 | 1 | 41786.3333 | 41800.3403 | 1 | 41800.3403 | 41821.3597 | 1 | 41821.3597 | 41848.5549 | 1 | 41848.5549 | 41848.5549 | 1 | 41848.4403 | 41998.4097 | 1 | 41848.4403 | 41862.7917 | 1 | 41863.3333 | 41892.4167 | 1 | 41892.4167 | 41939.6118 | 1 | 41939.6118 | 41998.4097 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4549 | 1 | 41753.375 | 41757.4083 | 1 | 41757.4083 | 41761.4014 | 1 | 41761.4014 | 41768.4285 | 1 | 41768.4285 | 41780.4549 | 1 | 41775.4535 | 41850.6785 | 1 | 41775.4535 | 41785.7917 | 1 | 41786.3333 | 41800.4201 | 1 | 41800.4201 | 41822.3535 | 1 | 41822.3535 | 41850.6785 | 1 | 41850.6785 | 41850.6785 | 1 | 41848.5882 | 42005.4597 | 1 | 41848.5882 | 41862.7917 | 1 | 41863.3333 | 41892.5917 | 1 | 41892.5917 | 41936.6181 | 1 | 41936.6181 | 42005.4597 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6264 | 1 | 41753.375 | 41757.3681 | 1 | 41757.3681 | 41761.3486 | 1 | 41761.3486 | 41768.3583 | 1 | 41768.3583 | 41779.6264 | 1 | 41774.5882 | 41851.6382 | 1 | 41774.5882 | 41785.7917 | 1 | 41786.3333 | 41801.5715 | 1 | 41801.5715 | 41821.5715 | 1 | 41821.5715 | 41851.6382 | 1 | 41851.6382 | 41851.6382 | 1 | 41848.5417 | 42012.5681 | 1 | 41848.5417 | 41862.7917 | 1 | 41863.3333 | 41893.5951 | 1 | 41893.5951 | 41941.575 | 1 | 41941.575 | 42012.5681 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.475 | 1 | 41753.375 | 41757.3715 | 1 | 41757.3715 | 41761.3847 | 1 | 41761.3847 | 41768.55 | 1 | 41768.55 | 41779.475 | 1 | 41774.6715 | 41848.625 | 1 | 41774.6715 | 41785.7917 | 1 | 41786.3333 | 41799.4632 | 1 | 41799.4632 | 41821.3764 | 1 | 41821.3764 | 41848.625 | 1 | 41848.625 | 41848.625 | 1 | 41844.6083 | 42006.7083 | 1 | 41844.6083 | 41862.7917 | 1 | 41863.3333 | 41897.4736 | 1 | 41897.4736 | 41941.5514 | 1 | 41941.5514 | 42006.7083 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3347 | 1 | 41753.375 | 41757.425 | 1 | 41757.425 | 41761.5465 | 1 | 41761.5465 | 41768.4549 | 1 | 41768.4549 | 41780.3347 | 1 | 41774.5917 | 41848.5514 | 1 | 41774.5917 | 41785.7917 | 1 | 41786.3333 | 41800.4264 | 1 | 41800.4264 | 41817.6917 | 1 | 41817.6917 | 41848.5514 | 1 | 41848.5514 | 41848.5514 | 1 | 41848.6785 | 42002.6618 | 1 | 41848.6785 | 41862.7917 | 1 | 41863.3333 | 41894.6514 | 1 | 41894.6514 | 41946.625 | 1 | 41946.625 | 42002.6618 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.65 | 1 | 41753.375 | 41757.3417 | 1 | 41757.3417 | 41761.5597 | 1 | 41761.5597 | 41768.7069 | 1 | 41768.7069 | 41780.65 | 1 | 41774.5986 | 41849.6486 | 1 | 41774.5986 | 41785.7917 | 1 | 41786.3333 | 41800.3597 | 1 | 41800.3597 | 41822.3597 | 1 | 41822.3597 | 41849.6486 | 1 | 41849.6486 | 41849.6486 | 1 | 41845.675 | 42013.6181 | 1 | 41845.675 | 41862.7917 | 1 | 41863.3333 | 41894.6118 | 1 | 41894.6118 | 41940.6549 | 1 | 41940.6549 | 42013.6181 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3986 | 1 | 41753.375 | 41757.3514 | 1 | 41757.3514 | 41761.3847 | 1 | 41761.3847 | 41768.5799 | 1 | 41768.5799 | 41779.3986 | 1 | 41775.3535 | 41849.6049 | 1 | 41775.3535 | 41785.7917 | 1 | 41786.3333 | 41800.5917 | 1 | 41800.5917 | 41821.5951 | 1 | 41821.5951 | 41849.6049 | 1 | 41849.6049 | 41849.6049 | 1 | 41848.6083 | 42005.4764 | 1 | 41848.6083 | 41862.7917 | 1 | 41863.3333 | 41891.6319 | 1 | 41891.6319 | 41934.3965 | 1 | 41934.3965 | 42005.4764 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3549 | 1 | 41753.375 | 41757.3986 | 1 | 41757.3986 | 41761.4215 | 1 | 41761.4215 | 41768.5465 | 1 | 41768.5465 | 41780.3549 | 1 | 41775.3465 | 41849.4264 | 1 | 41775.3465 | 41785.7917 | 1 | 41786.3333 | 41800.6618 | 1 | 41800.6618 | 41821.4465 | 1 | 41821.4465 | 41849.4264 | 1 | 41849.4264 | 41849.4264 | 1 | 41845.3701 | 41999.575 | 1 | 41845.3701 | 41862.7917 | 1 | 41863.3333 | 41894.6882 | 1 | 41894.6882 | 41942.3368 | 1 | 41942.3368 | 41999.575 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4153 | 1 | 41753.375 | 41757.375 | 1 | 41757.375 | 41761.4014 | 1 | 41761.4014 | 41768.4847 | 1 | 41768.4847 | 41779.4153 | 1 | 41775.4833 | 41849.5486 | 1 | 41775.4833 | 41785.7917 | 1 | 41786.3333 | 41800.5549 | 1 | 41800.5549 | 41822.4569 | 1 | 41822.4569 | 41849.5486 | 1 | 41849.5486 | 41849.5486 | 1 | 41845.6285 | 41996.625 | 1 | 41845.6285 | 41862.7917 | 1 | 41863.3333 | 41893.5514 | 1 | 41893.5514 | 41936.5451 | 1 | 41936.5451 | 41996.625 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6736 | 1 | 41753.375 | 41757.3715 | 1 | 41757.3715 | 41761.4049 | 1 | 41761.4049 | 41767.6903 | 1 | 41767.6903 | 41778.6736 | 1 | 41774.7014 | 41855.6514 | 1 | 41774.7014 | 41785.7917 | 1 | 41786.3333 | 41801.3403 | 1 | 41801.3403 | 41823.4236 | 1 | 41823.4236 | 41855.6514 | 1 | 41855.6514 | 41855.6514 | 1 | 41844.6785 | 42003.6681 | 1 | 41844.6785 | 41862.7917 | 1 | 41863.3333 | 41891.6181 | 1 | 41891.6181 | 41934.4333 | 1 | 41934.4333 | 42003.6681 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4514 | 1 | 41753.375 | 41757.425 | 1 | 41757.425 | 41761.55 | 1 | 41761.55 | 41771.4285 | 1 | 41771.4285 | 41780.4514 | 1 | 41775.3931 | 41849.4236 | 1 | 41775.3931 | 41785.7917 | 1 | 41786.3333 | 41800.6819 | 1 | 41800.6819 | 41822.4465 | 1 | 41822.4465 | 41849.4236 | 1 | 41849.4236 | 41849.4236 | 1 | 41843.6681 | 42012.6347 | 1 | 41843.6681 | 41862.7917 | 1 | 41863.3333 | 41897.3799 | 1 | 41897.3799 | 41941.4569 | 1 | 41941.4569 | 42012.6347 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6632 | 1 | 41753.375 | 41757.3653 | 1 | 41757.3653 | 41760.6799 | 1 | 41760.6799 | 41768.3882 | 1 | 41768.3882 | 41778.6632 | 1 | 41775.3764 | 41857.4264 | 1 | 41775.3764 | 41785.7917 | 1 | 41786.3333 | 41800.6215 | 1 | 41800.6215 | 41824.3569 | 1 | 41824.3569 | 41857.4264 | 1 | 41857.4264 | 41857.4264 | 1 | 41843.6986 | 42010.5653 | 1 | 41843.6986 | 41862.7917 | 1 | 41863.3333 | 41891.625 | 1 | 41891.625 | 41940.6014 | 1 | 41940.6014 | 42010.5653 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5535 | 1 | 41753.375 | 41757.375 | 1 | 41757.375 | 41761.4382 | 1 | 41761.4382 | 41768.6833 | 1 | 41768.6833 | 41779.5535 | 1 | 41775.3667 | 41855.4597 | 1 | 41775.3667 | 41785.7917 | 1 | 41786.3333 | 41800.5847 | 1 | 41800.5847 | 41822.4799 | 1 | 41822.4799 | 41855.4597 | 1 | 41855.4597 | 41855.4597 | 1 | 41848.3764 | 42005.5451 | 1 | 41848.3764 | 41862.7917 | 1 | 41863.3333 | 41898.6486 | 1 | 41898.6486 | 41947.6583 | 1 | 41947.6583 | 42005.5451 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4618 | 1 | 41753.375 | 41757.4451 | 1 | 41757.4451 | 41761.65 | 1 | 41761.65 | 41768.6569 | 1 | 41768.6569 | 41780.4618 | 1 | 41773.6514 | 41850.6618 | 1 | 41773.6514 | 41785.7917 | 1 | 41786.3333 | 41799.5847 | 1 | 41799.5847 | 41820.6882 | 1 | 41820.6882 | 41850.6618 | 1 | 41850.6618 | 41850.6618 | 1 | 41848.3931 | 42016.6083 | 1 | 41848.3931 | 41862.7917 | 1 | 41863.3333 | 41894.5583 | 1 | 41894.5583 | 41942.5882 | 1 | 41942.5882 | 42016.6083 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6931 | 1 | 41753.375 | 41757.4215 | 1 | 41757.4215 | 41761.5764 | 1 | 41761.5764 | 41768.5965 | 1 | 41768.5965 | 41779.6931 | 1 | 41775.3701 | 41852.6583 | 1 | 41775.3701 | 41785.7917 | 1 | 41786.3333 | 41800.5882 | 1 | 41800.5882 | 41822.5681 | 1 | 41822.5681 | 41852.6583 | 1 | 41852.6583 | 41852.6583 | 1 | 41844.5819 | 42002.3403 | 1 | 41844.5819 | 41862.7917 | 1 | 41863.3333 | 41891.6514 | 1 | 41891.6514 | 41940.4965 | 1 | 41940.4965 | 42002.3403 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3549 | 1 | 41753.375 | 41754.7 | 1 | 41754.7 | 41761.3451 | 1 | 41761.3451 | 41767.6701 | 1 | 41767.6701 | 41779.3549 | 1 | 41775.3333 | 41848.6382 | 1 | 41775.3333 | 41785.7917 | 1 | 41786.3333 | 41800.5 | 1 | 41800.5417 | 41820.5951 | 1 | 41820.5951 | 41848.6382 | 1 | 41848.6382 | 41848.6382 | 1 | 41844.4569 | 42018.4868 | 1 | 41844.4569 | 41862.7917 | 1 | 41863.3333 | 41897.4799 | 1 | 41897.4799 | 41948.4264 | 1 | 41948.4264 | 42018.4868 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3986 | 1 | 41753.375 | 41757.4382 | 1 | 41757.4382 | 41761.5569 | 1 | 41761.5569 | 41768.3618 | 1 | 41768.3618 | 41779.3986 | 1 | 41773.675 | 41849.5653 | 1 | 41773.675 | 41785.7917 | 1 | 41786.3333 | 41801.4833 | 1 | 41801.4833 | 41821.3569 | 1 | 41821.3569 | 41849.5653 | 1 | 41849.5653 | 41849.5653 | 1 | 41845.6847 | 42009.5847 | 1 | 41845.6847 | 41862.7917 | 1 | 41863.3333 | 41893.625 | 1 | 41893.625 | 41936.7049 | 1 | 41936.7049 | 42009.5847 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6132 | 1 | 41753.375 | 41754.6931 | 1 | 41754.6931 | 41761.4118 | 1 | 41761.4118 | 41767.7035 | 1 | 41767.7035 | 41779.6132 | 1 | 41774.6049 | 41848.4632 | 1 | 41774.6049 | 41785.7917 | 1 | 41786.3333 | 41800.3701 | 1 | 41800.3701 | 41820.5549 | 1 | 41820.5549 | 41848.4632 | 1 | 41848.4632 | 41848.4632 | 1 | 41843.3535 | 42013.3965 | 1 | 41843.3535 | 41862.7917 | 1 | 41863.3333 | 41893.6653 | 1 | 41893.6653 | 41949.5 | 1 | 41949.5417 | 42013.3965 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6035 | 1 | 41753.375 | 41757.4583 | 1 | 41757.4583 | 41761.4514 | 1 | 41761.4514 | 41768.4014 | 1 | 41768.4014 | 41779.6035 | 1 | 41774.4569 | 41849.4431 | 1 | 41774.4569 | 41785.7917 | 1 | 41786.3333 | 41800.3764 | 1 | 41800.3764 | 41821.6153 | 1 | 41821.6153 | 41849.4431 | 1 | 41849.4431 | 41849.4431 | 1 | 41843.3667 | 42005.4931 | 1 | 41843.3667 | 41862.7917 | 1 | 41863.3333 | 41897.5681 | 1 | 41897.5681 | 41940.3569 | 1 | 41940.3569 | 42005.4931 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4153 | 1 | 41753.375 | 41757.3653 | 1 | 41757.3653 | 41761.4847 | 1 | 41761.4847 | 41771.4347 | 1 | 41771.4347 | 41780.4153 | 1 | 41775.3868 | 41849.4201 | 1 | 41775.3868 | 41785.7917 | 1 | 41786.3333 | 41801.4167 | 1 | 41801.4167 | 41821.5618 | 1 | 41821.5618 | 41849.4201 | 1 | 41849.4201 | 41849.4201 | 1 | 41845.6014 | 42017.7083 | 1 | 41845.6014 | 41862.7917 | 1 | 41863.3333 | 41892.5986 | 1 | 41892.5986 | 41942.5819 | 1 | 41942.5819 | 42017.7083 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3451 | 1 | 41753.375 | 41757.4618 | 1 | 41757.4618 | 41761.4618 | 1 | 41761.4618 | 41768.6403 | 1 | 41768.6403 | 41780.3451 | 1 | 41775.4368 | 41850.6153 | 1 | 41775.4368 | 41785.7917 | 1 | 41786.3333 | 41801.3569 | 1 | 41801.3569 | 41823.6181 | 1 | 41823.6181 | 41850.6153 | 1 | 41850.6153 | 41850.6153 | 1 | 41848.6118 | 41999.4069 | 1 | 41848.6118 | 41862.7917 | 1 | 41863.3333 | 41897.3736 | 1 | 41897.3736 | 41942.5847 | 1 | 41942.5847 | 41999.4069 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5667 | 1 | 41753.375 | 41757.3681 | 1 | 41757.3681 | 41761.6368 | 1 | 41761.6368 | 41768.4417 | 1 | 41768.4417 | 41779.5667 | 1 | 41775.4931 | 41850.6514 | 1 | 41775.4931 | 41785.7917 | 1 | 41786.3333 | 41801.3701 | 1 | 41801.3701 | 41820.5951 | 1 | 41820.5951 | 41850.6514 | 1 | 41850.6514 | 41850.6514 | 1 | 41845.6319 | 42002.4764 | 1 | 41845.6319 | 41862.7917 | 1 | 41863.3333 | 41899.675 | 1 | 41899.675 | 41943.6583 | 1 | 41943.6583 | 42002.4764 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6736 | 1 | 41753.375 | 41757.3715 | 1 | 41757.3715 | 41761.4882 | 1 | 41761.4882 | 41768.6236 | 1 | 41768.6236 | 41779.6736 | 1 | 41774.4333 | 41850.6986 | 1 | 41774.4333 | 41785.7917 | 1 | 41786.3333 | 41800.6153 | 1 | 41800.6153 | 41821.625 | 1 | 41821.625 | 41850.6986 | 1 | 41850.6986 | 41850.6986 | 1 | 41844.3535 | 41995.4833 | 1 | 41844.3535 | 41862.7917 | 1 | 41863.3333 | 41893.3368 | 1 | 41893.3368 | 41935.5847 | 1 | 41935.5847 | 41995.4833 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41781.3618 | 1 | 41753.375 | 41757.4014 | 1 | 41757.4014 | 41761.4715 | 1 | 41761.4715 | 41771.3847 | 1 | 41771.3847 | 41781.3618 | 1 | 41774.3368 | 41851.3535 | 1 | 41774.3368 | 41785.7917 | 1 | 41786.3333 | 41800.3903 | 1 | 41800.3903 | 41820.7083 | 1 | 41821.3333 | 41851.3535 | 1 | 41851.3535 | 41851.3535 | 1 | 41848.3431 | 41999.4167 | 1 | 41848.3431 | 41862.7917 | 1 | 41863.3333 | 41894.4632 | 1 | 41894.4632 | 41936.4736 | 1 | 41936.4736 | 41999.4167 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6368 | 1 | 41753.375 | 41757.3514 | 1 | 41757.3514 | 41760.6701 | 1 | 41760.6701 | 41768.3486 | 1 | 41768.3486 | 41778.6368 | 1 | 41774.6382 | 41848.4931 | 1 | 41774.6382 | 41785.7917 | 1 | 41786.3333 | 41800.4 | 1 | 41800.4 | 41822.3701 | 1 | 41822.3701 | 41848.4931 | 1 | 41848.4931 | 41848.4931 | 1 | 41845.3868 | 42005.3868 | 1 | 41845.3868 | 41862.7917 | 1 | 41863.3333 | 41899.6181 | 1 | 41899.6181 | 41943.4569 | 1 | 41943.4569 | 42005.3868 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.5667 | 1 | 41753.375 | 41754.7069 | 1 | 41754.7069 | 41760.6667 | 1 | 41760.6667 | 41767.5632 | 1 | 41767.5632 | 41778.5667 | 1 | 41775.4069 | 41851.4931 | 1 | 41775.4069 | 41785.7917 | 1 | 41786.3333 | 41800.3368 | 1 | 41800.3368 | 41821.5847 | 1 | 41821.5847 | 41851.4931 | 1 | 41851.4931 | 41851.4931 | 1 | 41844.6049 | 42002.3667 | 1 | 41844.6049 | 41862.7917 | 1 | 41863.3333 | 41891.6153 | 1 | 41891.6153 | 41940.5451 | 1 | 41940.5451 | 42002.3667 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5431 | 1 | 41753.375 | 41757.3819 | 1 | 41757.3819 | 41761.4285 | 1 | 41761.4285 | 41768.4618 | 1 | 41768.4618 | 41779.5431 | 1 | 41774.4201 | 41855.3903 | 1 | 41774.4201 | 41785.7917 | 1 | 41786.3333 | 41800.4632 | 1 | 41800.4632 | 41823.4535 | 1 | 41823.4535 | 41855.3903 | 1 | 41855.3903 | 41855.3903 | 1 | 41844.6514 | 42005.5514 | 1 | 41844.6514 | 41862.7917 | 1 | 41863.3333 | 41892.4236 | 1 | 41892.4236 | 41935.7083 | 1 | 41936.3333 | 42005.5514 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3917 | 1 | 41753.375 | 41757.3382 | 1 | 41757.3382 | 41761.3486 | 1 | 41761.3486 | 41768.3653 | 1 | 41768.3653 | 41779.3917 | 1 | 41775.4069 | 41848.6486 | 1 | 41775.4069 | 41785.7917 | 1 | 41786.3333 | 41799.4903 | 1 | 41799.4903 | 41820.6118 | 1 | 41820.6118 | 41848.6486 | 1 | 41848.6486 | 41848.6486 | 1 | 41845.3431 | 41999.5951 | 1 | 41845.3431 | 41862.7917 | 1 | 41863.3333 | 41893.4201 | 1 | 41893.4201 | 41943.3701 | 1 | 41943.3701 | 41999.5951 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3486 | 1 | 41753.375 | 41757.4417 | 1 | 41757.4417 | 41761.3681 | 1 | 41761.3681 | 41768.6333 | 1 | 41768.6333 | 41780.3486 | 1 | 41774.6618 | 41849.6715 | 1 | 41774.6618 | 41785.7917 | 1 | 41786.3333 | 41799.6514 | 1 | 41799.6514 | 41820.6847 | 1 | 41820.6847 | 41849.6715 | 1 | 41849.6715 | 41849.6715 | 1 | 41844.5451 | 41995.5451 | 1 | 41844.5451 | 41862.7917 | 1 | 41863.3333 | 41892.4701 | 1 | 41892.4701 | 41935.4736 | 1 | 41935.4736 | 41995.5451 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6868 | 1 | 41753.375 | 41757.4215 | 1 | 41757.4215 | 41761.375 | 1 | 41761.375 | 41767.7035 | 1 | 41767.7035 | 41778.6868 | 1 | 41775.3465 | 41849.5785 | 1 | 41775.3465 | 41785.7917 | 1 | 41786.3333 | 41800.5882 | 1 | 41800.5882 | 41822.3764 | 1 | 41822.3764 | 41849.5785 | 1 | 41849.5785 | 41849.5785 | 1 | 41848.6285 | 41996.6819 | 1 | 41848.6285 | 41862.7917 | 1 | 41863.3333 | 41891.3632 | 1 | 41891.3632 | 41934.4632 | 1 | 41934.4632 | 41996.6819 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4285 | 1 | 41753.375 | 41757.3514 | 1 | 41757.3514 | 41761.5701 | 1 | 41761.5701 | 41768.4618 | 1 | 41768.4618 | 41780.4285 | 1 | 41774.4667 | 41849.6014 | 1 | 41774.4667 | 41785.7917 | 1 | 41786.3333 | 41800.4701 | 1 | 41800.4701 | 41820.575 | 1 | 41820.575 | 41849.6014 | 1 | 41849.6014 | 41849.6014 | 1 | 41845.4 | 42006.6986 | 1 | 41845.4 | 41862.7917 | 1 | 41863.3333 | 41893.5653 | 1 | 41893.5653 | 41948.4535 | 1 | 41948.4535 | 42006.6986 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.65 | 1 | 41753.375 | 41757.4285 | 1 | 41757.4285 | 41761.4583 | 1 | 41761.4583 | 41768.4514 | 1 | 41768.4514 | 41778.65 | 1 | 41775.575 | 41851.5951 | 1 | 41775.575 | 41785.7917 | 1 | 41786.3333 | 41801.4597 | 1 | 41801.4597 | 41821.4736 | 1 | 41821.4736 | 41851.5951 | 1 | 41851.5951 | 41851.5951 | 1 | 41848.4965 | 42002.3632 | 1 | 41848.4965 | 41862.7917 | 1 | 41863.3333 | 41893.5785 | 1 | 41893.5785 | 41941.5882 | 1 | 41941.5882 | 42002.3632 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3514 | 1 | 41753.375 | 41757.425 | 1 | 41757.425 | 41761.4486 | 1 | 41761.4486 | 41768.5632 | 1 | 41768.5632 | 41780.3514 | 1 | 41774.6319 | 41848.4903 | 1 | 41774.6319 | 41785.7917 | 1 | 41786.3333 | 41799.5951 | 1 | 41799.5951 | 41820.4736 | 1 | 41820.4736 | 41848.4903 | 1 | 41848.4903 | 41848.4903 | 1 | 41845.3535 | 41998.3431 | 1 | 41845.3535 | 41862.7917 | 1 | 41863.3333 | 41892.6382 | 1 | 41892.6382 | 41935.6653 | 1 | 41935.6653 | 41998.3431 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6431 | 1 | 41753.375 | 41757.3785 | 1 | 41757.3785 | 41761.3785 | 1 | 41761.3785 | 41768.375 | 1 | 41768.375 | 41778.6431 | 1 | 41774.4903 | 41852.6014 | 1 | 41774.4903 | 41785.7917 | 1 | 41786.3333 | 41800.6681 | 1 | 41800.6681 | 41823.3965 | 1 | 41823.3965 | 41852.6014 | 1 | 41852.6014 | 41852.6014 | 1 | 41845.575 | 42004.4667 | 1 | 41845.575 | 41862.7917 | 1 | 41863.3333 | 41894.6681 | 1 | 41894.6681 | 41941.3799 | 1 | 41941.3799 | 42004.4667 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3917 | 1 | 41753.375 | 41757.3819 | 1 | 41757.3819 | 41761.55 | 1 | 41761.55 | 41768.6701 | 1 | 41768.6701 | 41780.3917 | 1 | 41774.6118 | 41850.3403 | 1 | 41774.6118 | 41785.7917 | 1 | 41786.3333 | 41800.6951 | 1 | 41800.6951 | 41823.3667 | 1 | 41823.3667 | 41850.3403 | 1 | 41850.3403 | 41850.3403 | 1 | 41845.5986 | 42013.6083 | 1 | 41845.5986 | 41862.7917 | 1 | 41863.3333 | 41900.4264 | 1 | 41900.4264 | 41948.4431 | 1 | 41948.4431 | 42013.6083 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6597 | 1 | 41753.375 | 41757.3347 | 1 | 41757.3347 | 41761.3882 | 1 | 41761.3882 | 41768.4486 | 1 | 41768.4486 | 41779.6597 | 1 | 41775.4799 | 41851.3833 | 1 | 41775.4799 | 41785.7917 | 1 | 41786.3333 | 41799.5951 | 1 | 41799.5951 | 41821.3465 | 1 | 41821.3465 | 41851.3833 | 1 | 41851.3833 | 41851.3833 | 1 | 41845.5486 | 41997.575 | 1 | 41845.5486 | 41862.7917 | 1 | 41863.3333 | 41891.4368 | 1 | 41891.4368 | 41940.3903 | 1 | 41940.3903 | 41997.575 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6403 | 1 | 41753.375 | 41757.4049 | 1 | 41757.4049 | 41761.6465 | 1 | 41761.6465 | 41771.4549 | 1 | 41771.4549 | 41780.6403 | 1 | 41775.5819 | 41848.3632 | 1 | 41775.5819 | 41785.7917 | 1 | 41786.3333 | 41800.3965 | 1 | 41800.3965 | 41817.7049 | 1 | 41817.7049 | 41848.3632 | 1 | 41848.3632 | 41848.3632 | 1 | 41848.575 | 42003.3597 | 1 | 41848.575 | 41862.7917 | 1 | 41863.3333 | 41898.3833 | 1 | 41898.3833 | 41941.5917 | 1 | 41941.5917 | 42003.3597 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6465 | 1 | 41753.375 | 41757.425 | 1 | 41757.425 | 41761.4951 | 1 | 41761.4951 | 41768.5799 | 1 | 41768.5799 | 41779.6465 | 1 | 41774.4167 | 41851.4667 | 1 | 41774.4167 | 41785.7917 | 1 | 41786.3333 | 41799.4465 | 1 | 41799.4465 | 41822.4667 | 1 | 41822.4667 | 41851.4667 | 1 | 41851.4667 | 41851.4667 | 1 | 41848.6215 | 42006.6847 | 1 | 41848.6215 | 41862.7917 | 1 | 41863.3333 | 41892.4764 | 1 | 41892.4764 | 41939.3903 | 1 | 41939.3903 | 42006.6847 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6903 | 1 | 41753.375 | 41757.3382 | 1 | 41757.3382 | 41760.6903 | 1 | 41760.6903 | 41768.4181 | 1 | 41768.4181 | 41779.6903 | 1 | 41775.4931 | 41850.4299 | 1 | 41775.4931 | 41785.7917 | 1 | 41786.3333 | 41801.3833 | 1 | 41801.3833 | 41822.3368 | 1 | 41822.3368 | 41850.4299 | 1 | 41850.4299 | 41850.4299 | 1 | 41844.575 | 41999.4333 | 1 | 41844.575 | 41862.7917 | 1 | 41863.3333 | 41894.4097 | 1 | 41894.4097 | 41940.3431 | 1 | 41940.3431 | 41999.4333 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3514 | 1 | 41753.375 | 41757.3347 | 1 | 41757.3347 | 41761.4215 | 1 | 41761.4215 | 41768.5764 | 1 | 41768.5764 | 41779.3514 | 1 | 41774.3632 | 41845.6951 | 1 | 41774.3632 | 41785.7917 | 1 | 41786.3333 | 41799.3799 | 1 | 41799.3799 | 41821.3368 | 1 | 41821.3368 | 41845.6951 | 1 | 41845.6951 | 41845.6951 | 1 | 41848.45 | 42004.3701 | 1 | 41848.45 | 41862.7917 | 1 | 41863.3333 | 41893.5451 | 1 | 41893.5451 | 41940.4264 | 1 | 41940.4264 | 42004.3701 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3549 | 1 | 41753.375 | 41757.4319 | 1 | 41757.4319 | 41761.4549 | 1 | 41761.4549 | 41771.3451 | 1 | 41771.3451 | 41780.3549 | 1 | 41774.7014 | 41852.6319 | 1 | 41774.7014 | 41785.7917 | 1 | 41786.3333 | 41799.6451 | 1 | 41799.6451 | 41821.5847 | 1 | 41821.5847 | 41852.6319 | 1 | 41852.6319 | 41852.6319 | 1 | 41842.4701 | 42002.6917 | 1 | 41842.4701 | 41862.7917 | 1 | 41863.3333 | 41891.4431 | 1 | 41891.4431 | 41939.4069 | 1 | 41939.4069 | 42002.6917 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6833 | 1 | 41753.375 | 41754.7035 | 1 | 41754.7035 | 41760.5833 | 1 | 41760.5833 | 41767.6299 | 1 | 41767.6299 | 41778.6833 | 1 | 41775.3868 | 41849.3368 | 1 | 41775.3868 | 41785.7917 | 1 | 41786.3333 | 41800.4236 | 1 | 41800.4236 | 41820.6549 | 1 | 41820.6549 | 41849.3368 | 1 | 41849.3368 | 41849.3368 | 1 | 41848.5847 | 41992.675 | 1 | 41848.5847 | 41862.7917 | 1 | 41863.3333 | 41892.6951 | 1 | 41892.6951 | 41935.5917 | 1 | 41935.5917 | 41992.675 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6167 | 1 | 41753.375 | 41757.375 | 1 | 41757.375 | 41761.3451 | 1 | 41761.3451 | 41768.3681 | 1 | 41768.3681 | 41778.6167 | 1 | 41775.4431 | 41850.4 | 1 | 41775.4431 | 41785.7917 | 1 | 41786.3333 | 41800.4403 | 1 | 41800.4403 | 41821.7083 | 1 | 41822.3333 | 41850.4 | 1 | 41850.4 | 41850.4 | 1 | 41844.3333 | 42013.7049 | 1 | 41844.3333 | 41862.7917 | 1 | 41863.3333 | 41898.5681 | 1 | 41898.5681 | 41941.3903 | 1 | 41941.3903 | 42013.7049 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4181 | 1 | 41753.375 | 41757.3417 | 1 | 41757.3417 | 41760.6701 | 1 | 41760.6701 | 41768.4549 | 1 | 41768.4549 | 41779.4181 | 1 | 41773.6215 | 41850.4167 | 1 | 41773.6215 | 41785.7917 | 1 | 41786.3333 | 41799.5882 | 1 | 41799.5882 | 41820.4965 | 1 | 41820.4965 | 41850.4167 | 1 | 41850.4167 | 41850.4167 | 1 | 41848.3799 | 42019.5847 | 1 | 41848.3799 | 41862.7917 | 1 | 41863.3333 | 41893.6486 | 1 | 41893.6486 | 41943.4069 | 1 | 41943.4069 | 42019.5847 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5431 | 1 | 41753.375 | 41757.475 | 1 | 41757.475 | 41761.6701 | 1 | 41761.6701 | 41768.5632 | 1 | 41768.5632 | 41779.5431 | 1 | 41774.6986 | 41850.675 | 1 | 41774.6986 | 41785.7917 | 1 | 41786.3333 | 41800.6118 | 1 | 41800.6118 | 41820.6917 | 1 | 41820.6917 | 41850.675 | 1 | 41850.675 | 41850.675 | 1 | 41845.6681 | 42020.5514 | 1 | 41845.6681 | 41862.7917 | 1 | 41863.3333 | 41894.3431 | 1 | 41894.3431 | 41940.7083 | 1 | 41941.3333 | 42020.5514 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3785 | 1 | 41753.375 | 41757.3583 | 1 | 41757.3583 | 41761.4417 | 1 | 41761.4417 | 41768.55 | 1 | 41768.55 | 41780.3785 | 1 | 41774.6382 | 41849.5785 | 1 | 41774.6382 | 41785.7917 | 1 | 41786.3333 | 41800.6417 | 1 | 41800.6417 | 41821.35 | 1 | 41821.35 | 41849.5785 | 1 | 41849.5785 | 41849.5785 | 1 | 41845.3597 | 42010.4236 | 1 | 41845.3597 | 41862.7917 | 1 | 41863.3333 | 41892.4965 | 1 | 41892.4965 | 41949.5951 | 1 | 41949.5951 | 42010.4236 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4715 | 1 | 41753.375 | 41757.4153 | 1 | 41757.4153 | 41761.4715 | 1 | 41761.4715 | 41768.4181 | 1 | 41768.4181 | 41779.4715 | 1 | 41775.4299 | 41850.6118 | 1 | 41775.4299 | 41785.7917 | 1 | 41786.3333 | 41799.5549 | 1 | 41799.5549 | 41823.4333 | 1 | 41823.4333 | 41850.6118 | 1 | 41850.6118 | 41850.6118 | 1 | 41844.4868 | 41999.3764 | 1 | 41844.4868 | 41862.7917 | 1 | 41863.3333 | 41891.4132 | 1 | 41891.4132 | 41941.6451 | 1 | 41941.6451 | 41999.3764 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4153 | 1 | 41753.375 | 41757.4285 | 1 | 41757.4285 | 41761.4285 | 1 | 41761.4285 | 41768.6868 | 1 | 41768.6868 | 41780.4153 | 1 | 41774.4799 | 41848.4736 | 1 | 41774.4799 | 41785.7917 | 1 | 41786.3333 | 41799.4097 | 1 | 41799.4097 | 41820.4535 | 1 | 41820.4535 | 41848.4736 | 1 | 41848.4736 | 41848.4736 | 1 | 41845.4833 | 42020.4903 | 1 | 41845.4833 | 41862.7917 | 1 | 41863.3333 | 41900.4035 | 1 | 41900.4035 | 41953.3931 | 1 | 41953.3931 | 42020.4903 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3681 | 1 | 41753.375 | 41757.3882 | 1 | 41757.3882 | 41761.425 | 1 | 41761.425 | 41768.5632 | 1 | 41768.5632 | 41779.3681 | 1 | 41774.6347 | 41850.6715 | 1 | 41774.6347 | 41785.7917 | 1 | 41786.3333 | 41800.5819 | 1 | 41800.5819 | 41822.3569 | 1 | 41822.3569 | 41850.6715 | 1 | 41850.6715 | 41850.6715 | 1 | 41848.5681 | 41995.5986 | 1 | 41848.5681 | 41862.7917 | 1 | 41863.3333 | 41891.6285 | 1 | 41891.6285 | 41935.6819 | 1 | 41935.6819 | 41995.5986 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4951 | 1 | 41753.375 | 41757.3847 | 1 | 41757.3847 | 41761.5764 | 1 | 41761.5764 | 41768.5833 | 1 | 41768.5833 | 41780.4951 | 1 | 41774.6417 | 41849.5514 | 1 | 41774.6417 | 41785.7917 | 1 | 41786.3333 | 41800.4403 | 1 | 41800.4403 | 41822.6583 | 1 | 41822.6583 | 41849.5514 | 1 | 41849.5514 | 41849.5514 | 1 | 41844.6715 | 42012.3764 | 1 | 41844.6715 | 41862.7917 | 1 | 41863.3333 | 41900.4701 | 1 | 41900.4701 | 41943.3597 | 1 | 41943.3597 | 42012.3764 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4153 | 1 | 41753.375 | 41757.4486 | 1 | 41757.4486 | 41761.4618 | 1 | 41761.4618 | 41768.4319 | 1 | 41768.4319 | 41779.4153 | 1 | 41774.3931 | 41849.45 | 1 | 41774.3931 | 41785.7917 | 1 | 41786.3333 | 41800.4431 | 1 | 41800.4431 | 41821.7049 | 1 | 41821.7049 | 41849.45 | 1 | 41849.45 | 41849.45 | 1 | 41848.4764 | 42025.7083 | 1 | 41848.4764 | 41862.7917 | 1 | 41863.3333 | 41892.35 | 1 | 41892.35 | 41943.4965 | 1 | 41943.4965 | 42025.7083 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5535 | 1 | 41753.375 | 41757.3618 | 1 | 41757.3618 | 41761.3514 | 1 | 41761.3514 | 41768.4715 | 1 | 41768.4715 | 41779.5535 | 1 | 41774.3833 | 41849.5 | 1 | 41774.3833 | 41785.7917 | 1 | 41786.3333 | 41799.6347 | 1 | 41799.6347 | 41821.4201 | 1 | 41821.4201 | 41849.5 | 1 | 41849.5 | 41849.5 | 1 | 41844.5514 | 42003.7083 | 1 | 41844.5514 | 41862.7917 | 1 | 41863.3333 | 41893.5 | 1 | 41893.5417 | 41940.5951 | 1 | 41940.5951 | 42003.7083 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6368 | 1 | 41753.375 | 41757.4917 | 1 | 41757.4917 | 41764.3847 | 1 | 41764.3847 | 41771.3653 | 1 | 41771.3653 | 41779.6368 | 1 | 41774.5917 | 41849.6986 | 1 | 41774.5917 | 41785.7917 | 1 | 41786.3333 | 41801.3597 | 1 | 41801.3597 | 41822.4132 | 1 | 41822.4132 | 41849.6986 | 1 | 41849.6986 | 41849.6986 | 1 | 41845.625 | 42009.3368 | 1 | 41845.625 | 41862.7917 | 1 | 41863.3333 | 41892.675 | 1 | 41892.675 | 41941.6785 | 1 | 41941.6785 | 42009.3368 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6736 | 1 | 41753.375 | 41757.3986 | 1 | 41757.3986 | 41760.6833 | 1 | 41760.6833 | 41767.6597 | 1 | 41767.6597 | 41779.6736 | 1 | 41775.4403 | 41849.5681 | 1 | 41775.4403 | 41785.7917 | 1 | 41786.3333 | 41800.4868 | 1 | 41800.4868 | 41820.6417 | 1 | 41820.6417 | 41849.5681 | 1 | 41849.5681 | 41849.5681 | 1 | 41848.6951 | 42002.5514 | 1 | 41848.6951 | 41862.7917 | 1 | 41863.3333 | 41892.5 | 1 | 41892.5417 | 41941.6486 | 1 | 41941.6486 | 42002.5514 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4653 | 1 | 41753.375 | 41757.3514 | 1 | 41757.3514 | 41761.5535 | 1 | 41761.5535 | 41768.3681 | 1 | 41768.3681 | 41779.4653 | 1 | 41774.4299 | 41849.4132 | 1 | 41774.4299 | 41785.7917 | 1 | 41786.3333 | 41799.6653 | 1 | 41799.6653 | 41822.3764 | 1 | 41822.3764 | 41849.4132 | 1 | 41849.4132 | 41849.4132 | 1 | 41844.3368 | 42002.4035 | 1 | 41844.3368 | 41862.7917 | 1 | 41863.3333 | 41894.3431 | 1 | 41894.3431 | 41943.4868 | 1 | 41943.4868 | 42002.4035 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3917 | 1 | 41753.375 | 41757.4986 | 1 | 41757.4986 | 41761.5799 | 1 | 41761.5799 | 41771.425 | 1 | 41771.425 | 41780.3917 | 1 | 41774.3431 | 41850.4597 | 1 | 41774.3431 | 41785.7917 | 1 | 41786.3333 | 41801.3931 | 1 | 41801.3931 | 41822.5451 | 1 | 41822.5451 | 41850.4597 | 1 | 41850.4597 | 41850.4597 | 1 | 41848.3368 | 41997.6417 | 1 | 41848.3368 | 41862.7917 | 1 | 41863.3333 | 41891.4597 | 1 | 41891.4597 | 41941.3701 | 1 | 41941.3701 | 41997.6417 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4382 | 1 | 41753.375 | 41754.7035 | 1 | 41754.7035 | 41760.7069 | 1 | 41760.7069 | 41768.5667 | 1 | 41768.5667 | 41780.4382 | 1 | 41775.3736 | 41855.3431 | 1 | 41775.3736 | 41785.7917 | 1 | 41786.3333 | 41801.5819 | 1 | 41801.5819 | 41824.5618 | 1 | 41824.5618 | 41855.3431 | 1 | 41855.3431 | 41855.3431 | 1 | 41845.3965 | 42026.6285 | 1 | 41845.3965 | 41862.7917 | 1 | 41863.3333 | 41892.45 | 1 | 41892.45 | 41954.4403 | 1 | 41954.4403 | 42026.6285 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4382 | 1 | 41753.375 | 41757.4181 | 1 | 41757.4181 | 41761.3347 | 1 | 41761.3347 | 41767.6965 | 1 | 41767.6965 | 41779.4382 | 1 | 41775.3965 | 41849.6382 | 1 | 41775.3965 | 41785.7917 | 1 | 41786.3333 | 41800.6514 | 1 | 41800.6514 | 41821.5486 | 1 | 41821.5486 | 41849.6382 | 1 | 41849.6382 | 41849.6382 | 1 | 41848.6917 | 42006.3465 | 1 | 41848.6917 | 41862.7917 | 1 | 41863.3333 | 41891.4465 | 1 | 41891.4465 | 41947.4667 | 1 | 41947.4667 | 42006.3465 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3583 | 1 | 41753.375 | 41757.375 | 1 | 41757.375 | 41761.4181 | 1 | 41761.4181 | 41768.6868 | 1 | 41768.6868 | 41780.3583 | 1 | 41774.3701 | 41855.3903 | 1 | 41774.3701 | 41785.7917 | 1 | 41786.3333 | 41800.6319 | 1 | 41800.6319 | 41823.4868 | 1 | 41823.4868 | 41855.3903 | 1 | 41855.3903 | 41855.3903 | 1 | 41844.5549 | 41996.6014 | 1 | 41844.5549 | 41862.7917 | 1 | 41863.3333 | 41891.6347 | 1 | 41891.6347 | 41935.3799 | 1 | 41935.3799 | 41996.6014 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5701 | 1 | 41753.375 | 41757.3917 | 1 | 41757.3917 | 41761.4215 | 1 | 41761.4215 | 41768.6403 | 1 | 41768.6403 | 41779.5701 | 1 | 41775.5715 | 41848.6181 | 1 | 41775.5715 | 41785.7917 | 1 | 41786.3333 | 41799.6417 | 1 | 41799.6417 | 41821.6549 | 1 | 41821.6549 | 41848.6181 | 1 | 41848.6181 | 41848.6181 | 1 | 41843.3833 | 42003.625 | 1 | 41843.3833 | 41862.7917 | 1 | 41863.3333 | 41894.3903 | 1 | 41894.3903 | 41936.4132 | 1 | 41936.4132 | 42003.625 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3986 | 1 | 41753.375 | 41757.4347 | 1 | 41757.4347 | 41761.4715 | 1 | 41761.4715 | 41768.6465 | 1 | 41768.6465 | 41780.3986 | 1 | 41774.5951 | 41857.6417 | 1 | 41774.5951 | 41785.7917 | 1 | 41786.3333 | 41801.4465 | 1 | 41801.4465 | 41824.6451 | 1 | 41824.6451 | 41857.6417 | 1 | 41857.6417 | 41857.6417 | 1 | 41845.4965 | 42012.5653 | 1 | 41845.4965 | 41862.7917 | 1 | 41863.3333 | 41900.3965 | 1 | 41900.3965 | 41947.6049 | 1 | 41947.6049 | 42012.5653 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6799 | 1 | 41753.375 | 41757.4417 | 1 | 41757.4417 | 41761.4319 | 1 | 41761.4319 | 41768.3347 | 1 | 41768.3347 | 41778.6799 | 1 | 41774.7049 | 41849.5917 | 1 | 41774.7049 | 41785.7917 | 1 | 41786.3333 | 41799.4632 | 1 | 41799.4632 | 41817.4236 | 1 | 41817.4236 | 41849.5917 | 1 | 41849.5917 | 41849.5917 | 1 | 41844.6583 | 42006.4264 | 1 | 41844.6583 | 41862.7917 | 1 | 41863.3333 | 41894.3736 | 1 | 41894.3736 | 41947.6819 | 1 | 41947.6819 | 42006.4264 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6632 | 1 | 41753.375 | 41757.3382 | 1 | 41757.3382 | 41761.4215 | 1 | 41761.4215 | 41768.4118 | 1 | 41768.4118 | 41779.6632 | 1 | 41775.4132 | 41850.3569 | 1 | 41775.4132 | 41785.7917 | 1 | 41786.3333 | 41800.4299 | 1 | 41800.4299 | 41820.6486 | 1 | 41820.6486 | 41850.3569 | 1 | 41850.3569 | 41850.3569 | 1 | 41845.6118 | 42009.45 | 1 | 41845.6118 | 41862.7917 | 1 | 41863.3333 | 41899.5653 | 1 | 41899.5653 | 41942.6417 | 1 | 41942.6417 | 42009.45 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4681 | 1 | 41753.375 | 41757.4285 | 1 | 41757.4285 | 41761.3618 | 1 | 41761.3618 | 41768.6 | 1 | 41768.6 | 41780.4681 | 1 | 41774.4868 | 41850.3465 | 1 | 41774.4868 | 41785.7917 | 1 | 41786.3333 | 41799.4667 | 1 | 41799.4667 | 41820.7014 | 1 | 41820.7014 | 41850.3465 | 1 | 41850.3465 | 41850.3465 | 1 | 41845.3368 | 41997.4299 | 1 | 41845.3368 | 41862.7917 | 1 | 41863.3333 | 41891.5451 | 1 | 41891.5451 | 41934.4035 | 1 | 41934.4035 | 41997.4299 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.65 | 1 | 41753.375 | 41757.4417 | 1 | 41757.4417 | 41761.3347 | 1 | 41761.3347 | 41768.3514 | 1 | 41768.3514 | 41778.65 | 1 | 41774.5681 | 41850.6819 | 1 | 41774.5681 | 41785.7917 | 1 | 41786.3333 | 41801.3736 | 1 | 41801.3736 | 41822.5653 | 1 | 41822.5653 | 41850.6819 | 1 | 41850.6819 | 41850.6819 | 1 | 41848.5819 | 42016.6319 | 1 | 41848.5819 | 41862.7917 | 1 | 41863.3333 | 41898.4035 | 1 | 41898.4035 | 41949.6486 | 1 | 41949.6486 | 42016.6319 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.55 | 1 | 41753.375 | 41757.3847 | 1 | 41757.3847 | 41761.4986 | 1 | 41761.4986 | 41768.5764 | 1 | 41768.5764 | 41779.55 | 1 | 41774.5882 | 41852.4201 | 1 | 41774.5882 | 41785.7917 | 1 | 41786.3333 | 41800.6514 | 1 | 41800.6514 | 41824.4764 | 1 | 41824.4764 | 41852.4201 | 1 | 41852.4201 | 41852.4201 | 1 | 41845.4931 | 41998.4299 | 1 | 41845.4931 | 41862.7917 | 1 | 41863.3333 | 41893.6215 | 1 | 41893.6215 | 41939.5514 | 1 | 41939.5514 | 41998.4299 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41781.3382 | 1 | 41753.375 | 41757.3681 | 1 | 41757.3681 | 41761.4319 | 1 | 41761.4319 | 41771.3486 | 1 | 41771.3486 | 41781.3382 | 1 | 41774.7049 | 41851.4132 | 1 | 41774.7049 | 41785.7917 | 1 | 41786.3333 | 41800.35 | 1 | 41800.35 | 41822.6285 | 1 | 41822.6285 | 41851.4132 | 1 | 41851.4132 | 41851.4132 | 1 | 41845.4965 | 42009.4465 | 1 | 41845.4965 | 41862.7917 | 1 | 41863.3333 | 41891.5986 | 1 | 41891.5986 | 41943.5486 | 1 | 41943.5486 | 42009.4465 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6764 | 1 | 41753.375 | 41757.4583 | 1 | 41757.4583 | 41761.4486 | 1 | 41761.4486 | 41768.4653 | 1 | 41768.4653 | 41778.6764 | 1 | 41774.6618 | 41851.4097 | 1 | 41774.6618 | 41785.7917 | 1 | 41786.3333 | 41799.5681 | 1 | 41799.5681 | 41822.6049 | 1 | 41822.6049 | 41851.4097 | 1 | 41851.4097 | 41851.4097 | 1 | 41848.6785 | 42002.4368 | 1 | 41848.6785 | 41862.7917 | 1 | 41863.3333 | 41897.6917 | 1 | 41897.6917 | 41942.6951 | 1 | 41942.6951 | 42002.4368 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3882 | 1 | 41753.375 | 41757.4215 | 1 | 41757.4215 | 41761.4681 | 1 | 41761.4681 | 41768.6069 | 1 | 41768.6069 | 41780.3882 | 1 | 41775.4465 | 41850.3931 | 1 | 41775.4465 | 41785.7917 | 1 | 41786.3333 | 41800.3799 | 1 | 41800.3799 | 41822.5583 | 1 | 41822.5583 | 41850.3931 | 1 | 41850.3931 | 41850.3931 | 1 | 41845.575 | 42006.6847 | 1 | 41845.575 | 41862.7917 | 1 | 41863.3333 | 41893.3736 | 1 | 41893.3736 | 41950.6847 | 1 | 41950.6847 | 42006.6847 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3514 | 1 | 41753.375 | 41757.3882 | 1 | 41757.3882 | 41761.4285 | 1 | 41761.4285 | 41768.3819 | 1 | 41768.3819 | 41779.3514 | 1 | 41774.4736 | 41851.4833 | 1 | 41774.4736 | 41785.7917 | 1 | 41786.3333 | 41800.4465 | 1 | 41800.4465 | 41821.5681 | 1 | 41821.5681 | 41851.4833 | 1 | 41851.4833 | 41851.4833 | 1 | 41843.6181 | 42003.5549 | 1 | 41843.6181 | 41862.7917 | 1 | 41863.3333 | 41891.6014 | 1 | 41891.6014 | 41940.3764 | 1 | 41940.3764 | 42003.5549 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4819 | 1 | 41753.375 | 41757.3681 | 1 | 41757.3681 | 41761.6299 | 1 | 41761.6299 | 41768.5931 | 1 | 41768.5931 | 41780.4819 | 1 | 41775.3868 | 41851.4535 | 1 | 41775.3868 | 41785.7917 | 1 | 41786.3333 | 41799.6917 | 1 | 41799.6917 | 41821.6417 | 1 | 41821.6417 | 41851.4535 | 1 | 41851.4535 | 41851.4535 | 1 | 41848.6049 | 42024.5618 | 1 | 41848.6049 | 41862.7917 | 1 | 41863.3333 | 41893.4903 | 1 | 41893.4903 | 41954.4299 | 1 | 41954.4299 | 42024.5618 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4382 | 1 | 41753.375 | 41757.3785 | 1 | 41757.3785 | 41761.4181 | 1 | 41761.4181 | 41768.55 | 1 | 41768.55 | 41780.4382 | 1 | 41774.6451 | 41852.6486 | 1 | 41774.6451 | 41785.7917 | 1 | 41786.3333 | 41800.5986 | 1 | 41800.5986 | 41822.4299 | 1 | 41822.4299 | 41852.6486 | 1 | 41852.6486 | 41852.6486 | 1 | 41848.4965 | 41992.3736 | 1 | 41848.4965 | 41862.7917 | 1 | 41863.3333 | 41893.3431 | 1 | 41893.3431 | 41935.4 | 1 | 41935.4 | 41992.3736 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3819 | 1 | 41753.375 | 41757.4618 | 1 | 41757.4618 | 41761.5868 | 1 | 41761.5868 | 41768.4951 | 1 | 41768.4951 | 41780.3819 | 1 | 41775.4167 | 41851.6347 | 1 | 41775.4167 | 41785.7917 | 1 | 41786.3333 | 41799.5486 | 1 | 41799.5486 | 41822.3569 | 1 | 41822.3569 | 41851.6347 | 1 | 41851.6347 | 41851.6347 | 1 | 41848.4465 | 42003.4903 | 1 | 41848.4465 | 41862.7917 | 1 | 41863.3333 | 41893.3597 | 1 | 41893.3597 | 41943.4368 | 1 | 41943.4368 | 42003.4903 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3715 | 1 | 41753.375 | 41757.4049 | 1 | 41757.4049 | 41761.4986 | 1 | 41761.4986 | 41771.3514 | 1 | 41771.3514 | 41780.3715 | 1 | 41775.4299 | 41851.4736 | 1 | 41775.4299 | 41785.7917 | 1 | 41786.3333 | 41799.7014 | 1 | 41799.7014 | 41822.4597 | 1 | 41822.4597 | 41851.4736 | 1 | 41851.4736 | 41851.4736 | 1 | 41848.6951 | 42033.675 | 1 | 41848.6951 | 41862.7917 | 1 | 41863.3333 | 41897.4868 | 1 | 41897.4868 | 41957.6014 | 1 | 41957.6014 | 42033.675 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6764 | 1 | 41753.375 | 41757.3847 | 1 | 41757.3847 | 41761.4715 | 1 | 41761.4715 | 41768.5535 | 1 | 41768.5535 | 41779.6764 | 1 | 41775.35 | 41849.4535 | 1 | 41775.35 | 41785.7917 | 1 | 41786.3333 | 41799.6681 | 1 | 41799.6681 | 41821.6153 | 1 | 41821.6153 | 41849.4535 | 1 | 41849.4535 | 41849.4535 | 1 | 41848.5951 | 42020.4333 | 1 | 41848.5951 | 41862.7917 | 1 | 41863.3333 | 41899.3736 | 1 | 41899.3736 | 41954.7049 | 1 | 41954.7049 | 42020.4333 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5701 | 1 | 41753.375 | 41757.3583 | 1 | 41757.3583 | 41761.3618 | 1 | 41761.3618 | 41767.6535 | 1 | 41767.6535 | 41779.5701 | 1 | 41774.6285 | 41848.3736 | 1 | 41774.6285 | 41785.7917 | 1 | 41786.3333 | 41800.3569 | 1 | 41800.3569 | 41820.3799 | 1 | 41820.3799 | 41848.3736 | 1 | 41848.3736 | 41848.3736 | 1 | 41844.5618 | 41998.6215 | 1 | 41844.5618 | 41862.7917 | 1 | 41863.3333 | 41892.3597 | 1 | 41892.3597 | 41934.6014 | 1 | 41934.6014 | 41998.6215 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3347 | 1 | 41753.375 | 41757.3917 | 1 | 41757.3917 | 41761.3785 | 1 | 41761.3785 | 41768.3653 | 1 | 41768.3653 | 41780.3347 | 1 | 41774.5847 | 41851.4764 | 1 | 41774.5847 | 41785.7917 | 1 | 41786.3333 | 41801.45 | 1 | 41801.45 | 41822.6181 | 1 | 41822.6181 | 41851.4764 | 1 | 41851.4764 | 41851.4764 | 1 | 41844.3667 | 42005.6549 | 1 | 41844.3667 | 41862.7917 | 1 | 41863.3333 | 41893.5514 | 1 | 41893.5514 | 41942.6153 | 1 | 41942.6153 | 42005.6549 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.5903 | 1 | 41753.375 | 41757.3451 | 1 | 41757.3451 | 41760.6097 | 1 | 41760.6097 | 41767.6535 | 1 | 41767.6535 | 41778.5903 | 1 | 41774.45 | 41848.5583 | 1 | 41774.45 | 41785.7917 | 1 | 41786.3333 | 41799.6118 | 1 | 41799.6118 | 41821.4 | 1 | 41821.4 | 41848.5583 | 1 | 41848.5583 | 41848.5583 | 1 | 41843.5486 | 42002.6382 | 1 | 41843.5486 | 41862.7917 | 1 | 41863.3333 | 41893.6417 | 1 | 41893.6417 | 41946.5653 | 1 | 41946.5653 | 42002.6382 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.5931 | 1 | 41753.375 | 41757.4847 | 1 | 41757.4847 | 41761.6132 | 1 | 41761.6132 | 41771.4882 | 1 | 41771.4882 | 41780.5931 | 1 | 41775.4799 | 41845.6882 | 1 | 41775.4799 | 41785.7917 | 1 | 41786.3333 | 41800.6347 | 1 | 41800.6347 | 41820.6917 | 1 | 41820.6917 | 41845.6882 | 1 | 41845.6882 | 41845.6882 | 1 | 41848.5681 | 41996.6715 | 1 | 41848.5681 | 41862.7917 | 1 | 41863.3333 | 41891.4931 | 1 | 41891.4931 | 41935.6549 | 1 | 41935.6549 | 41996.6715 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5833 | 1 | 41753.375 | 41757.4285 | 1 | 41757.4285 | 41761.4715 | 1 | 41761.4715 | 41768.4549 | 1 | 41768.4549 | 41779.5833 | 1 | 41775.3965 | 41855.4701 | 1 | 41775.3965 | 41785.7917 | 1 | 41786.3333 | 41799.6583 | 1 | 41799.6583 | 41822.5653 | 1 | 41822.5653 | 41855.4701 | 1 | 41855.4701 | 41855.4701 | 1 | 41843.5951 | 42026.5486 | 1 | 41843.5951 | 41862.7917 | 1 | 41863.3333 | 41894.6014 | 1 | 41894.6014 | 41954.3368 | 1 | 41954.3368 | 42026.5486 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.375 | 1 | 41753.375 | 41754.7069 | 1 | 41754.7069 | 41760.6833 | 1 | 41760.6833 | 41768.4847 | 1 | 41768.4847 | 41780.375 | 1 | 41774.625 | 41849.3535 | 1 | 41774.625 | 41785.7917 | 1 | 41786.3333 | 41799.6451 | 1 | 41799.6451 | 41820.5514 | 1 | 41820.5514 | 41849.3535 | 1 | 41849.3535 | 41849.3535 | 1 | 41843.4035 | 41995.575 | 1 | 41843.4035 | 41862.7917 | 1 | 41863.3333 | 41891.4069 | 1 | 41891.4069 | 41936.5715 | 1 | 41936.5715 | 41995.575 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.7 | 1 | 41753.375 | 41757.3514 | 1 | 41757.3514 | 41761.4785 | 1 | 41761.4785 | 41771.3583 | 1 | 41771.3583 | 41779.7 | 1 | 41774.5514 | 41845.6486 | 1 | 41774.5514 | 41785.7917 | 1 | 41786.3333 | 41799.4868 | 1 | 41799.4868 | 41820.3403 | 1 | 41820.3403 | 41845.6486 | 1 | 41845.6486 | 41845.6486 | 1 | 41843.4535 | 42002.7083 | 1 | 41843.4535 | 41862.7917 | 1 | 41863.3333 | 41893.575 | 1 | 41893.575 | 41936.5514 | 1 | 41936.5514 | 42002.7083 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4986 | 1 | 41753.375 | 41757.4215 | 1 | 41757.4215 | 41761.4951 | 1 | 41761.4951 | 41768.5431 | 1 | 41768.5431 | 41779.4986 | 1 | 41775.3465 | 41848.6451 | 1 | 41775.3465 | 41785.7917 | 1 | 41786.3333 | 41799.7049 | 1 | 41799.7049 | 41821.5583 | 1 | 41821.5583 | 41848.6451 | 1 | 41848.6451 | 41848.6451 | 1 | 41845.3764 | 42006.3764 | 1 | 41845.3764 | 41862.7917 | 1 | 41863.3333 | 41894.7049 | 1 | 41894.7049 | 41949.6653 | 1 | 41949.6653 | 42006.3764 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6465 | 1 | 41753.375 | 41757.4819 | 1 | 41757.4819 | 41761.5736 | 1 | 41761.5736 | 41768.6569 | 1 | 41768.6569 | 41779.6465 | 1 | 41773.6347 | 41845.6049 | 1 | 41773.6347 | 41785.7917 | 1 | 41786.3333 | 41799.6153 | 1 | 41799.6153 | 41817.5785 | 1 | 41817.5785 | 41845.6049 | 1 | 41845.6049 | 41845.6049 | 1 | 41848.4132 | 42003.4736 | 1 | 41848.4132 | 41862.7917 | 1 | 41863.3333 | 41891.6681 | 1 | 41891.6681 | 41942.3431 | 1 | 41942.3431 | 42003.4736 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5736 | 1 | 41753.375 | 41757.3382 | 1 | 41757.3382 | 41761.3451 | 1 | 41761.3451 | 41768.4715 | 1 | 41768.4715 | 41779.5736 | 1 | 41774.4667 | 41850.6014 | 1 | 41774.4667 | 41785.7917 | 1 | 41786.3333 | 41800.5986 | 1 | 41800.5986 | 41821.4465 | 1 | 41821.4465 | 41850.6014 | 1 | 41850.6014 | 41850.6014 | 1 | 41845.4264 | 42006.6319 | 1 | 41845.4264 | 41862.7917 | 1 | 41863.3333 | 41894.4903 | 1 | 41894.4903 | 41940.5514 | 1 | 41940.5514 | 42006.6319 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4847 | 1 | 41753.375 | 41757.3549 | 1 | 41757.3549 | 41761.3847 | 1 | 41761.3847 | 41771.3618 | 1 | 41771.3618 | 41780.4847 | 1 | 41775.3701 | 41845.4333 | 1 | 41775.3701 | 41785.7917 | 1 | 41786.3333 | 41799.6347 | 1 | 41799.6347 | 41820.3368 | 1 | 41820.3368 | 41845.4333 | 1 | 41845.4333 | 41845.4333 | 1 | 41848.4201 | 42003.5583 | 1 | 41848.4201 | 41862.7917 | 1 | 41863.3333 | 41897.4264 | 1 | 41897.4264 | 41939.6417 | 1 | 41939.6417 | 42003.5583 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.65 | 1 | 41753.375 | 41757.3715 | 1 | 41757.3715 | 41761.5465 | 1 | 41761.5465 | 41768.3986 | 1 | 41768.3986 | 41779.65 | 1 | 41775.4201 | 41851.4799 | 1 | 41775.4201 | 41785.7917 | 1 | 41786.3333 | 41800.625 | 1 | 41800.625 | 41822.4465 | 1 | 41822.4465 | 41851.4799 | 1 | 41851.4799 | 41851.4799 | 1 | 41844.5986 | 41999.3465 | 1 | 41844.5986 | 41862.7917 | 1 | 41863.3333 | 41891.7049 | 1 | 41891.7049 | 41935.5514 | 1 | 41935.5514 | 41999.3465 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.4083 | 1 | 41753.375 | 41757.3986 | 1 | 41757.3986 | 41760.6597 | 1 | 41760.6597 | 41767.6132 | 1 | 41767.6132 | 41778.4083 | 1 | 41775.3535 | 41852.4236 | 1 | 41775.3535 | 41785.7917 | 1 | 41786.3333 | 41800.4097 | 1 | 41800.4097 | 41821.6083 | 1 | 41821.6083 | 41852.4236 | 1 | 41852.4236 | 41852.4236 | 1 | 41845.3667 | 42006.3632 | 1 | 41845.3667 | 41862.7917 | 1 | 41863.3333 | 41894.5653 | 1 | 41894.5653 | 41941.3833 | 1 | 41941.3833 | 42006.3632 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4014 | 1 | 41753.375 | 41757.3882 | 1 | 41757.3882 | 41761.3917 | 1 | 41761.3917 | 41768.3514 | 1 | 41768.3514 | 41780.4014 | 1 | 41775.3569 | 41849.5 | 1 | 41775.3569 | 41785.7917 | 1 | 41786.3333 | 41801.4132 | 1 | 41801.4132 | 41821.675 | 1 | 41821.675 | 41849.5 | 1 | 41849.5 | 41849.5 | 1 | 41845.6847 | 42025.4701 | 1 | 41845.6847 | 41862.7917 | 1 | 41863.3333 | 41898.4097 | 1 | 41898.4097 | 41954.4069 | 1 | 41954.4069 | 42025.4701 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4153 | 1 | 41753.375 | 41757.3819 | 1 | 41757.3819 | 41761.5597 | 1 | 41761.5597 | 41768.6465 | 1 | 41768.6465 | 41780.4153 | 1 | 41775.4 | 41851.45 | 1 | 41775.4 | 41785.7917 | 1 | 41786.3333 | 41800.3931 | 1 | 41800.3931 | 41821.3569 | 1 | 41821.3569 | 41851.45 | 1 | 41851.45 | 41851.45 | 1 | 41843.4132 | 42023.3569 | 1 | 41843.4132 | 41862.7917 | 1 | 41863.3333 | 41898.7014 | 1 | 41898.7014 | 41955.4535 | 1 | 41955.4535 | 42023.3569 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6264 | 1 | 41753.375 | 41757.4347 | 1 | 41757.4347 | 41761.6597 | 1 | 41761.6597 | 41768.6236 | 1 | 41768.6236 | 41780.6264 | 1 | 41775.3701 | 41852.6417 | 1 | 41775.3701 | 41785.7917 | 1 | 41786.3333 | 41800.4903 | 1 | 41800.4903 | 41822.3965 | 1 | 41822.3965 | 41852.6417 | 1 | 41852.6417 | 41852.6417 | 1 | 41848.4299 | 42006.4333 | 1 | 41848.4299 | 41862.7917 | 1 | 41863.3333 | 41892.6486 | 1 | 41892.6486 | 41943.6917 | 1 | 41943.6917 | 42006.4333 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4285 | 1 | 41753.375 | 41757.3715 | 1 | 41757.3715 | 41761.6264 | 1 | 41761.6264 | 41771.4347 | 1 | 41771.4347 | 41780.4285 | 1 | 41774.6882 | 41851.7083 | 1 | 41774.6882 | 41785.7917 | 1 | 41786.3333 | 41801.3667 | 1 | 41801.3667 | 41823.4333 | 1 | 41823.4333 | 41851.7083 | 1 | 41851.7083 | 41851.7083 | 1 | 41848.4632 | 42011.4597 | 1 | 41848.4632 | 41862.7917 | 1 | 41863.3333 | 41891.5514 | 1 | 41891.5514 | 41942.6785 | 1 | 41942.6785 | 42011.4597 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3681 | 1 | 41753.375 | 41757.3417 | 1 | 41757.3417 | 41761.3847 | 1 | 41761.3847 | 41768.65 | 1 | 41768.65 | 41780.3681 | 1 | 41774.5583 | 41850.6514 | 1 | 41774.5583 | 41785.7917 | 1 | 41786.3333 | 41800.4701 | 1 | 41800.4701 | 41823.4236 | 1 | 41823.4236 | 41850.6514 | 1 | 41850.6514 | 41850.6514 | 1 | 41845.3403 | 42018.4368 | 1 | 41845.3403 | 41862.7917 | 1 | 41863.3333 | 41894.6049 | 1 | 41894.6049 | 41947.4035 | 1 | 41947.4035 | 42018.4368 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3382 | 1 | 41753.375 | 41757.4049 | 1 | 41757.4049 | 41761.3715 | 1 | 41761.3715 | 41768.4153 | 1 | 41768.4153 | 41780.3382 | 1 | 41775.3632 | 41850.5681 | 1 | 41775.3632 | 41785.7917 | 1 | 41786.3333 | 41800.6681 | 1 | 41800.6681 | 41822.5681 | 1 | 41822.5681 | 41850.5681 | 1 | 41850.5681 | 41850.5681 | 1 | 41844.4097 | 42006.45 | 1 | 41844.4097 | 41862.7917 | 1 | 41863.3333 | 41901.6014 | 1 | 41901.6014 | 41943.6049 | 1 | 41943.6049 | 42006.45 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4382 | 1 | 41753.375 | 41757.4153 | 1 | 41757.4153 | 41761.5931 | 1 | 41761.5931 | 41771.4319 | 1 | 41771.4319 | 41780.4382 | 1 | 41775.4764 | 41849.5986 | 1 | 41775.4764 | 41785.7917 | 1 | 41786.3333 | 41800.4868 | 1 | 41800.4868 | 41820.6382 | 1 | 41820.6382 | 41849.5986 | 1 | 41849.5986 | 41849.5986 | 1 | 41845.3833 | 42005.5715 | 1 | 41845.3833 | 41862.7917 | 1 | 41863.3333 | 41891.4931 | 1 | 41891.4931 | 41935.6417 | 1 | 41935.6417 | 42005.5715 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6431 | 1 | 41753.375 | 41757.3917 | 1 | 41757.3917 | 41761.425 | 1 | 41761.425 | 41767.6764 | 1 | 41767.6764 | 41779.6431 | 1 | 41774.6618 | 41850.4403 | 1 | 41774.6618 | 41785.7917 | 1 | 41786.3333 | 41801.625 | 1 | 41801.625 | 41823.6382 | 1 | 41823.6382 | 41850.4403 | 1 | 41850.4403 | 41850.4403 | 1 | 41845.6549 | 42005.5681 | 1 | 41845.6549 | 41862.7917 | 1 | 41863.3333 | 41899.7014 | 1 | 41899.7014 | 41942.6083 | 1 | 41942.6083 | 42005.5681 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6069 | 1 | 41753.375 | 41757.4285 | 1 | 41757.4285 | 41761.6069 | 1 | 41761.6069 | 41771.3514 | 1 | 41771.3514 | 41779.6069 | 1 | 41774.5819 | 41845.6583 | 1 | 41774.5819 | 41785.7917 | 1 | 41786.3333 | 41799.4333 | 1 | 41799.4333 | 41817.4201 | 1 | 41817.4201 | 41845.6583 | 1 | 41845.6583 | 41845.6583 | 1 | 41843.625 | 42005.3903 | 1 | 41843.625 | 41862.7917 | 1 | 41863.3333 | 41898.6153 | 1 | 41898.6153 | 41942.4236 | 1 | 41942.4236 | 42005.3903 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3583 | 1 | 41753.375 | 41757.4549 | 1 | 41757.4549 | 41761.5701 | 1 | 41761.5701 | 41768.5535 | 1 | 41768.5535 | 41780.3583 | 1 | 41774.5417 | 41850.5486 | 1 | 41774.5417 | 41785.7917 | 1 | 41786.3333 | 41800.4167 | 1 | 41800.4167 | 41822.6347 | 1 | 41822.6347 | 41850.5486 | 1 | 41850.5486 | 41850.5486 | 1 | 41848.6319 | 42010.4833 | 1 | 41848.6319 | 41862.7917 | 1 | 41863.3333 | 41900.6583 | 1 | 41900.6583 | 41950.4132 | 1 | 41950.4132 | 42010.4833 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3681 | 1 | 41753.375 | 41757.4451 | 1 | 41757.4451 | 41761.5465 | 1 | 41761.5465 | 41768.5903 | 1 | 41768.5903 | 41780.3681 | 1 | 41775.3368 | 41849.4201 | 1 | 41775.3368 | 41785.7917 | 1 | 41786.3333 | 41800.4764 | 1 | 41800.4764 | 41820.4465 | 1 | 41820.4465 | 41849.4201 | 1 | 41849.4201 | 41849.4201 | 1 | 41848.5917 | 42013.3403 | 1 | 41848.5917 | 41862.7917 | 1 | 41863.3333 | 41897.3833 | 1 | 41897.3833 | 41941.6417 | 1 | 41941.6417 | 42013.3403 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6764 | 1 | 41753.375 | 41757.4118 | 1 | 41757.4118 | 41761.3681 | 1 | 41761.3681 | 41768.3382 | 1 | 41768.3382 | 41778.6764 | 1 | 41774.5653 | 41851.4097 | 1 | 41774.5653 | 41785.7917 | 1 | 41786.3333 | 41800.5549 | 1 | 41800.5549 | 41823.4833 | 1 | 41823.4833 | 41851.4097 | 1 | 41851.4097 | 41851.4097 | 1 | 41848.4299 | 42017.5583 | 1 | 41848.4299 | 41862.7917 | 1 | 41863.3333 | 41898.4368 | 1 | 41898.4368 | 41949.3903 | 1 | 41949.3903 | 42017.5583 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6368 | 1 | 41753.375 | 41757.4347 | 1 | 41757.4347 | 41761.6569 | 1 | 41761.6569 | 41771.3549 | 1 | 41771.3549 | 41780.6368 | 1 | 41775.3368 | 41849.5618 | 1 | 41775.3368 | 41785.7917 | 1 | 41786.3333 | 41800.5681 | 1 | 41800.5681 | 41822.5549 | 1 | 41822.5549 | 41849.5618 | 1 | 41849.5618 | 41849.5618 | 1 | 41848.5514 | 42019.4465 | 1 | 41848.5514 | 41862.7917 | 1 | 41863.3333 | 41897.4701 | 1 | 41897.4701 | 41942.575 | 1 | 41942.575 | 42019.4465 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4785 | 1 | 41753.375 | 41757.3681 | 1 | 41757.3681 | 41761.4715 | 1 | 41761.4715 | 41768.4653 | 1 | 41768.4653 | 41779.4785 | 1 | 41774.6049 | 41855.6847 | 1 | 41774.6049 | 41785.7917 | 1 | 41786.3333 | 41800.4535 | 1 | 41800.4535 | 41823.5618 | 1 | 41823.5618 | 41855.6847 | 1 | 41855.6847 | 41855.6847 | 1 | 41844.5847 | 42002.5653 | 1 | 41844.5847 | 41862.7917 | 1 | 41863.3333 | 41898.6417 | 1 | 41898.6417 | 41940.6917 | 1 | 41940.6917 | 42002.5653 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4951 | 1 | 41753.375 | 41757.3653 | 1 | 41757.3653 | 41761.5931 | 1 | 41761.5931 | 41768.5764 | 1 | 41768.5764 | 41779.4951 | 1 | 41774.6917 | 41851.3931 | 1 | 41774.6917 | 41785.7917 | 1 | 41786.3333 | 41799.6285 | 1 | 41799.6285 | 41821.6715 | 1 | 41821.6715 | 41851.3931 | 1 | 41851.3931 | 41851.3931 | 1 | 41848.5785 | 42016.3597 | 1 | 41848.5785 | 41862.7917 | 1 | 41863.3333 | 41891.7083 | 1 | 41892.3333 | 41935.6347 | 1 | 41935.6347 | 42016.3597 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3785 | 1 | 41753.375 | 41757.3382 | 1 | 41757.3382 | 41761.3653 | 1 | 41761.3653 | 41768.3583 | 1 | 41768.3583 | 41780.3785 | 1 | 41774.3799 | 41851.575 | 1 | 41774.3799 | 41785.7917 | 1 | 41786.3333 | 41800.4736 | 1 | 41800.4736 | 41822.6382 | 1 | 41822.6382 | 41851.575 | 1 | 41851.575 | 41851.575 | 1 | 41844.4264 | 42004.3868 | 1 | 41844.4264 | 41862.7917 | 1 | 41863.3333 | 41891.4632 | 1 | 41891.4632 | 41939.5583 | 1 | 41939.5583 | 42004.3868 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.375 | 1 | 41753.375 | 41757.4153 | 1 | 41757.4153 | 41761.3486 | 1 | 41761.3486 | 41768.4549 | 1 | 41768.4549 | 41780.375 | 1 | 41775.35 | 41850.5486 | 1 | 41775.35 | 41785.7917 | 1 | 41786.3333 | 41800.6083 | 1 | 41800.6083 | 41822.5882 | 1 | 41822.5882 | 41850.5486 | 1 | 41850.5486 | 41850.5486 | 1 | 41844.4167 | 41999.6819 | 1 | 41844.4167 | 41862.7917 | 1 | 41863.3333 | 41897.5986 | 1 | 41897.5986 | 41941.4535 | 1 | 41941.4535 | 41999.6819 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6632 | 1 | 41753.375 | 41757.4118 | 1 | 41757.4118 | 41761.6069 | 1 | 41761.6069 | 41771.3986 | 1 | 41771.3986 | 41779.6632 | 1 | 41775.4167 | 41849.5847 | 1 | 41775.4167 | 41785.7917 | 1 | 41786.3333 | 41799.6917 | 1 | 41799.6917 | 41820.4097 | 1 | 41820.4097 | 41849.5847 | 1 | 41849.5847 | 41849.5847 | 1 | 41845.5785 | 42005.6681 | 1 | 41845.5785 | 41862.7917 | 1 | 41863.3333 | 41898.5986 | 1 | 41898.5986 | 41942.6715 | 1 | 41942.6715 | 42005.6681 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6035 | 1 | 41753.375 | 41757.4514 | 1 | 41757.4514 | 41761.6333 | 1 | 41761.6333 | 41768.6 | 1 | 41768.6 | 41779.6035 | 1 | 41774.5951 | 41852.5583 | 1 | 41774.5951 | 41785.7917 | 1 | 41786.3333 | 41800.4569 | 1 | 41800.4569 | 41821.4201 | 1 | 41821.4201 | 41852.5583 | 1 | 41852.5583 | 41852.5583 | 1 | 41843.4167 | 42013.6819 | 1 | 41843.4167 | 41862.7917 | 1 | 41863.3333 | 41898.3965 | 1 | 41898.3965 | 41949.4868 | 1 | 41949.4868 | 42013.6819 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6035 | 1 | 41753.375 | 41757.4347 | 1 | 41757.4347 | 41761.5667 | 1 | 41761.5667 | 41768.5868 | 1 | 41768.5868 | 41779.6035 | 1 | 41774.5681 | 41852.4569 | 1 | 41774.5681 | 41785.7917 | 1 | 41786.3333 | 41801.5549 | 1 | 41801.5549 | 41824.4299 | 1 | 41824.4299 | 41852.4569 | 1 | 41852.4569 | 41852.4569 | 1 | 41848.6014 | 42020.675 | 1 | 41848.6014 | 41862.7917 | 1 | 41863.3333 | 41897.5451 | 1 | 41897.5451 | 41948.5618 | 1 | 41948.5618 | 42020.675 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3951 | 1 | 41753.375 | 41757.3882 | 1 | 41757.3882 | 41761.3986 | 1 | 41761.3986 | 41768.3715 | 1 | 41768.3715 | 41779.3951 | 1 | 41774.3764 | 41849.675 | 1 | 41774.3764 | 41785.7917 | 1 | 41786.3333 | 41799.7049 | 1 | 41799.7049 | 41822.7014 | 1 | 41822.7014 | 41849.675 | 1 | 41849.675 | 41849.675 | 1 | 41845.4097 | 42013.4333 | 1 | 41845.4097 | 41862.7917 | 1 | 41863.3333 | 41894.6285 | 1 | 41894.6285 | 41954.4799 | 1 | 41954.4799 | 42013.4333 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.5431 | 1 | 41753.375 | 41757.3514 | 1 | 41757.3514 | 41760.6764 | 1 | 41760.6764 | 41767.6167 | 1 | 41767.6167 | 41778.5431 | 1 | 41774.4465 | 41849.6715 | 1 | 41774.4465 | 41785.7917 | 1 | 41786.3333 | 41800.4333 | 1 | 41800.4333 | 41820.4701 | 1 | 41820.4701 | 41849.6715 | 1 | 41849.6715 | 41849.6715 | 1 | 41844.5486 | 42020.3799 | 1 | 41844.5486 | 41862.7917 | 1 | 41863.3333 | 41892.5785 | 1 | 41892.5785 | 41946.4201 | 1 | 41946.4201 | 42020.3799 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.65 | 1 | 41753.375 | 41757.4681 | 1 | 41757.4681 | 41761.5965 | 1 | 41761.5965 | 41768.5701 | 1 | 41768.5701 | 41779.65 | 1 | 41774.5715 | 41851.7014 | 1 | 41774.5715 | 41785.7917 | 1 | 41786.3333 | 41800.4035 | 1 | 41800.4035 | 41822.4299 | 1 | 41822.4299 | 41851.7014 | 1 | 41851.7014 | 41851.7014 | 1 | 41845.6486 | 42017.4569 | 1 | 41845.6486 | 41862.7917 | 1 | 41863.3333 | 41898.3903 | 1 | 41898.3903 | 41955.4764 | 1 | 41955.4764 | 42017.4569 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6431 | 1 | 41753.375 | 41757.3951 | 1 | 41757.3951 | 41761.5632 | 1 | 41761.5632 | 41768.4653 | 1 | 41768.4653 | 41779.6431 | 1 | 41775.3701 | 41850.5715 | 1 | 41775.3701 | 41785.7917 | 1 | 41786.3333 | 41799.6819 | 1 | 41799.6819 | 41820.3931 | 1 | 41820.3931 | 41850.5715 | 1 | 41850.5715 | 41850.5715 | 1 | 41848.4236 | 42016.6715 | 1 | 41848.4236 | 41862.7917 | 1 | 41863.3333 | 41897.6153 | 1 | 41897.6153 | 41946.6882 | 1 | 41946.6882 | 42016.6715 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4451 | 1 | 41753.375 | 41757.3618 | 1 | 41757.3618 | 41761.3451 | 1 | 41761.3451 | 41768.4014 | 1 | 41768.4014 | 41779.4451 | 1 | 41775.3667 | 41849.3736 | 1 | 41775.3667 | 41785.7917 | 1 | 41786.3333 | 41801.35 | 1 | 41801.35 | 41821.45 | 1 | 41821.45 | 41849.3736 | 1 | 41849.3736 | 41849.3736 | 1 | 41845.6514 | 42006.625 | 1 | 41845.6514 | 41862.7917 | 1 | 41863.3333 | 41893.45 | 1 | 41893.45 | 41935.5847 | 1 | 41935.5847 | 42006.625 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.5431 | 1 | 41753.375 | 41757.4451 | 1 | 41757.4451 | 41761.4951 | 1 | 41761.4951 | 41768.4653 | 1 | 41768.4653 | 41780.5431 | 1 | 41774.4701 | 41849.6319 | 1 | 41774.4701 | 41785.7917 | 1 | 41786.3333 | 41801.6049 | 1 | 41801.6049 | 41822.4903 | 1 | 41822.4903 | 41849.6319 | 1 | 41849.6319 | 41849.6319 | 1 | 41843.575 | 41991.7049 | 1 | 41843.575 | 41862.7917 | 1 | 41863.3333 | 41891.4035 | 1 | 41891.4035 | 41934.5583 | 1 | 41934.5583 | 41991.7049 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4549 | 1 | 41753.375 | 41757.4014 | 1 | 41757.4014 | 41761.5764 | 1 | 41761.5764 | 41768.6465 | 1 | 41768.6465 | 41779.4549 | 1 | 41774.6715 | 41848.5618 | 1 | 41774.6715 | 41785.7917 | 1 | 41786.3333 | 41800.4167 | 1 | 41800.4167 | 41820.5715 | 1 | 41820.5715 | 41848.5618 | 1 | 41848.5618 | 41848.5618 | 1 | 41848.5514 | 42016.3799 | 1 | 41848.5514 | 41862.7917 | 1 | 41863.3333 | 41894.4299 | 1 | 41894.4299 | 41947.5514 | 1 | 41947.5514 | 42016.3799 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3549 | 1 | 41753.375 | 41757.3681 | 1 | 41757.3681 | 41761.4014 | 1 | 41761.4014 | 41768.3583 | 1 | 41768.3583 | 41779.3549 | 1 | 41774.6549 | 41855.5917 | 1 | 41774.6549 | 41785.7917 | 1 | 41786.3333 | 41799.45 | 1 | 41799.45 | 41822.3597 | 1 | 41822.3597 | 41855.5917 | 1 | 41855.5917 | 41855.5917 | 1 | 41845.6417 | 41995.4132 | 1 | 41845.6417 | 41862.7917 | 1 | 41863.3333 | 41894.4833 | 1 | 41894.4833 | 41939.3667 | 1 | 41939.3667 | 41995.4132 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6299 | 1 | 41753.375 | 41757.3715 | 1 | 41757.3715 | 41761.4486 | 1 | 41761.4486 | 41767.6833 | 1 | 41767.6833 | 41779.6299 | 1 | 41773.6083 | 41844.4569 | 1 | 41773.6083 | 41785.7917 | 1 | 41786.3333 | 41799.6618 | 1 | 41799.6618 | 41817.6382 | 1 | 41817.6382 | 41844.4569 | 1 | 41844.4569 | 41844.4569 | 1 | 41843.5715 | 42003.4097 | 1 | 41843.5715 | 41862.7917 | 1 | 41863.3333 | 41897.3368 | 1 | 41897.3368 | 41946.3965 | 1 | 41946.3965 | 42003.4097 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6903 | 1 | 41753.375 | 41757.3486 | 1 | 41757.3486 | 41760.6799 | 1 | 41760.6799 | 41768.4451 | 1 | 41768.4451 | 41778.6903 | 1 | 41773.6785 | 41851.5785 | 1 | 41773.6785 | 41785.7917 | 1 | 41786.3333 | 41799.4868 | 1 | 41799.4868 | 41822.3632 | 1 | 41822.3632 | 41851.5785 | 1 | 41851.5785 | 41851.5785 | 1 | 41848.4097 | 42023.4403 | 1 | 41848.4097 | 41862.7917 | 1 | 41863.3333 | 41894.5785 | 1 | 41894.5785 | 41942.4069 | 1 | 41942.4069 | 42023.4403 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6799 | 1 | 41753.375 | 41757.475 | 1 | 41757.475 | 41761.7069 | 1 | 41761.7069 | 41771.3514 | 1 | 41771.3514 | 41780.6799 | 1 | 41775.3597 | 41849.4701 | 1 | 41775.3597 | 41785.7917 | 1 | 41786.3333 | 41799.6951 | 1 | 41799.6951 | 41820.6049 | 1 | 41820.6049 | 41849.4701 | 1 | 41849.4701 | 41849.4701 | 1 | 41845.5882 | 41992.4236 | 1 | 41845.5882 | 41862.7917 | 1 | 41863.3333 | 41891.4667 | 1 | 41891.4667 | 41934.3736 | 1 | 41934.3736 | 41992.4236 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4882 | 1 | 41753.375 | 41757.4118 | 1 | 41757.4118 | 41761.5535 | 1 | 41761.5535 | 41768.4118 | 1 | 41768.4118 | 41779.4882 | 1 | 41774.575 | 41851.3667 | 1 | 41774.575 | 41785.7917 | 1 | 41786.3333 | 41799.5847 | 1 | 41799.5847 | 41821.5 | 1 | 41821.5417 | 41851.3667 | 1 | 41851.3667 | 41851.3667 | 1 | 41843.6819 | 42004.3465 | 1 | 41843.6819 | 41862.7917 | 1 | 41863.3333 | 41897.675 | 1 | 41897.675 | 41943.5486 | 1 | 41943.5486 | 42004.3465 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6 | 1 | 41753.375 | 41754.7035 | 1 | 41754.7035 | 41760.6632 | 1 | 41760.6632 | 41767.5535 | 1 | 41767.5535 | 41778.6 | 1 | 41775.3368 | 41850.4299 | 1 | 41775.3368 | 41785.7917 | 1 | 41786.3333 | 41799.4264 | 1 | 41799.4264 | 41817.6514 | 1 | 41817.6514 | 41850.4299 | 1 | 41850.4299 | 41850.4299 | 1 | 41848.4167 | 42010.4236 | 1 | 41848.4167 | 41862.7917 | 1 | 41863.3333 | 41901.5785 | 1 | 41901.5785 | 41950.4 | 1 | 41950.4 | 42010.4236 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4715 | 1 | 41753.375 | 41757.4118 | 1 | 41757.4118 | 41761.3451 | 1 | 41761.3451 | 41768.4819 | 1 | 41768.4819 | 41779.4715 | 1 | 41774.5451 | 41850.4403 | 1 | 41774.5451 | 41785.7917 | 1 | 41786.3333 | 41800.4035 | 1 | 41800.4035 | 41822.5847 | 1 | 41822.5847 | 41850.4403 | 1 | 41850.4403 | 41850.4403 | 1 | 41848.5486 | 42013.4701 | 1 | 41848.5486 | 41862.7917 | 1 | 41863.3333 | 41891.6785 | 1 | 41891.6785 | 41950.3764 | 1 | 41950.3764 | 42013.4701 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3514 | 1 | 41753.375 | 41757.4215 | 1 | 41757.4215 | 41761.3451 | 1 | 41761.3451 | 41767.6799 | 1 | 41767.6799 | 41780.3514 | 1 | 41774.5514 | 41852.3903 | 1 | 41774.5514 | 41785.7917 | 1 | 41786.3333 | 41800.3903 | 1 | 41800.3903 | 41821.6215 | 1 | 41821.6215 | 41852.3903 | 1 | 41852.3903 | 41852.3903 | 1 | 41845.4569 | 42009.3965 | 1 | 41845.4569 | 41862.7917 | 1 | 41863.3333 | 41892.4701 | 1 | 41892.4701 | 41946.4701 | 1 | 41946.4701 | 42009.3965 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4681 | 1 | 41753.375 | 41757.4653 | 1 | 41757.4653 | 41761.4153 | 1 | 41761.4153 | 41768.6 | 1 | 41768.6 | 41779.4681 | 1 | 41773.7049 | 41849.5583 | 1 | 41773.7049 | 41785.7917 | 1 | 41786.3333 | 41799.6986 | 1 | 41799.6986 | 41821.3833 | 1 | 41821.3833 | 41849.5583 | 1 | 41849.5583 | 41849.5583 | 1 | 41848.7049 | 41996.6486 | 1 | 41848.7049 | 41862.7917 | 1 | 41863.3333 | 41892.4833 | 1 | 41892.4833 | 41940.3965 | 1 | 41940.3965 | 41996.6486 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3451 | 1 | 41753.375 | 41757.3618 | 1 | 41757.3618 | 41761.3681 | 1 | 41761.3681 | 41767.6632 | 1 | 41767.6632 | 41779.3451 | 1 | 41775.3403 | 41850.6917 | 1 | 41775.3403 | 41785.7917 | 1 | 41786.3333 | 41800.3465 | 1 | 41800.3465 | 41823.3799 | 1 | 41823.3799 | 41850.6917 | 1 | 41850.6917 | 41850.6917 | 1 | 41845.6986 | 42006.5847 | 1 | 41845.6986 | 41862.7917 | 1 | 41863.3333 | 41894.625 | 1 | 41894.625 | 41940.3764 | 1 | 41940.3764 | 42006.5847 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3715 | 1 | 41753.375 | 41757.3382 | 1 | 41757.3382 | 41761.4347 | 1 | 41761.4347 | 41768.5569 | 1 | 41768.5569 | 41780.3715 | 1 | 41775.4597 | 41848.4403 | 1 | 41775.4597 | 41785.7917 | 1 | 41786.3333 | 41800.3569 | 1 | 41800.3569 | 41821.4868 | 1 | 41821.4868 | 41848.4403 | 1 | 41848.4403 | 41848.4403 | 1 | 41848.45 | 42017.4931 | 1 | 41848.45 | 41862.7917 | 1 | 41863.3333 | 41898.6285 | 1 | 41898.6285 | 41957.4736 | 1 | 41957.4736 | 42017.4931 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.7035 | 1 | 41753.375 | 41757.4618 | 1 | 41757.4618 | 41761.4549 | 1 | 41761.4549 | 41768.4653 | 1 | 41768.4653 | 41778.7035 | 1 | 41775.4667 | 41849.4799 | 1 | 41775.4667 | 41785.7917 | 1 | 41786.3333 | 41800.4667 | 1 | 41800.4667 | 41821.3465 | 1 | 41821.3465 | 41849.4799 | 1 | 41849.4799 | 41849.4799 | 1 | 41843.4597 | 42002.4667 | 1 | 41843.4597 | 41862.7917 | 1 | 41863.3333 | 41893.4569 | 1 | 41893.4569 | 41935.6049 | 1 | 41935.6049 | 42002.4667 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.3951 | 1 | 41753.375 | 41757.3618 | 1 | 41757.3618 | 41760.6569 | 1 | 41760.6569 | 41767.5597 | 1 | 41767.5597 | 41778.3951 | 1 | 41774.6653 | 41849.4431 | 1 | 41774.6653 | 41785.7917 | 1 | 41786.3333 | 41800.4868 | 1 | 41800.4868 | 41821.3632 | 1 | 41821.3632 | 41849.4431 | 1 | 41849.4431 | 41849.4431 | 1 | 41848.5549 | 42005.5618 | 1 | 41848.5549 | 41862.7917 | 1 | 41863.3333 | 41897.6319 | 1 | 41897.6319 | 41940.6417 | 1 | 41940.6417 | 42005.5618 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.5833 | 1 | 41753.375 | 41757.3785 | 1 | 41757.3785 | 41760.7 | 1 | 41760.7 | 41767.6201 | 1 | 41767.6201 | 41778.5833 | 1 | 41774.4403 | 41852.4097 | 1 | 41774.4403 | 41785.7917 | 1 | 41786.3333 | 41800.6583 | 1 | 41800.6583 | 41822.6583 | 1 | 41822.6583 | 41852.4097 | 1 | 41852.4097 | 41852.4097 | 1 | 41845.5819 | 42019.5618 | 1 | 41845.5819 | 41862.7917 | 1 | 41863.3333 | 41891.3764 | 1 | 41891.3764 | 41942.6285 | 1 | 41942.6285 | 42019.5618 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4514 | 1 | 41753.375 | 41757.3819 | 1 | 41757.3819 | 41761.5535 | 1 | 41761.5535 | 41768.6632 | 1 | 41768.6632 | 41780.4514 | 1 | 41774.5917 | 41852.4 | 1 | 41774.5917 | 41785.7917 | 1 | 41786.3333 | 41801.4069 | 1 | 41801.4069 | 41822.3597 | 1 | 41822.3597 | 41852.4 | 1 | 41852.4 | 41852.4 | 1 | 41845.4868 | 42017.4764 | 1 | 41845.4868 | 41862.7917 | 1 | 41863.3333 | 41892.3465 | 1 | 41892.3465 | 41936.3368 | 1 | 41936.3368 | 42017.4764 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4715 | 1 | 41753.375 | 41757.5465 | 1 | 41757.5465 | 41761.4819 | 1 | 41761.4819 | 41768.4451 | 1 | 41768.4451 | 41779.4715 | 1 | 41774.4931 | 41852.6347 | 1 | 41774.4931 | 41785.7917 | 1 | 41786.3333 | 41800.6486 | 1 | 41800.6486 | 41824.4097 | 1 | 41824.4097 | 41852.6347 | 1 | 41852.6347 | 41852.6347 | 1 | 41848.5618 | 42013.4299 | 1 | 41848.5618 | 41862.7917 | 1 | 41863.3333 | 41892.3667 | 1 | 41892.3667 | 41953.35 | 1 | 41953.35 | 42013.4299 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3382 | 1 | 41753.375 | 41757.3451 | 1 | 41757.3451 | 41761.475 | 1 | 41761.475 | 41768.4819 | 1 | 41768.4819 | 41780.3382 | 1 | 41774.3333 | 41849.4667 | 1 | 41774.3333 | 41785.7917 | 1 | 41786.3333 | 41799.625 | 1 | 41799.625 | 41820.4 | 1 | 41820.4 | 41849.4667 | 1 | 41849.4667 | 41849.4667 | 1 | 41845.5451 | 42006.575 | 1 | 41845.5451 | 41862.7917 | 1 | 41863.3333 | 41900.6653 | 1 | 41900.6653 | 41943.5847 | 1 | 41943.5847 | 42006.575 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6431 | 1 | 41753.375 | 41757.3583 | 1 | 41757.3583 | 41761.3681 | 1 | 41761.3681 | 41767.6965 | 1 | 41767.6965 | 41779.6431 | 1 | 41774.5819 | 41852.4465 | 1 | 41774.5819 | 41785.7917 | 1 | 41786.3333 | 41801.5514 | 1 | 41801.5514 | 41822.3368 | 1 | 41822.3368 | 41852.4465 | 1 | 41852.4465 | 41852.4465 | 1 | 41843.4 | 42010.5785 | 1 | 41843.4 | 41862.7917 | 1 | 41863.3333 | 41894.6785 | 1 | 41894.6785 | 41948.6215 | 1 | 41948.6215 | 42010.5785 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5931 | 1 | 41753.375 | 41754.7 | 1 | 41754.7 | 41760.6632 | 1 | 41760.6632 | 41768.4653 | 1 | 41768.4653 | 41779.5931 | 1 | 41774.5583 | 41848.6153 | 1 | 41774.5583 | 41785.7917 | 1 | 41786.3333 | 41799.6785 | 1 | 41799.6785 | 41820.6847 | 1 | 41820.6847 | 41848.6153 | 1 | 41848.6153 | 41848.6153 | 1 | 41848.4868 | 42006.3736 | 1 | 41848.4868 | 41862.7917 | 1 | 41863.3333 | 41901.3431 | 1 | 41901.3431 | 41949.5847 | 1 | 41949.5847 | 42006.3736 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4083 | 1 | 41753.375 | 41757.3785 | 1 | 41757.3785 | 41761.3618 | 1 | 41761.3618 | 41768.6368 | 1 | 41768.6368 | 41779.4083 | 1 | 41774.3903 | 41849.6181 | 1 | 41774.3903 | 41785.7917 | 1 | 41786.3333 | 41799.675 | 1 | 41799.675 | 41822.35 | 1 | 41822.35 | 41849.6181 | 1 | 41849.6181 | 41849.6181 | 1 | 41843.6083 | 42016.3736 | 1 | 41843.6083 | 41862.7917 | 1 | 41863.3333 | 41891.4736 | 1 | 41891.4736 | 41934.6514 | 1 | 41934.6514 | 42016.3736 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3583 | 1 | 41753.375 | 41757.4681 | 1 | 41757.4681 | 41761.4382 | 1 | 41761.4382 | 41768.5535 | 1 | 41768.5535 | 41779.3583 | 1 | 41774.5847 | 41848.6618 | 1 | 41774.5847 | 41785.7917 | 1 | 41786.3333 | 41800.4201 | 1 | 41800.4201 | 41821.4632 | 1 | 41821.4632 | 41848.6618 | 1 | 41848.6618 | 41848.6618 | 1 | 41845.4736 | 42004.6653 | 1 | 41845.4736 | 41862.7917 | 1 | 41863.3333 | 41892.6549 | 1 | 41892.6549 | 41936.4868 | 1 | 41936.4868 | 42004.6653 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4549 | 1 | 41753.375 | 41757.4583 | 1 | 41757.4583 | 41761.6736 | 1 | 41761.6736 | 41771.3514 | 1 | 41771.3514 | 41780.4549 | 1 | 41774.6882 | 41850.4931 | 1 | 41774.6882 | 41785.7917 | 1 | 41786.3333 | 41800.3569 | 1 | 41800.3569 | 41821.4569 | 1 | 41821.4569 | 41850.4931 | 1 | 41850.4931 | 41850.4931 | 1 | 41848.3569 | 42018.6347 | 1 | 41848.3569 | 41862.7917 | 1 | 41863.3333 | 41892.4597 | 1 | 41892.4597 | 41943.5715 | 1 | 41943.5715 | 42018.6347 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6764 | 1 | 41753.375 | 41757.4514 | 1 | 41757.4514 | 41761.6167 | 1 | 41761.6167 | 41768.6167 | 1 | 41768.6167 | 41779.6764 | 1 | 41773.6618 | 41851.5951 | 1 | 41773.6618 | 41785.7917 | 1 | 41786.3333 | 41800.6882 | 1 | 41800.6882 | 41822.6181 | 1 | 41822.6181 | 41851.5951 | 1 | 41851.5951 | 41851.5951 | 1 | 41842.4965 | 42005.3597 | 1 | 41842.4965 | 41862.7917 | 1 | 41863.3333 | 41891.3736 | 1 | 41891.3736 | 41934.4465 | 1 | 41934.4465 | 42005.3597 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4715 | 1 | 41753.375 | 41757.4382 | 1 | 41757.4382 | 41761.3819 | 1 | 41761.3819 | 41767.6931 | 1 | 41767.6931 | 41779.4715 | 1 | 41774.5917 | 41855.3736 | 1 | 41774.5917 | 41785.7917 | 1 | 41786.3333 | 41801.4236 | 1 | 41801.4236 | 41822.3535 | 1 | 41822.3535 | 41855.3736 | 1 | 41855.3736 | 41855.3736 | 1 | 41848.6347 | 42004.6382 | 1 | 41848.6347 | 41862.7917 | 1 | 41863.3333 | 41898.4403 | 1 | 41898.4403 | 41947.5715 | 1 | 41947.5715 | 42004.6382 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.65 | 1 | 41753.375 | 41757.3917 | 1 | 41757.3917 | 41761.5868 | 1 | 41761.5868 | 41768.5833 | 1 | 41768.5833 | 41779.65 | 1 | 41774.5986 | 41851.3632 | 1 | 41774.5986 | 41785.7917 | 1 | 41786.3333 | 41800.4264 | 1 | 41800.4264 | 41822.4868 | 1 | 41822.4868 | 41851.3632 | 1 | 41851.3632 | 41851.3632 | 1 | 41848.4701 | 42003.6181 | 1 | 41848.4701 | 41862.7917 | 1 | 41863.3333 | 41893.4431 | 1 | 41893.4431 | 41942.5819 | 1 | 41942.5819 | 42003.6181 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6903 | 1 | 41753.375 | 41757.3347 | 1 | 41757.3347 | 41760.6569 | 1 | 41760.6569 | 41768.3618 | 1 | 41768.3618 | 41778.6903 | 1 | 41774.6917 | 41848.6618 | 1 | 41774.6917 | 41785.7917 | 1 | 41786.3333 | 41800.35 | 1 | 41800.35 | 41821.4903 | 1 | 41821.4903 | 41848.6618 | 1 | 41848.6618 | 41848.6618 | 1 | 41844.4736 | 42004.6882 | 1 | 41844.4736 | 41862.7917 | 1 | 41863.3333 | 41897.4431 | 1 | 41897.4431 | 41948.6319 | 1 | 41948.6319 | 42004.6882 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5597 | 1 | 41753.375 | 41757.3819 | 1 | 41757.3819 | 41761.3715 | 1 | 41761.3715 | 41768.5903 | 1 | 41768.5903 | 41779.5597 | 1 | 41774.4132 | 41848.4569 | 1 | 41774.4132 | 41785.7917 | 1 | 41786.3333 | 41799.5951 | 1 | 41799.5951 | 41817.6118 | 1 | 41817.6118 | 41848.4569 | 1 | 41848.4569 | 41848.4569 | 1 | 41848.625 | 42017.6347 | 1 | 41848.625 | 41862.7917 | 1 | 41863.3333 | 41894.5917 | 1 | 41894.5917 | 41940.4965 | 1 | 41940.4965 | 42017.6347 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3681 | 1 | 41753.375 | 41757.3917 | 1 | 41757.3917 | 41761.4549 | 1 | 41761.4549 | 41768.4917 | 1 | 41768.4917 | 41779.3681 | 1 | 41774.6583 | 41848.4465 | 1 | 41774.6583 | 41785.7917 | 1 | 41786.3333 | 41799.4931 | 1 | 41799.4931 | 41820.6319 | 1 | 41820.6319 | 41848.4465 | 1 | 41848.4465 | 41848.4465 | 1 | 41848.4965 | 42013.6882 | 1 | 41848.4965 | 41862.7917 | 1 | 41863.3333 | 41897.3403 | 1 | 41897.3403 | 41941.6451 | 1 | 41941.6451 | 42013.6882 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3583 | 1 | 41753.375 | 41757.4014 | 1 | 41757.4014 | 41760.6868 | 1 | 41760.6868 | 41767.7035 | 1 | 41767.7035 | 41779.3583 | 1 | 41775.4201 | 41849.6486 | 1 | 41775.4201 | 41785.7917 | 1 | 41786.3333 | 41799.4569 | 1 | 41799.4569 | 41820.35 | 1 | 41820.35 | 41849.6486 | 1 | 41849.6486 | 41849.6486 | 1 | 41848.6347 | 42002.5681 | 1 | 41848.6347 | 41862.7917 | 1 | 41863.3333 | 41892.5882 | 1 | 41892.5882 | 41939.5549 | 1 | 41939.5549 | 42002.5681 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6431 | 1 | 41753.375 | 41757.3583 | 1 | 41757.3583 | 41761.4083 | 1 | 41761.4083 | 41767.6965 | 1 | 41767.6965 | 41778.6431 | 1 | 41774.4403 | 41851.6917 | 1 | 41774.4403 | 41785.7917 | 1 | 41786.3333 | 41800.5681 | 1 | 41800.5681 | 41821.6819 | 1 | 41821.6819 | 41851.6917 | 1 | 41851.6917 | 41851.6917 | 1 | 41845.4833 | 42006.625 | 1 | 41845.4833 | 41862.7917 | 1 | 41863.3333 | 41891.7049 | 1 | 41891.7049 | 41948.5583 | 1 | 41948.5583 | 42006.625 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.5431 | 1 | 41753.375 | 41757.4181 | 1 | 41757.4181 | 41761.475 | 1 | 41761.475 | 41768.6069 | 1 | 41768.6069 | 41780.5431 | 1 | 41775.4736 | 41848.4201 | 1 | 41775.4736 | 41785.7917 | 1 | 41786.3333 | 41799.4701 | 1 | 41799.4701 | 41817.4799 | 1 | 41817.4799 | 41848.4201 | 1 | 41848.4201 | 41848.4201 | 1 | 41844.4368 | 42010.5653 | 1 | 41844.4368 | 41862.7917 | 1 | 41863.3333 | 41891.5514 | 1 | 41891.5514 | 41933.5785 | 1 | 41933.5785 | 42010.5653 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4951 | 1 | 41753.375 | 41757.4653 | 1 | 41757.4653 | 41761.3618 | 1 | 41761.3618 | 41768.4153 | 1 | 41768.4153 | 41779.4951 | 1 | 41775.4132 | 41855.4701 | 1 | 41775.4132 | 41785.7917 | 1 | 41786.3333 | 41800.4701 | 1 | 41800.4701 | 41822.4465 | 1 | 41822.4465 | 41855.4701 | 1 | 41855.4701 | 41855.4701 | 1 | 41842.3903 | 42011.4368 | 1 | 41842.3903 | 41862.7917 | 1 | 41863.3333 | 41894.3701 | 1 | 41894.3701 | 41947.6618 | 1 | 41947.6618 | 42011.4368 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6799 | 1 | 41753.375 | 41757.4549 | 1 | 41757.4549 | 41761.4118 | 1 | 41761.4118 | 41768.3882 | 1 | 41768.3882 | 41778.6799 | 1 | 41775.4 | 41850.3701 | 1 | 41775.4 | 41785.7917 | 1 | 41786.3333 | 41800.3403 | 1 | 41800.3403 | 41820.7049 | 1 | 41820.7049 | 41850.3701 | 1 | 41850.3701 | 41850.3701 | 1 | 41848.7014 | 42019.4431 | 1 | 41848.7014 | 41862.7917 | 1 | 41863.3333 | 41894.6583 | 1 | 41894.6583 | 41949.3403 | 1 | 41949.3403 | 42019.4431 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.425 | 1 | 41753.375 | 41757.3882 | 1 | 41757.3882 | 41761.6368 | 1 | 41761.6368 | 41768.6799 | 1 | 41768.6799 | 41780.425 | 1 | 41773.6951 | 41849.4931 | 1 | 41773.6951 | 41785.7917 | 1 | 41786.3333 | 41801.6417 | 1 | 41801.6417 | 41822.4403 | 1 | 41822.4403 | 41849.4931 | 1 | 41849.4931 | 41849.4931 | 1 | 41844.4569 | 41996.5882 | 1 | 41844.4569 | 41862.7917 | 1 | 41863.3333 | 41894.4465 | 1 | 41894.4465 | 41939.3868 | 1 | 41939.3868 | 41996.5882 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6 | 1 | 41753.375 | 41757.4215 | 1 | 41757.4215 | 41761.4951 | 1 | 41761.4951 | 41768.6597 | 1 | 41768.6597 | 41780.6 | 1 | 41774.6347 | 41848.4764 | 1 | 41774.6347 | 41785.7917 | 1 | 41786.3333 | 41799.4736 | 1 | 41799.4736 | 41821.3667 | 1 | 41821.3667 | 41848.4764 | 1 | 41848.4764 | 41848.4764 | 1 | 41843.6417 | 42023.5549 | 1 | 41843.6417 | 41862.7917 | 1 | 41863.3333 | 41904.4569 | 1 | 41904.4569 | 41962.6118 | 1 | 41962.6118 | 42023.5549 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3583 | 1 | 41753.375 | 41757.375 | 1 | 41757.375 | 41761.6167 | 1 | 41761.6167 | 41768.5833 | 1 | 41768.5833 | 41780.3583 | 1 | 41775.5583 | 41852.5951 | 1 | 41775.5583 | 41785.7917 | 1 | 41786.3333 | 41801.4764 | 1 | 41801.4764 | 41822.6847 | 1 | 41822.6847 | 41852.5951 | 1 | 41852.5951 | 41852.5951 | 1 | 41844.3569 | 42013.3736 | 1 | 41844.3569 | 41862.7917 | 1 | 41863.3333 | 41901.4535 | 1 | 41901.4535 | 41948.625 | 1 | 41948.625 | 42013.3736 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3451 | 1 | 41753.375 | 41757.3618 | 1 | 41757.3618 | 41761.5736 | 1 | 41761.5736 | 41768.5799 | 1 | 41768.5799 | 41780.3451 | 1 | 41775.3333 | 41845.4035 | 1 | 41775.3333 | 41785.7917 | 1 | 41786.3333 | 41799.5986 | 1 | 41799.5986 | 41817.6653 | 1 | 41817.6653 | 41845.4035 | 1 | 41845.4035 | 41845.4035 | 1 | 41848.4535 | 42018.4833 | 1 | 41848.4535 | 41862.7917 | 1 | 41863.3333 | 41893.4132 | 1 | 41893.4132 | 41954.4535 | 1 | 41954.4535 | 42018.4833 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3847 | 1 | 41753.375 | 41757.4215 | 1 | 41757.4215 | 41761.4785 | 1 | 41761.4785 | 41768.4917 | 1 | 41768.4917 | 41780.3847 | 1 | 41775.4667 | 41857.5882 | 1 | 41775.4667 | 41785.7917 | 1 | 41786.3333 | 41801.6319 | 1 | 41801.6319 | 41827.35 | 1 | 41827.35 | 41857.5882 | 1 | 41857.5882 | 41857.5882 | 1 | 41843.5882 | 42002.45 | 1 | 41843.5882 | 41862.7917 | 1 | 41863.3333 | 41893.575 | 1 | 41893.575 | 41946.4264 | 1 | 41946.4264 | 42002.45 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5597 | 1 | 41753.375 | 41757.4153 | 1 | 41757.4153 | 41761.3785 | 1 | 41761.3785 | 41768.3917 | 1 | 41768.3917 | 41779.5597 | 1 | 41774.6681 | 41849.5 | 1 | 41774.6681 | 41785.7917 | 1 | 41786.3333 | 41799.4764 | 1 | 41799.4764 | 41821.3597 | 1 | 41821.3597 | 41849.5 | 1 | 41849.5 | 41849.5 | 1 | 41845.625 | 42006.4035 | 1 | 41845.625 | 41862.7917 | 1 | 41863.3333 | 41899.5486 | 1 | 41899.5486 | 41942.4701 | 1 | 41942.4701 | 42006.4035 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4618 | 1 | 41753.375 | 41757.3417 | 1 | 41757.3417 | 41761.4382 | 1 | 41761.4382 | 41768.4715 | 1 | 41768.4715 | 41779.4618 | 1 | 41773.6181 | 41852.6986 | 1 | 41773.6181 | 41785.7917 | 1 | 41786.3333 | 41800.4069 | 1 | 41800.4069 | 41822.6951 | 1 | 41822.6951 | 41852.6986 | 1 | 41852.6986 | 41852.6986 | 1 | 41843.6014 | 41996.6917 | 1 | 41843.6014 | 41862.7917 | 1 | 41863.3333 | 41894.6382 | 1 | 41894.6382 | 41939.6285 | 1 | 41939.6285 | 41996.6917 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6701 | 1 | 41753.375 | 41757.4049 | 1 | 41757.4049 | 41761.4215 | 1 | 41761.4215 | 41768.4486 | 1 | 41768.4486 | 41779.6701 | 1 | 41774.4965 | 41848.3535 | 1 | 41774.4965 | 41785.7917 | 1 | 41786.3333 | 41800.3736 | 1 | 41800.3736 | 41820.6819 | 1 | 41820.6819 | 41848.3535 | 1 | 41848.3535 | 41848.3535 | 1 | 41848.6882 | 42002.6882 | 1 | 41848.6882 | 41862.7917 | 1 | 41863.3333 | 41892.6153 | 1 | 41892.6153 | 41940.5681 | 1 | 41940.5681 | 42002.6882 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4486 | 1 | 41753.375 | 41757.4514 | 1 | 41757.4514 | 41761.5903 | 1 | 41761.5903 | 41768.6736 | 1 | 41768.6736 | 41780.4486 | 1 | 41774.625 | 41851.5 | 1 | 41774.625 | 41785.7917 | 1 | 41786.3333 | 41799.6319 | 1 | 41799.6319 | 41820.5549 | 1 | 41820.5549 | 41851.5 | 1 | 41851.5 | 41851.5 | 1 | 41848.6514 | 42026.4597 | 1 | 41848.6514 | 41862.7917 | 1 | 41863.3333 | 41891.4403 | 1 | 41891.4403 | 41948.4799 | 1 | 41948.4799 | 42026.4597 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3681 | 1 | 41753.375 | 41757.3951 | 1 | 41757.3951 | 41761.3618 | 1 | 41761.3618 | 41768.4514 | 1 | 41768.4514 | 41780.3681 | 1 | 41774.6083 | 41851.6118 | 1 | 41774.6083 | 41785.7917 | 1 | 41786.3333 | 41799.6653 | 1 | 41799.6653 | 41822.4431 | 1 | 41822.4431 | 41851.6118 | 1 | 41851.6118 | 41851.6118 | 1 | 41844.6549 | 42006.6514 | 1 | 41844.6549 | 41862.7917 | 1 | 41863.3333 | 41893.6083 | 1 | 41893.6083 | 41943.6181 | 1 | 41943.6181 | 42006.6514 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4514 | 1 | 41753.375 | 41757.3785 | 1 | 41757.3785 | 41761.4417 | 1 | 41761.4417 | 41768.3785 | 1 | 41768.3785 | 41779.4514 | 1 | 41775.3535 | 41858.4 | 1 | 41775.3535 | 41785.7917 | 1 | 41786.3333 | 41801.4701 | 1 | 41801.4701 | 41824.4965 | 1 | 41824.4965 | 41858.4 | 1 | 41858.4 | 41858.4 | 1 | 41848.625 | 42011.5618 | 1 | 41848.625 | 41862.7917 | 1 | 41863.3333 | 41893.3535 | 1 | 41893.3535 | 41949.4903 | 1 | 41949.4903 | 42011.5618 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3417 | 1 | 41753.375 | 41757.475 | 1 | 41757.475 | 41761.4917 | 1 | 41761.4917 | 41768.4215 | 1 | 41768.4215 | 41780.3417 | 1 | 41775.5847 | 41851.5451 | 1 | 41775.5847 | 41785.7917 | 1 | 41786.3333 | 41800.6951 | 1 | 41800.6951 | 41821.5951 | 1 | 41821.5951 | 41851.5451 | 1 | 41851.5451 | 41851.5451 | 1 | 41848.6986 | 42004.4431 | 1 | 41848.6986 | 41862.7917 | 1 | 41863.3333 | 41894.4965 | 1 | 41894.4965 | 41947.35 | 1 | 41947.35 | 42004.4431 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4347 | 1 | 41753.375 | 41757.4014 | 1 | 41757.4014 | 41761.4382 | 1 | 41761.4382 | 41768.6201 | 1 | 41768.6201 | 41779.4347 | 1 | 41775.4597 | 41850.4833 | 1 | 41775.4597 | 41785.7917 | 1 | 41786.3333 | 41800.6618 | 1 | 41800.6618 | 41822.3597 | 1 | 41822.3597 | 41850.4833 | 1 | 41850.4833 | 41850.4833 | 1 | 41843.6847 | 42025.675 | 1 | 41843.6847 | 41862.7917 | 1 | 41863.3333 | 41898.5486 | 1 | 41898.5486 | 41948.4264 | 1 | 41948.4264 | 42025.675 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3819 | 1 | 41753.375 | 41757.3618 | 1 | 41757.3618 | 41761.3618 | 1 | 41761.3618 | 41767.6535 | 1 | 41767.6535 | 41779.3819 | 1 | 41773.6882 | 41849.4799 | 1 | 41773.6882 | 41785.7917 | 1 | 41786.3333 | 41799.6715 | 1 | 41799.6715 | 41821.6382 | 1 | 41821.6382 | 41849.4799 | 1 | 41849.4799 | 41849.4799 | 1 | 41848.6681 | 42003.6014 | 1 | 41848.6681 | 41862.7917 | 1 | 41863.3333 | 41899.6083 | 1 | 41899.6083 | 41946.3764 | 1 | 41946.3764 | 42003.6014 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3882 | 1 | 41753.375 | 41757.3451 | 1 | 41757.3451 | 41761.3347 | 1 | 41761.3347 | 41767.6535 | 1 | 41767.6535 | 41780.3882 | 1 | 41774.6285 | 41851.5819 | 1 | 41774.6285 | 41785.7917 | 1 | 41786.3333 | 41800.4 | 1 | 41800.4 | 41820.6153 | 1 | 41820.6153 | 41851.5819 | 1 | 41851.5819 | 41851.5819 | 1 | 41844.4035 | 42003.3465 | 1 | 41844.4035 | 41862.7917 | 1 | 41863.3333 | 41893.4868 | 1 | 41893.4868 | 41941.4069 | 1 | 41941.4069 | 42003.3465 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5965 | 1 | 41753.375 | 41757.4083 | 1 | 41757.4083 | 41761.4785 | 1 | 41761.4785 | 41768.5667 | 1 | 41768.5667 | 41779.5965 | 1 | 41774.3701 | 41852.3535 | 1 | 41774.3701 | 41785.7917 | 1 | 41786.3333 | 41799.5681 | 1 | 41799.5681 | 41821.3965 | 1 | 41821.3965 | 41852.3535 | 1 | 41852.3535 | 41852.3535 | 1 | 41845.5819 | 42011.3465 | 1 | 41845.5819 | 41862.7917 | 1 | 41863.3333 | 41900.6882 | 1 | 41900.6882 | 41950.4333 | 1 | 41950.4333 | 42011.3465 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4847 | 1 | 41753.375 | 41757.4319 | 1 | 41757.4319 | 41761.4049 | 1 | 41761.4049 | 41768.5701 | 1 | 41768.5701 | 41779.4847 | 1 | 41774.5451 | 41851.3833 | 1 | 41774.5451 | 41785.7917 | 1 | 41786.3333 | 41800.5951 | 1 | 41800.5951 | 41821.4569 | 1 | 41821.4569 | 41851.3833 | 1 | 41851.3833 | 41851.3833 | 1 | 41845.6618 | 41999.6986 | 1 | 41845.6618 | 41862.7917 | 1 | 41863.3333 | 41892.6681 | 1 | 41892.6681 | 41939.6083 | 1 | 41939.6083 | 41999.6986 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3451 | 1 | 41753.375 | 41757.4514 | 1 | 41757.4514 | 41761.4951 | 1 | 41761.4951 | 41768.6965 | 1 | 41768.6965 | 41780.3451 | 1 | 41774.4736 | 41851.6681 | 1 | 41774.4736 | 41785.7917 | 1 | 41786.3333 | 41800.4132 | 1 | 41800.4132 | 41821.3535 | 1 | 41821.3535 | 41851.6681 | 1 | 41851.6681 | 41851.6681 | 1 | 41843.45 | 42024.4632 | 1 | 41843.45 | 41862.7917 | 1 | 41863.3333 | 41899.6285 | 1 | 41899.6285 | 41950.3931 | 1 | 41950.3931 | 42024.4632 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4583 | 1 | 41753.375 | 41757.4681 | 1 | 41757.4681 | 41761.7069 | 1 | 41761.7069 | 41768.7 | 1 | 41768.7 | 41780.4583 | 1 | 41774.6153 | 41852.3597 | 1 | 41774.6153 | 41785.7917 | 1 | 41786.3333 | 41800.4597 | 1 | 41800.4597 | 41822.6819 | 1 | 41822.6819 | 41852.3597 | 1 | 41852.3597 | 41852.3597 | 1 | 41845.6618 | 41996.6181 | 1 | 41845.6618 | 41862.7917 | 1 | 41863.3333 | 41892.6049 | 1 | 41892.6049 | 41935.4167 | 1 | 41935.4167 | 41996.6181 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3583 | 1 | 41753.375 | 41757.4049 | 1 | 41757.4049 | 41761.3681 | 1 | 41761.3681 | 41767.6736 | 1 | 41767.6736 | 41780.3583 | 1 | 41774.3736 | 41850.6153 | 1 | 41774.3736 | 41785.7917 | 1 | 41786.3333 | 41800.3736 | 1 | 41800.3736 | 41820.6417 | 1 | 41820.6417 | 41850.6153 | 1 | 41850.6153 | 41850.6153 | 1 | 41848.4903 | 42016.6285 | 1 | 41848.4903 | 41862.7917 | 1 | 41863.3333 | 41894.3597 | 1 | 41894.3597 | 41943.7014 | 1 | 41943.7014 | 42016.6285 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5431 | 1 | 41753.375 | 41757.3417 | 1 | 41757.3417 | 41760.6201 | 1 | 41760.6201 | 41768.3882 | 1 | 41768.3882 | 41779.5431 | 1 | 41774.6382 | 41851.5882 | 1 | 41774.6382 | 41785.7917 | 1 | 41786.3333 | 41799.6083 | 1 | 41799.6083 | 41822.4903 | 1 | 41822.4903 | 41851.5882 | 1 | 41851.5882 | 41851.5882 | 1 | 41844.4368 | 42003.6917 | 1 | 41844.4368 | 41862.7917 | 1 | 41863.3333 | 41891.6486 | 1 | 41891.6486 | 41939.4236 | 1 | 41939.4236 | 42003.6917 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3819 | 1 | 41753.375 | 41757.3951 | 1 | 41757.3951 | 41761.5799 | 1 | 41761.5799 | 41768.5833 | 1 | 41768.5833 | 41780.3819 | 1 | 41775.3799 | 41852.4903 | 1 | 41775.3799 | 41785.7917 | 1 | 41786.3333 | 41800.4535 | 1 | 41800.4535 | 41823.4965 | 1 | 41823.4965 | 41852.4903 | 1 | 41852.4903 | 41852.4903 | 1 | 41843.5951 | 42011.3701 | 1 | 41843.5951 | 41862.7917 | 1 | 41863.3333 | 41899.3535 | 1 | 41899.3535 | 41947.3597 | 1 | 41947.3597 | 42011.3701 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6167 | 1 | 41753.375 | 41757.3785 | 1 | 41757.3785 | 41761.4618 | 1 | 41761.4618 | 41768.4347 | 1 | 41768.4347 | 41779.6167 | 1 | 41773.6549 | 41845.4333 | 1 | 41773.6549 | 41785.7917 | 1 | 41786.3333 | 41799.6014 | 1 | 41799.6014 | 41820.5514 | 1 | 41820.5514 | 41845.4333 | 1 | 41845.4333 | 41845.4333 | 1 | 41848.3667 | 41998.4264 | 1 | 41848.3667 | 41862.7917 | 1 | 41863.3333 | 41897.6715 | 1 | 41897.6715 | 41941.6514 | 1 | 41941.6514 | 41998.4264 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5833 | 1 | 41753.375 | 41757.4014 | 1 | 41757.4014 | 41761.3951 | 1 | 41761.3951 | 41767.7069 | 1 | 41767.7069 | 41779.5833 | 1 | 41774.6181 | 41849.6382 | 1 | 41774.6181 | 41785.7917 | 1 | 41786.3333 | 41799.5785 | 1 | 41799.5785 | 41820.4833 | 1 | 41820.4833 | 41849.6382 | 1 | 41849.6382 | 41849.6382 | 1 | 41848.4368 | 41992.4764 | 1 | 41848.4368 | 41862.7917 | 1 | 41863.3333 | 41893.3701 | 1 | 41893.3701 | 41935.4403 | 1 | 41935.4403 | 41992.4764 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.5903 | 1 | 41753.375 | 41757.3986 | 1 | 41757.3986 | 41760.7 | 1 | 41760.7 | 41767.6431 | 1 | 41767.6431 | 41778.5903 | 1 | 41774.6014 | 41850.3569 | 1 | 41774.6014 | 41785.7917 | 1 | 41786.3333 | 41800.6653 | 1 | 41800.6653 | 41822.6917 | 1 | 41822.6917 | 41850.3569 | 1 | 41850.3569 | 41850.3569 | 1 | 41848.6819 | 41997.4167 | 1 | 41848.6819 | 41862.7917 | 1 | 41863.3333 | 41898.4465 | 1 | 41898.4465 | 41940.7014 | 1 | 41940.7014 | 41997.4167 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5799 | 1 | 41753.375 | 41757.4785 | 1 | 41757.4785 | 41761.5764 | 1 | 41761.5764 | 41768.5431 | 1 | 41768.5431 | 41779.5799 | 1 | 41775.5486 | 41849.5681 | 1 | 41775.5486 | 41785.7917 | 1 | 41786.3333 | 41800.6181 | 1 | 41800.6181 | 41821.5549 | 1 | 41821.5549 | 41849.5681 | 1 | 41849.5681 | 41849.5681 | 1 | 41848.3333 | 42012.3597 | 1 | 41848.3333 | 41862.7917 | 1 | 41863.3333 | 41891.5715 | 1 | 41891.5715 | 41940.4465 | 1 | 41940.4465 | 42012.3597 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.55 | 1 | 41753.375 | 41757.4583 | 1 | 41757.4583 | 41761.4014 | 1 | 41761.4014 | 41768.3618 | 1 | 41768.3618 | 41779.55 | 1 | 41774.6451 | 41849.7083 | 1 | 41774.6451 | 41785.7917 | 1 | 41786.3333 | 41800.3764 | 1 | 41800.3764 | 41821.5618 | 1 | 41821.5618 | 41849.7083 | 1 | 41849.7083 | 41849.7083 | 1 | 41843.5583 | 42016.575 | 1 | 41843.5583 | 41862.7917 | 1 | 41863.3333 | 41892.3965 | 1 | 41892.3965 | 41941.5486 | 1 | 41941.5486 | 42016.575 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6736 | 1 | 41753.375 | 41757.3882 | 1 | 41757.3882 | 41761.4549 | 1 | 41761.4549 | 41768.4153 | 1 | 41768.4153 | 41778.6736 | 1 | 41774.3965 | 41849.4 | 1 | 41774.3965 | 41785.7917 | 1 | 41786.3333 | 41800.4736 | 1 | 41800.4736 | 41822.6819 | 1 | 41822.6819 | 41849.4 | 1 | 41849.4 | 41849.4 | 1 | 41845.4132 | 42018.3903 | 1 | 41845.4132 | 41862.7917 | 1 | 41863.3333 | 41897.3931 | 1 | 41897.3931 | 41950.5583 | 1 | 41950.5583 | 42018.3903 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3347 | 1 | 41753.375 | 41757.3514 | 1 | 41757.3514 | 41760.6931 | 1 | 41760.6931 | 41767.6833 | 1 | 41767.6833 | 41780.3347 | 1 | 41774.5549 | 41851.7083 | 1 | 41774.5549 | 41785.7917 | 1 | 41786.3333 | 41801.3403 | 1 | 41801.3403 | 41822.4 | 1 | 41822.4 | 41851.7083 | 1 | 41851.7083 | 41851.7083 | 1 | 41848.7049 | 42009.6451 | 1 | 41848.7049 | 41862.7917 | 1 | 41863.3333 | 41891.4868 | 1 | 41891.4868 | 41939.3736 | 1 | 41939.3736 | 42009.6451 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4486 | 1 | 41753.375 | 41757.3785 | 1 | 41757.3785 | 41760.6701 | 1 | 41760.6701 | 41768.6264 | 1 | 41768.6264 | 41780.4486 | 1 | 41774.6215 | 41852.6819 | 1 | 41774.6215 | 41785.7917 | 1 | 41786.3333 | 41800.5514 | 1 | 41800.5514 | 41821.6083 | 1 | 41821.6083 | 41852.6819 | 1 | 41852.6819 | 41852.6819 | 1 | 41844.3903 | 41999.5583 | 1 | 41844.3903 | 41862.7917 | 1 | 41863.3333 | 41893.4403 | 1 | 41893.4403 | 41936.3931 | 1 | 41936.3931 | 41999.5583 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6931 | 1 | 41753.375 | 41757.4083 | 1 | 41757.4083 | 41761.4583 | 1 | 41761.4583 | 41768.5465 | 1 | 41768.5465 | 41779.6931 | 1 | 41775.3333 | 41849.5785 | 1 | 41775.3333 | 41785.7917 | 1 | 41786.3333 | 41800.3799 | 1 | 41800.3799 | 41820.5986 | 1 | 41820.5986 | 41849.5785 | 1 | 41849.5785 | 41849.5785 | 1 | 41843.675 | 42005.6049 | 1 | 41843.675 | 41862.7917 | 1 | 41863.3333 | 41892.6083 | 1 | 41892.6083 | 41943.3431 | 1 | 41943.3431 | 42005.6049 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4951 | 1 | 41753.375 | 41757.3486 | 1 | 41757.3486 | 41761.4486 | 1 | 41761.4486 | 41768.6431 | 1 | 41768.6431 | 41780.4951 | 1 | 41774.5715 | 41848.6882 | 1 | 41774.5715 | 41785.7917 | 1 | 41786.3333 | 41800.3701 | 1 | 41800.3701 | 41821.4368 | 1 | 41821.4368 | 41848.6882 | 1 | 41848.6882 | 41848.6882 | 1 | 41843.4736 | 41997.5681 | 1 | 41843.4736 | 41862.7917 | 1 | 41863.3333 | 41892.6417 | 1 | 41892.6417 | 41935.4201 | 1 | 41935.4201 | 41997.5681 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6236 | 1 | 41753.375 | 41757.3583 | 1 | 41757.3583 | 41761.3917 | 1 | 41761.3917 | 41768.5465 | 1 | 41768.5465 | 41779.6236 | 1 | 41773.7049 | 41850.6681 | 1 | 41773.7049 | 41785.7917 | 1 | 41786.3333 | 41800.3403 | 1 | 41800.3403 | 41822.6083 | 1 | 41822.6083 | 41850.6681 | 1 | 41850.6681 | 41850.6681 | 1 | 41845.6347 | 42009.6785 | 1 | 41845.6347 | 41862.7917 | 1 | 41863.3333 | 41897.3632 | 1 | 41897.3632 | 41950.3569 | 1 | 41950.3569 | 42009.6785 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3486 | 1 | 41753.375 | 41757.4715 | 1 | 41757.4715 | 41761.4819 | 1 | 41761.4819 | 41768.5799 | 1 | 41768.5799 | 41780.3486 | 1 | 41774.4833 | 41845.6681 | 1 | 41774.4833 | 41785.7917 | 1 | 41786.3333 | 41799.6417 | 1 | 41799.6417 | 41820.3868 | 1 | 41820.3868 | 41845.6681 | 1 | 41845.6681 | 41845.6681 | 1 | 41848.4833 | 42009.5847 | 1 | 41848.4833 | 41862.7917 | 1 | 41863.3333 | 41899.3965 | 1 | 41899.3965 | 41950.5 | 1 | 41950.5417 | 42009.5847 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6931 | 1 | 41753.375 | 41757.4785 | 1 | 41757.4785 | 41761.375 | 1 | 41761.375 | 41768.3951 | 1 | 41768.3951 | 41779.6931 | 1 | 41774.675 | 41849.4236 | 1 | 41774.675 | 41785.7917 | 1 | 41786.3333 | 41800.675 | 1 | 41800.675 | 41821.5486 | 1 | 41821.5486 | 41849.4236 | 1 | 41849.4236 | 41849.4236 | 1 | 41845.4465 | 42004.4965 | 1 | 41845.4465 | 41862.7917 | 1 | 41863.3333 | 41893.4097 | 1 | 41893.4097 | 41943.4167 | 1 | 41943.4167 | 42004.4965 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.55 | 1 | 41753.375 | 41757.3486 | 1 | 41757.3486 | 41761.3785 | 1 | 41761.3785 | 41768.4583 | 1 | 41768.4583 | 41779.55 | 1 | 41774.6618 | 41848.5882 | 1 | 41774.6618 | 41785.7917 | 1 | 41786.3333 | 41801.3465 | 1 | 41801.3465 | 41821.4 | 1 | 41821.4 | 41848.5882 | 1 | 41848.5882 | 41848.5882 | 1 | 41848.4667 | 42005.5715 | 1 | 41848.4667 | 41862.7917 | 1 | 41863.3333 | 41890.7083 | 1 | 41891.3333 | 41939.6583 | 1 | 41939.6583 | 42005.5715 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5465 | 1 | 41753.375 | 41757.4382 | 1 | 41757.4382 | 41761.5465 | 1 | 41761.5465 | 41768.6132 | 1 | 41768.6132 | 41779.5465 | 1 | 41773.6917 | 41851.3535 | 1 | 41773.6917 | 41785.7917 | 1 | 41786.3333 | 41799.7014 | 1 | 41799.7014 | 41821.3535 | 1 | 41821.3535 | 41851.3535 | 1 | 41851.3535 | 41851.3535 | 1 | 41845.675 | 41997.6819 | 1 | 41845.675 | 41862.7917 | 1 | 41863.3333 | 41894.4403 | 1 | 41894.4403 | 41939.4201 | 1 | 41939.4201 | 41997.6819 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.425 | 1 | 41753.375 | 41757.3847 | 1 | 41757.3847 | 41761.3514 | 1 | 41761.3514 | 41768.6333 | 1 | 41768.6333 | 41780.425 | 1 | 41774.4264 | 41849.3799 | 1 | 41774.4264 | 41785.7917 | 1 | 41786.3333 | 41800.6653 | 1 | 41800.6653 | 41822.5486 | 1 | 41822.5486 | 41849.3799 | 1 | 41849.3799 | 41849.3799 | 1 | 41843.5819 | 42016.6785 | 1 | 41843.5819 | 41862.7917 | 1 | 41863.3333 | 41898.6819 | 1 | 41898.6819 | 41953.4097 | 1 | 41953.4097 | 42016.6785 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5931 | 1 | 41753.375 | 41757.4319 | 1 | 41757.4319 | 41761.6035 | 1 | 41761.6035 | 41768.5667 | 1 | 41768.5667 | 41779.5931 | 1 | 41775.4431 | 41851.4632 | 1 | 41775.4431 | 41785.7917 | 1 | 41786.3333 | 41800.6917 | 1 | 41800.6917 | 41822.4035 | 1 | 41822.4035 | 41851.4632 | 1 | 41851.4632 | 41851.4632 | 1 | 41845.3632 | 41997.7083 | 1 | 41845.3632 | 41862.7917 | 1 | 41863.3333 | 41892.7014 | 1 | 41892.7014 | 41940.5819 | 1 | 41940.5819 | 41997.7083 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3785 | 1 | 41753.375 | 41757.4583 | 1 | 41757.4583 | 41761.6569 | 1 | 41761.6569 | 41771.4382 | 1 | 41771.4382 | 41780.3785 | 1 | 41774.6215 | 41849.6514 | 1 | 41774.6215 | 41785.7917 | 1 | 41786.3333 | 41799.6486 | 1 | 41799.6486 | 41822.4236 | 1 | 41822.4236 | 41849.6514 | 1 | 41849.6514 | 41849.6514 | 1 | 41848.3736 | 42002.6917 | 1 | 41848.3736 | 41862.7917 | 1 | 41863.3333 | 41891.5847 | 1 | 41891.5847 | 41936.6917 | 1 | 41936.6917 | 42002.6917 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6868 | 1 | 41753.375 | 41757.3986 | 1 | 41757.3986 | 41761.4049 | 1 | 41761.4049 | 41768.475 | 1 | 41768.475 | 41779.6868 | 1 | 41774.6653 | 41850.3833 | 1 | 41774.6653 | 41785.7917 | 1 | 41786.3333 | 41800.3868 | 1 | 41800.3868 | 41821.4264 | 1 | 41821.4264 | 41850.3833 | 1 | 41850.3833 | 41850.3833 | 1 | 41845.35 | 42004.4264 | 1 | 41845.35 | 41862.7917 | 1 | 41863.3333 | 41893.5917 | 1 | 41893.5917 | 41943.3833 | 1 | 41943.3833 | 42004.4264 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.7069 | 1 | 41753.375 | 41757.3882 | 1 | 41757.3882 | 41761.3785 | 1 | 41761.3785 | 41767.7 | 1 | 41767.7 | 41778.7069 | 1 | 41775.4632 | 41850.4236 | 1 | 41775.4632 | 41785.7917 | 1 | 41786.3333 | 41800.6847 | 1 | 41800.6847 | 41823.5451 | 1 | 41823.5451 | 41850.4236 | 1 | 41850.4236 | 41850.4236 | 1 | 41844.3764 | 42003.4299 | 1 | 41844.3764 | 41862.7917 | 1 | 41863.3333 | 41892.4299 | 1 | 41892.4299 | 41941.4833 | 1 | 41941.4833 | 42003.4299 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3583 | 1 | 41753.375 | 41757.4319 | 1 | 41757.4319 | 41761.5736 | 1 | 41761.5736 | 41768.55 | 1 | 41768.55 | 41780.3583 | 1 | 41774.6347 | 41848.6715 | 1 | 41774.6347 | 41785.7917 | 1 | 41786.3333 | 41799.6882 | 1 | 41799.6882 | 41820.575 | 1 | 41820.575 | 41848.6715 | 1 | 41848.6715 | 41848.6715 | 1 | 41848.5715 | 42012.4368 | 1 | 41848.5715 | 41862.7917 | 1 | 41863.3333 | 41900.4403 | 1 | 41900.4403 | 41947.5986 | 1 | 41947.5986 | 42012.4368 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6465 | 1 | 41753.375 | 41757.4083 | 1 | 41757.4083 | 41761.4583 | 1 | 41761.4583 | 41768.4917 | 1 | 41768.4917 | 41779.6465 | 1 | 41774.4465 | 41848.7049 | 1 | 41774.4465 | 41785.7917 | 1 | 41786.3333 | 41799.6285 | 1 | 41799.6285 | 41821.6014 | 1 | 41821.6014 | 41848.7049 | 1 | 41848.7049 | 41848.7049 | 1 | 41843.6618 | 42011.3569 | 1 | 41843.6618 | 41862.7917 | 1 | 41863.3333 | 41893.5583 | 1 | 41893.5583 | 41940.35 | 1 | 41940.35 | 42011.3569 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4049 | 1 | 41753.375 | 41754.6868 | 1 | 41754.6868 | 41760.65 | 1 | 41760.65 | 41768.5764 | 1 | 41768.5764 | 41780.4049 | 1 | 41774.6917 | 41849.5549 | 1 | 41774.6917 | 41785.7917 | 1 | 41786.3333 | 41799.6118 | 1 | 41799.6118 | 41820.4965 | 1 | 41820.4965 | 41849.5549 | 1 | 41849.5549 | 41849.5549 | 1 | 41848.4799 | 42025.6417 | 1 | 41848.4799 | 41862.7917 | 1 | 41863.3333 | 41892.6514 | 1 | 41892.6514 | 41954.3736 | 1 | 41954.3736 | 42025.6417 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4583 | 1 | 41753.375 | 41757.4486 | 1 | 41757.4486 | 41761.4951 | 1 | 41761.4951 | 41768.6701 | 1 | 41768.6701 | 41780.4583 | 1 | 41774.4097 | 41848.6319 | 1 | 41774.4097 | 41785.7917 | 1 | 41786.3333 | 41799.5583 | 1 | 41799.5583 | 41820.5583 | 1 | 41820.5583 | 41848.6319 | 1 | 41848.6319 | 41848.6319 | 1 | 41848.4799 | 42006.575 | 1 | 41848.4799 | 41862.7917 | 1 | 41863.3333 | 41899.4201 | 1 | 41899.4201 | 41946.5514 | 1 | 41946.5514 | 42006.575 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5701 | 1 | 41753.375 | 41757.3618 | 1 | 41757.3618 | 41761.4549 | 1 | 41761.4549 | 41768.6132 | 1 | 41768.6132 | 41779.5701 | 1 | 41775.4701 | 41851.6382 | 1 | 41775.4701 | 41785.7917 | 1 | 41786.3333 | 41800.3667 | 1 | 41800.3667 | 41822.4632 | 1 | 41822.4632 | 41851.6382 | 1 | 41851.6382 | 41851.6382 | 1 | 41848.6653 | 42020.4431 | 1 | 41848.6653 | 41862.7917 | 1 | 41863.3333 | 41899.3799 | 1 | 41899.3799 | 41957.6049 | 1 | 41957.6049 | 42020.4431 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5799 | 1 | 41753.375 | 41757.4181 | 1 | 41757.4181 | 41761.4618 | 1 | 41761.4618 | 41768.4347 | 1 | 41768.4347 | 41779.5799 | 1 | 41775.4701 | 41850.5917 | 1 | 41775.4701 | 41785.7917 | 1 | 41786.3333 | 41799.6549 | 1 | 41799.6549 | 41820.625 | 1 | 41820.625 | 41850.5917 | 1 | 41850.5917 | 41850.5917 | 1 | 41848.6847 | 42002.6083 | 1 | 41848.6847 | 41862.7917 | 1 | 41863.3333 | 41899.3632 | 1 | 41899.3632 | 41946.5986 | 1 | 41946.5986 | 42002.6083 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5535 | 1 | 41753.375 | 41757.3986 | 1 | 41757.3986 | 41761.4417 | 1 | 41761.4417 | 41768.5632 | 1 | 41768.5632 | 41779.5535 | 1 | 41773.5951 | 41845.7014 | 1 | 41773.5951 | 41785.7917 | 1 | 41786.3333 | 41800.3368 | 1 | 41800.3368 | 41821.4667 | 1 | 41821.4667 | 41845.7014 | 1 | 41845.7014 | 41845.7014 | 1 | 41845.4903 | 42013.3632 | 1 | 41845.4903 | 41862.7917 | 1 | 41863.3333 | 41891.5583 | 1 | 41891.5583 | 41948.4 | 1 | 41948.4 | 42013.3632 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3347 | 1 | 41753.375 | 41757.4618 | 1 | 41757.4618 | 41761.5431 | 1 | 41761.5431 | 41768.4014 | 1 | 41768.4014 | 41780.3347 | 1 | 41775.3833 | 41849.6785 | 1 | 41775.3833 | 41785.7917 | 1 | 41786.3333 | 41800.7049 | 1 | 41800.7049 | 41822.4465 | 1 | 41822.4465 | 41849.6785 | 1 | 41849.6785 | 41849.6785 | 1 | 41848.4201 | 42016.6014 | 1 | 41848.4201 | 41862.7917 | 1 | 41863.3333 | 41892.4799 | 1 | 41892.4799 | 41946.4931 | 1 | 41946.4931 | 42016.6014 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.7035 | 1 | 41753.375 | 41757.4715 | 1 | 41757.4715 | 41761.4014 | 1 | 41761.4014 | 41768.4417 | 1 | 41768.4417 | 41779.7035 | 1 | 41774.4403 | 41845.4965 | 1 | 41774.4403 | 41785.7917 | 1 | 41786.3333 | 41799.4368 | 1 | 41799.4368 | 41817.5715 | 1 | 41817.5715 | 41845.4965 | 1 | 41845.4965 | 41845.4965 | 1 | 41845.7014 | 42002.7049 | 1 | 41845.7014 | 41862.7917 | 1 | 41863.3333 | 41891.5618 | 1 | 41891.5618 | 41935.4903 | 1 | 41935.4903 | 42002.7049 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4451 | 1 | 41753.375 | 41757.3986 | 1 | 41757.3986 | 41761.3847 | 1 | 41761.3847 | 41768.4847 | 1 | 41768.4847 | 41780.4451 | 1 | 41774.5681 | 41851.4465 | 1 | 41774.5681 | 41785.7917 | 1 | 41786.3333 | 41800.4431 | 1 | 41800.4431 | 41821.6986 | 1 | 41821.6986 | 41851.4465 | 1 | 41851.4465 | 41851.4465 | 1 | 41848.4569 | 42004.5917 | 1 | 41848.4569 | 41862.7917 | 1 | 41863.3333 | 41898.6549 | 1 | 41898.6549 | 41946.4236 | 1 | 41946.4236 | 42004.5917 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4583 | 1 | 41753.375 | 41757.3819 | 1 | 41757.3819 | 41761.3549 | 1 | 41761.3549 | 41767.6569 | 1 | 41767.6569 | 41779.4583 | 1 | 41774.5451 | 41852.6917 | 1 | 41774.5451 | 41785.7917 | 1 | 41786.3333 | 41800.4569 | 1 | 41800.4569 | 41822.6049 | 1 | 41822.6049 | 41852.6917 | 1 | 41852.6917 | 41852.6917 | 1 | 41845.5882 | 42009.5847 | 1 | 41845.5882 | 41862.7917 | 1 | 41863.3333 | 41897.3465 | 1 | 41897.3465 | 41950.4299 | 1 | 41950.4299 | 42009.5847 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5431 | 1 | 41753.375 | 41757.3653 | 1 | 41757.3653 | 41761.3514 | 1 | 41761.3514 | 41768.4153 | 1 | 41768.4153 | 41779.5431 | 1 | 41773.7014 | 41848.3368 | 1 | 41773.7014 | 41785.7917 | 1 | 41786.3333 | 41799.6215 | 1 | 41799.6215 | 41820.6417 | 1 | 41820.6417 | 41848.3368 | 1 | 41848.3368 | 41848.3368 | 1 | 41845.5847 | 42025.5618 | 1 | 41845.5847 | 41862.7917 | 1 | 41863.3333 | 41892.5486 | 1 | 41892.5486 | 41950.4701 | 1 | 41950.4701 | 42025.5618 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6201 | 1 | 41753.375 | 41757.3819 | 1 | 41757.3819 | 41761.3819 | 1 | 41761.3819 | 41768.3583 | 1 | 41768.3583 | 41778.6201 | 1 | 41774.3931 | 41850.6347 | 1 | 41774.3931 | 41785.7917 | 1 | 41786.3333 | 41799.6549 | 1 | 41799.6549 | 41821.6382 | 1 | 41821.6382 | 41850.6347 | 1 | 41850.6347 | 41850.6347 | 1 | 41844.4868 | 42006.6486 | 1 | 41844.4868 | 41862.7917 | 1 | 41863.3333 | 41891.6583 | 1 | 41891.6583 | 41935.7014 | 1 | 41935.7014 | 42006.6486 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3549 | 1 | 41753.375 | 41757.3986 | 1 | 41757.3986 | 41761.3715 | 1 | 41761.3715 | 41768.3681 | 1 | 41768.3681 | 41780.3549 | 1 | 41775.5917 | 41851.6181 | 1 | 41775.5917 | 41785.7917 | 1 | 41786.3333 | 41801.4299 | 1 | 41801.4299 | 41822.6083 | 1 | 41822.6083 | 41851.6181 | 1 | 41851.6181 | 41851.6181 | 1 | 41848.6014 | 42024.5986 | 1 | 41848.6014 | 41862.7917 | 1 | 41863.3333 | 41899.4299 | 1 | 41899.4299 | 41942.4431 | 1 | 41942.4431 | 42024.5986 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3847 | 1 | 41753.375 | 41757.4417 | 1 | 41757.4417 | 41761.5569 | 1 | 41761.5569 | 41768.65 | 1 | 41768.65 | 41780.3847 | 1 | 41775.5417 | 41851.6681 | 1 | 41775.5417 | 41785.7917 | 1 | 41786.3333 | 41800.575 | 1 | 41800.575 | 41822.4097 | 1 | 41822.4097 | 41851.6681 | 1 | 41851.6681 | 41851.6681 | 1 | 41843.4833 | 42010.4931 | 1 | 41843.4833 | 41862.7917 | 1 | 41863.3333 | 41893.5653 | 1 | 41893.5653 | 41948.3667 | 1 | 41948.3667 | 42010.4931 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3847 | 1 | 41753.375 | 41757.3549 | 1 | 41757.3549 | 41761.3653 | 1 | 41761.3653 | 41768.5965 | 1 | 41768.5965 | 41780.3847 | 1 | 41775.4167 | 41850.4201 | 1 | 41775.4167 | 41785.7917 | 1 | 41786.3333 | 41800.3965 | 1 | 41800.3965 | 41821.6681 | 1 | 41821.6681 | 41850.4201 | 1 | 41850.4201 | 41850.4201 | 1 | 41848.3465 | 41998.6486 | 1 | 41848.3465 | 41862.7917 | 1 | 41863.3333 | 41893.6549 | 1 | 41893.6549 | 41942.6181 | 1 | 41942.6181 | 41998.6486 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5868 | 1 | 41753.375 | 41757.3986 | 1 | 41757.3986 | 41761.425 | 1 | 41761.425 | 41768.4382 | 1 | 41768.4382 | 41779.5868 | 1 | 41774.5785 | 41848.6583 | 1 | 41774.5785 | 41785.7917 | 1 | 41786.3333 | 41799.5715 | 1 | 41799.5715 | 41820.4736 | 1 | 41820.4736 | 41848.6583 | 1 | 41848.6583 | 41848.6583 | 1 | 41844.4965 | 42005.7014 | 1 | 41844.4965 | 41862.7917 | 1 | 41863.3333 | 41892.3764 | 1 | 41892.3764 | 41948.4236 | 1 | 41948.4236 | 42005.7014 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4083 | 1 | 41753.375 | 41757.3819 | 1 | 41757.3819 | 41761.3549 | 1 | 41761.3549 | 41768.5632 | 1 | 41768.5632 | 41779.4083 | 1 | 41774.4535 | 41850.6451 | 1 | 41774.4535 | 41785.7917 | 1 | 41786.3333 | 41800.4403 | 1 | 41800.4403 | 41821.4931 | 1 | 41821.4931 | 41850.6451 | 1 | 41850.6451 | 41850.6451 | 1 | 41844.6653 | 42018.3403 | 1 | 41844.6653 | 41862.7917 | 1 | 41863.3333 | 41899.4736 | 1 | 41899.4736 | 41961.6715 | 1 | 41961.6715 | 42018.3403 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.4951 | 1 | 41753.375 | 41757.3514 | 1 | 41757.3514 | 41760.6201 | 1 | 41760.6201 | 41767.4549 | 1 | 41767.4549 | 41778.4951 | 1 | 41775.4632 | 41852.3701 | 1 | 41775.4632 | 41785.7917 | 1 | 41786.3333 | 41800.7083 | 1 | 41801.3333 | 41822.4535 | 1 | 41822.4535 | 41852.3701 | 1 | 41852.3701 | 41852.3701 | 1 | 41848.3903 | 41992.3535 | 1 | 41848.3903 | 41862.7917 | 1 | 41863.3333 | 41892.3868 | 1 | 41892.3868 | 41934.4597 | 1 | 41934.4597 | 41992.3535 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6097 | 1 | 41753.375 | 41757.4715 | 1 | 41757.4715 | 41761.3819 | 1 | 41761.3819 | 41768.3382 | 1 | 41768.3382 | 41778.6097 | 1 | 41775.3597 | 41851.6181 | 1 | 41775.3597 | 41785.7917 | 1 | 41786.3333 | 41800.4132 | 1 | 41800.4132 | 41822.4868 | 1 | 41822.4868 | 41851.6181 | 1 | 41851.6181 | 41851.6181 | 1 | 41844.6986 | 42011.575 | 1 | 41844.6986 | 41862.7917 | 1 | 41863.3333 | 41892.4167 | 1 | 41892.4167 | 41943.5951 | 1 | 41943.5951 | 42011.575 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4819 | 1 | 41753.375 | 41757.4083 | 1 | 41757.4083 | 41761.4382 | 1 | 41761.4382 | 41768.5764 | 1 | 41768.5764 | 41779.4819 | 1 | 41775.3903 | 41850.6417 | 1 | 41775.3903 | 41785.7917 | 1 | 41786.3333 | 41800.6049 | 1 | 41800.6049 | 41821.5951 | 1 | 41821.5951 | 41850.6417 | 1 | 41850.6417 | 41850.6417 | 1 | 41848.4069 | 42005.4236 | 1 | 41848.4069 | 41862.7917 | 1 | 41863.3333 | 41898.6882 | 1 | 41898.6882 | 41941.3535 | 1 | 41941.3535 | 42005.4236 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3486 | 1 | 41753.375 | 41757.3986 | 1 | 41757.3986 | 41761.3514 | 1 | 41761.3514 | 41767.6833 | 1 | 41767.6833 | 41780.3486 | 1 | 41775.4035 | 41848.4535 | 1 | 41775.4035 | 41785.7917 | 1 | 41786.3333 | 41800.6083 | 1 | 41800.6083 | 41821.3764 | 1 | 41821.3764 | 41848.4535 | 1 | 41848.4535 | 41848.4535 | 1 | 41845.4569 | 42020.3403 | 1 | 41845.4569 | 41862.7917 | 1 | 41863.3333 | 41892.6847 | 1 | 41892.6847 | 41947.45 | 1 | 41947.45 | 42020.3403 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4653 | 1 | 41753.375 | 41757.3785 | 1 | 41757.3785 | 41761.4486 | 1 | 41761.4486 | 41767.7069 | 1 | 41767.7069 | 41779.4653 | 1 | 41774.4903 | 41850.4069 | 1 | 41774.4903 | 41785.7917 | 1 | 41786.3333 | 41799.4167 | 1 | 41799.4167 | 41821.4569 | 1 | 41821.4569 | 41850.4069 | 1 | 41850.4069 | 41850.4069 | 1 | 41845.5917 | 42012.4069 | 1 | 41845.5917 | 41862.7917 | 1 | 41863.3333 | 41892.5 | 1 | 41892.5417 | 41947.5917 | 1 | 41947.5917 | 42012.4069 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6299 | 1 | 41753.375 | 41757.4181 | 1 | 41757.4181 | 41761.4347 | 1 | 41761.4347 | 41767.6903 | 1 | 41767.6903 | 41778.6299 | 1 | 41774.5549 | 41849.7014 | 1 | 41774.5549 | 41785.7917 | 1 | 41786.3333 | 41800.6049 | 1 | 41800.6049 | 41821.4701 | 1 | 41821.4701 | 41849.7014 | 1 | 41849.7014 | 41849.7014 | 1 | 41844.4667 | 42026.3535 | 1 | 41844.4667 | 41862.7917 | 1 | 41863.3333 | 41897.4535 | 1 | 41897.4535 | 41956.3569 | 1 | 41956.3569 | 42026.3535 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6868 | 1 | 41753.375 | 41757.4653 | 1 | 41757.4653 | 41761.4715 | 1 | 41761.4715 | 41768.4319 | 1 | 41768.4319 | 41779.6868 | 1 | 41774.4 | 41850.4667 | 1 | 41774.4 | 41785.7917 | 1 | 41786.3333 | 41800.4535 | 1 | 41800.4535 | 41820.6618 | 1 | 41820.6618 | 41850.4667 | 1 | 41850.4667 | 41850.4667 | 1 | 41844.4903 | 42019.4264 | 1 | 41844.4903 | 41862.7917 | 1 | 41863.3333 | 41900.4201 | 1 | 41900.4201 | 41947.6417 | 1 | 41947.6417 | 42019.4264 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41781.4785 | 1 | 41753.375 | 41757.4049 | 1 | 41757.4049 | 41761.4083 | 1 | 41761.4083 | 41771.3785 | 1 | 41771.3785 | 41781.4785 | 1 | 41774.6486 | 41845.7049 | 1 | 41774.6486 | 41785.7917 | 1 | 41786.3333 | 41800.5951 | 1 | 41800.5951 | 41820.6417 | 1 | 41820.6417 | 41845.7049 | 1 | 41845.7049 | 41845.7049 | 1 | 41845.6181 | 42013.625 | 1 | 41845.6181 | 41862.7917 | 1 | 41863.3333 | 41898.4632 | 1 | 41898.4632 | 41950.6215 | 1 | 41950.6215 | 42013.625 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6035 | 1 | 41753.375 | 41757.3882 | 1 | 41757.3882 | 41761.3715 | 1 | 41761.3715 | 41768.375 | 1 | 41768.375 | 41779.6035 | 1 | 41775.4035 | 41850.6153 | 1 | 41775.4035 | 41785.7917 | 1 | 41786.3333 | 41801.4167 | 1 | 41801.4167 | 41822.4965 | 1 | 41822.4965 | 41850.6153 | 1 | 41850.6153 | 41850.6153 | 1 | 41845.4535 | 42010.3903 | 1 | 41845.4535 | 41862.7917 | 1 | 41863.3333 | 41891.7014 | 1 | 41891.7014 | 41939.4236 | 1 | 41939.4236 | 42010.3903 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.425 | 1 | 41753.375 | 41757.3653 | 1 | 41757.3653 | 41761.5701 | 1 | 41761.5701 | 41768.7035 | 1 | 41768.7035 | 41780.425 | 1 | 41774.6785 | 41850.6215 | 1 | 41774.6785 | 41785.7917 | 1 | 41786.3333 | 41801.3799 | 1 | 41801.3799 | 41821.4132 | 1 | 41821.4132 | 41850.6215 | 1 | 41850.6215 | 41850.6215 | 1 | 41848.4736 | 42003.4368 | 1 | 41848.4736 | 41862.7917 | 1 | 41863.3333 | 41899.4535 | 1 | 41899.4535 | 41946.4799 | 1 | 41946.4799 | 42003.4368 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41781.3382 | 1 | 41753.375 | 41757.375 | 1 | 41757.375 | 41761.4215 | 1 | 41761.4215 | 41768.7 | 1 | 41768.7 | 41781.3382 | 1 | 41774.4535 | 41849.4299 | 1 | 41774.4535 | 41785.7917 | 1 | 41786.3333 | 41801.3903 | 1 | 41801.3903 | 41821.6285 | 1 | 41821.6285 | 41849.4299 | 1 | 41849.4299 | 41849.4299 | 1 | 41845.5618 | 42009.5986 | 1 | 41845.5618 | 41862.7917 | 1 | 41863.3333 | 41893.6785 | 1 | 41893.6785 | 41940.6583 | 1 | 41940.6583 | 42009.5986 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5431 | 1 | 41753.375 | 41757.3618 | 1 | 41757.3618 | 41761.3653 | 1 | 41761.3653 | 41768.4083 | 1 | 41768.4083 | 41779.5431 | 1 | 41775.3736 | 41850.3667 | 1 | 41775.3736 | 41785.7917 | 1 | 41786.3333 | 41800.4833 | 1 | 41800.4833 | 41823.4201 | 1 | 41823.4201 | 41850.3667 | 1 | 41850.3667 | 41850.3667 | 1 | 41845.5486 | 42016.5917 | 1 | 41845.5486 | 41862.7917 | 1 | 41863.3333 | 41891.3799 | 1 | 41891.3799 | 41950.4069 | 1 | 41950.4069 | 42016.5917 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6264 | 1 | 41753.375 | 41757.4451 | 1 | 41757.4451 | 41761.3819 | 1 | 41761.3819 | 41767.6833 | 1 | 41767.6833 | 41778.6264 | 1 | 41775.4097 | 41845.6486 | 1 | 41775.4097 | 41785.7917 | 1 | 41786.3333 | 41799.675 | 1 | 41799.675 | 41821.3931 | 1 | 41821.3931 | 41845.6486 | 1 | 41845.6486 | 41845.6486 | 1 | 41848.5847 | 42005.4931 | 1 | 41848.5847 | 41862.7917 | 1 | 41863.3333 | 41900.4632 | 1 | 41900.4632 | 41948.6917 | 1 | 41948.6917 | 42005.4931 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3951 | 1 | 41753.375 | 41757.375 | 1 | 41757.375 | 41761.4882 | 1 | 41761.4882 | 41768.4882 | 1 | 41768.4882 | 41779.3951 | 1 | 41774.4632 | 41851.4632 | 1 | 41774.4632 | 41785.7917 | 1 | 41786.3333 | 41799.4569 | 1 | 41799.4569 | 41821.4097 | 1 | 41821.4097 | 41851.4632 | 1 | 41851.4632 | 41851.4632 | 1 | 41848.6153 | 42010.6451 | 1 | 41848.6153 | 41862.7917 | 1 | 41863.3333 | 41893.6014 | 1 | 41893.6014 | 41948.4403 | 1 | 41948.4403 | 42010.6451 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6069 | 1 | 41753.375 | 41757.4347 | 1 | 41757.4347 | 41761.4917 | 1 | 41761.4917 | 41768.6035 | 1 | 41768.6035 | 41779.6069 | 1 | 41774.5417 | 41851.6215 | 1 | 41774.5417 | 41785.7917 | 1 | 41786.3333 | 41801.3868 | 1 | 41801.3868 | 41822.4333 | 1 | 41822.4333 | 41851.6215 | 1 | 41851.6215 | 41851.6215 | 1 | 41843.6451 | 42004.5549 | 1 | 41843.6451 | 41862.7917 | 1 | 41863.3333 | 41891.3736 | 1 | 41891.3736 | 41941.6486 | 1 | 41941.6486 | 42004.5549 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6 | 1 | 41753.375 | 41757.4181 | 1 | 41757.4181 | 41761.4486 | 1 | 41761.4486 | 41768.6201 | 1 | 41768.6201 | 41780.6 | 1 | 41774.3403 | 41852.6382 | 1 | 41774.3403 | 41785.7917 | 1 | 41786.3333 | 41801.3736 | 1 | 41801.3736 | 41824.3465 | 1 | 41824.3465 | 41852.6382 | 1 | 41852.6382 | 41852.6382 | 1 | 41845.6951 | 41998.4431 | 1 | 41845.6951 | 41862.7917 | 1 | 41863.3333 | 41892.3799 | 1 | 41892.3799 | 41935.3799 | 1 | 41935.3799 | 41998.4431 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6833 | 1 | 41753.375 | 41757.3951 | 1 | 41757.3951 | 41761.4118 | 1 | 41761.4118 | 41768.3583 | 1 | 41768.3583 | 41778.6833 | 1 | 41774.6486 | 41851.3799 | 1 | 41774.6486 | 41785.7917 | 1 | 41786.3333 | 41800.3632 | 1 | 41800.3632 | 41821.6583 | 1 | 41821.6583 | 41851.3799 | 1 | 41851.3799 | 41851.3799 | 1 | 41843.6715 | 42002.4368 | 1 | 41843.6715 | 41862.7917 | 1 | 41863.3333 | 41894.3368 | 1 | 41894.3368 | 41936.4632 | 1 | 41936.4632 | 42002.4368 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6465 | 1 | 41753.375 | 41757.4118 | 1 | 41757.4118 | 41761.6465 | 1 | 41761.6465 | 41771.3882 | 1 | 41771.3882 | 41779.6465 | 1 | 41774.6319 | 41850.4097 | 1 | 41774.6319 | 41785.7917 | 1 | 41786.3333 | 41799.6785 | 1 | 41799.6785 | 41820.5951 | 1 | 41820.5951 | 41850.4097 | 1 | 41850.4097 | 41850.4097 | 1 | 41845.6153 | 41998.3403 | 1 | 41845.6153 | 41862.7917 | 1 | 41863.3333 | 41892.3569 | 1 | 41892.3569 | 41940.4833 | 1 | 41940.4833 | 41998.3403 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4951 | 1 | 41753.375 | 41757.3583 | 1 | 41757.3583 | 41761.65 | 1 | 41761.65 | 41768.4785 | 1 | 41768.4785 | 41779.4951 | 1 | 41774.7049 | 41849.5681 | 1 | 41774.7049 | 41785.7917 | 1 | 41786.3333 | 41801.5486 | 1 | 41801.5486 | 41822.3667 | 1 | 41822.3667 | 41849.5681 | 1 | 41849.5681 | 41849.5681 | 1 | 41845.3569 | 42003.3736 | 1 | 41845.3569 | 41862.7917 | 1 | 41863.3333 | 41893.6285 | 1 | 41893.6285 | 41942.4167 | 1 | 41942.4167 | 42003.3736 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3882 | 1 | 41753.375 | 41757.4285 | 1 | 41757.4285 | 41761.3882 | 1 | 41761.3882 | 41768.3549 | 1 | 41768.3549 | 41779.3882 | 1 | 41775.3333 | 41850.5882 | 1 | 41775.3333 | 41785.7917 | 1 | 41786.3333 | 41801.6118 | 1 | 41801.6118 | 41822.4167 | 1 | 41822.4167 | 41850.5882 | 1 | 41850.5882 | 41850.5882 | 1 | 41848.5451 | 42017.5847 | 1 | 41848.5451 | 41862.7917 | 1 | 41863.3333 | 41894.6618 | 1 | 41894.6618 | 41946.5951 | 1 | 41946.5951 | 42017.5847 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6069 | 1 | 41753.375 | 41757.3785 | 1 | 41757.3785 | 41761.3653 | 1 | 41761.3653 | 41768.5701 | 1 | 41768.5701 | 41779.6069 | 1 | 41775.3465 | 41851.3965 | 1 | 41775.3465 | 41785.7917 | 1 | 41786.3333 | 41800.6382 | 1 | 41800.6382 | 41821.4201 | 1 | 41821.4201 | 41851.3965 | 1 | 41851.3965 | 41851.3965 | 1 | 41848.6285 | 41998.4799 | 1 | 41848.6285 | 41862.7917 | 1 | 41863.3333 | 41894.4368 | 1 | 41894.4368 | 41939.6986 | 1 | 41939.6986 | 41998.4799 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4181 | 1 | 41753.375 | 41757.4118 | 1 | 41757.4118 | 41761.375 | 1 | 41761.375 | 41768.425 | 1 | 41768.425 | 41779.4181 | 1 | 41774.6153 | 41849.4201 | 1 | 41774.6153 | 41785.7917 | 1 | 41786.3333 | 41800.4465 | 1 | 41800.4465 | 41821.4264 | 1 | 41821.4264 | 41849.4201 | 1 | 41849.4201 | 41849.4201 | 1 | 41848.4569 | 42017.4667 | 1 | 41848.4569 | 41862.7917 | 1 | 41863.3333 | 41898.6618 | 1 | 41898.6618 | 41946.5681 | 1 | 41946.5681 | 42017.4667 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.7 | 1 | 41753.375 | 41757.3653 | 1 | 41757.3653 | 41761.4819 | 1 | 41761.4819 | 41768.6868 | 1 | 41768.6868 | 41779.7 | 1 | 41774.6653 | 41848.675 | 1 | 41774.6653 | 41785.7917 | 1 | 41786.3333 | 41801.4431 | 1 | 41801.4431 | 41821.4632 | 1 | 41821.4632 | 41848.675 | 1 | 41848.675 | 41848.675 | 1 | 41848.5451 | 42018.4736 | 1 | 41848.5451 | 41862.7917 | 1 | 41863.3333 | 41893.4632 | 1 | 41893.4632 | 41955.3931 | 1 | 41955.3931 | 42018.4736 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3382 | 1 | 41753.375 | 41757.3618 | 1 | 41757.3618 | 41761.6035 | 1 | 41761.6035 | 41768.5431 | 1 | 41768.5431 | 41780.3382 | 1 | 41774.6215 | 41848.4465 | 1 | 41774.6215 | 41785.7917 | 1 | 41786.3333 | 41800.6285 | 1 | 41800.6285 | 41821.6083 | 1 | 41821.6083 | 41848.4465 | 1 | 41848.4465 | 41848.4465 | 1 | 41848.675 | 42017.6083 | 1 | 41848.675 | 41862.7917 | 1 | 41863.3333 | 41900.7049 | 1 | 41900.7049 | 41956.675 | 1 | 41956.675 | 42017.6083 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6167 | 1 | 41753.375 | 41757.3549 | 1 | 41757.3549 | 41761.4917 | 1 | 41761.4917 | 41768.6736 | 1 | 41768.6736 | 41780.6167 | 1 | 41775.3903 | 41855.7049 | 1 | 41775.3903 | 41785.7917 | 1 | 41786.3333 | 41801.4 | 1 | 41801.4 | 41822.4535 | 1 | 41822.4535 | 41855.7049 | 1 | 41855.7049 | 41855.7049 | 1 | 41844.4701 | 42011.4764 | 1 | 41844.4701 | 41862.7917 | 1 | 41863.3333 | 41897.4632 | 1 | 41897.4632 | 41943.6181 | 1 | 41943.6181 | 42011.4764 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5632 | 1 | 41753.375 | 41757.3986 | 1 | 41757.3986 | 41761.4382 | 1 | 41761.4382 | 41768.4819 | 1 | 41768.4819 | 41779.5632 | 1 | 41775.4701 | 41849.3965 | 1 | 41775.4701 | 41785.7917 | 1 | 41786.3333 | 41800.4667 | 1 | 41800.4667 | 41822.4299 | 1 | 41822.4299 | 41849.3965 | 1 | 41849.3965 | 41849.3965 | 1 | 41843.6285 | 42005.3799 | 1 | 41843.6285 | 41862.7917 | 1 | 41863.3333 | 41893.7049 | 1 | 41893.7049 | 41943.4132 | 1 | 41943.4132 | 42005.3799 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4819 | 1 | 41753.375 | 41757.4681 | 1 | 41757.4681 | 41761.4882 | 1 | 41761.4882 | 41768.4819 | 1 | 41768.4819 | 41779.4819 | 1 | 41774.6382 | 41849.6819 | 1 | 41774.6382 | 41785.7917 | 1 | 41786.3333 | 41799.6618 | 1 | 41799.6618 | 41820.675 | 1 | 41820.675 | 41849.6819 | 1 | 41849.6819 | 41849.6819 | 1 | 41843.4667 | 42020.5819 | 1 | 41843.4667 | 41862.7917 | 1 | 41863.3333 | 41898.3701 | 1 | 41898.3701 | 41943.4035 | 1 | 41943.4035 | 42020.5819 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6132 | 1 | 41753.375 | 41757.3451 | 1 | 41757.3451 | 41760.6903 | 1 | 41760.6903 | 41768.375 | 1 | 41768.375 | 41779.6132 | 1 | 41774.5514 | 41848.6014 | 1 | 41774.5514 | 41785.7917 | 1 | 41786.3333 | 41799.6549 | 1 | 41799.6549 | 41820.4035 | 1 | 41820.4035 | 41848.6014 | 1 | 41848.6014 | 41848.6014 | 1 | 41844.4236 | 41991.6451 | 1 | 41844.4236 | 41862.7917 | 1 | 41863.3333 | 41891.3965 | 1 | 41891.3965 | 41934.6285 | 1 | 41934.6285 | 41991.6451 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3986 | 1 | 41753.375 | 41757.3486 | 1 | 41757.3486 | 41761.475 | 1 | 41761.475 | 41768.3951 | 1 | 41768.3951 | 41779.3986 | 1 | 41774.3833 | 41849.5 | 1 | 41774.3833 | 41785.7917 | 1 | 41786.3333 | 41800.6549 | 1 | 41800.6549 | 41821.6785 | 1 | 41821.6785 | 41849.5 | 1 | 41849.5 | 41849.5 | 1 | 41845.6083 | 42016.5681 | 1 | 41845.6083 | 41862.7917 | 1 | 41863.3333 | 41893.6882 | 1 | 41893.6882 | 41942.7083 | 1 | 41943.3333 | 42016.5681 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.5965 | 1 | 41753.375 | 41757.3382 | 1 | 41757.3382 | 41761.5569 | 1 | 41761.5569 | 41768.4118 | 1 | 41768.4118 | 41778.5965 | 1 | 41774.6181 | 41849.3667 | 1 | 41774.6181 | 41785.7917 | 1 | 41786.3333 | 41799.575 | 1 | 41799.575 | 41821.675 | 1 | 41821.675 | 41849.3667 | 1 | 41849.3667 | 41849.3667 | 1 | 41844.625 | 42005.6882 | 1 | 41844.625 | 41862.7917 | 1 | 41863.3333 | 41894.4701 | 1 | 41894.4701 | 41947.5785 | 1 | 41947.5785 | 42005.6882 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4285 | 1 | 41753.375 | 41757.3882 | 1 | 41757.3882 | 41761.6597 | 1 | 41761.6597 | 41768.5931 | 1 | 41768.5931 | 41780.4285 | 1 | 41774.6653 | 41845.575 | 1 | 41774.6653 | 41785.7917 | 1 | 41786.3333 | 41800.4069 | 1 | 41800.4069 | 41820.5451 | 1 | 41820.5451 | 41845.575 | 1 | 41845.575 | 41845.575 | 1 | 41848.3597 | 42006.7014 | 1 | 41848.3597 | 41862.7917 | 1 | 41863.3333 | 41893.6451 | 1 | 41893.6451 | 41943.4597 | 1 | 41943.4597 | 42006.7014 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5701 | 1 | 41753.375 | 41757.3653 | 1 | 41757.3653 | 41761.3715 | 1 | 41761.3715 | 41768.4285 | 1 | 41768.4285 | 41779.5701 | 1 | 41773.6847 | 41849.6715 | 1 | 41773.6847 | 41785.7917 | 1 | 41786.3333 | 41799.6451 | 1 | 41799.6451 | 41822.6486 | 1 | 41822.6486 | 41849.6715 | 1 | 41849.6715 | 41849.6715 | 1 | 41844.4799 | 42013.6986 | 1 | 41844.4799 | 41862.7917 | 1 | 41863.3333 | 41892.6285 | 1 | 41892.6285 | 41942.4833 | 1 | 41942.4833 | 42013.6986 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.65 | 1 | 41753.375 | 41757.3951 | 1 | 41757.3951 | 41761.3785 | 1 | 41761.3785 | 41768.6069 | 1 | 41768.6069 | 41780.65 | 1 | 41774.6181 | 41845.6347 | 1 | 41774.6181 | 41785.7917 | 1 | 41786.3333 | 41799.4132 | 1 | 41799.4132 | 41820.3368 | 1 | 41820.3368 | 41845.6347 | 1 | 41845.6347 | 41845.6347 | 1 | 41848.4132 | 42009.4535 | 1 | 41848.4132 | 41862.7917 | 1 | 41863.3333 | 41897.4965 | 1 | 41897.4965 | 41943.6215 | 1 | 41943.6215 | 42009.4535 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6 | 1 | 41753.375 | 41757.3882 | 1 | 41757.3882 | 41761.4951 | 1 | 41761.4951 | 41768.6236 | 1 | 41768.6236 | 41779.6 | 1 | 41775.3833 | 41849.4535 | 1 | 41775.3833 | 41785.7917 | 1 | 41786.3333 | 41800.4035 | 1 | 41800.4035 | 41821.5549 | 1 | 41821.5549 | 41849.4535 | 1 | 41849.4535 | 41849.4535 | 1 | 41848.5583 | 42026.3368 | 1 | 41848.5583 | 41862.7917 | 1 | 41863.3333 | 41904.3597 | 1 | 41904.3597 | 41956.5653 | 1 | 41956.5653 | 42026.3368 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6132 | 1 | 41753.375 | 41757.3681 | 1 | 41757.3681 | 41761.4549 | 1 | 41761.4549 | 41768.6069 | 1 | 41768.6069 | 41779.6132 | 1 | 41774.6014 | 41852.4097 | 1 | 41774.6014 | 41785.7917 | 1 | 41786.3333 | 41800.3965 | 1 | 41800.3965 | 41821.3569 | 1 | 41821.3569 | 41852.4097 | 1 | 41852.4097 | 41852.4097 | 1 | 41845.3535 | 42013.5917 | 1 | 41845.3535 | 41862.7917 | 1 | 41863.3333 | 41892.3431 | 1 | 41892.3431 | 41936.4965 | 1 | 41936.4965 | 42013.5917 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4819 | 1 | 41753.375 | 41757.3917 | 1 | 41757.3917 | 41761.3819 | 1 | 41761.3819 | 41768.4285 | 1 | 41768.4285 | 41779.4819 | 1 | 41774.4333 | 41848.4167 | 1 | 41774.4333 | 41785.7917 | 1 | 41786.3333 | 41799.6215 | 1 | 41799.6215 | 41820.4132 | 1 | 41820.4132 | 41848.4167 | 1 | 41848.4167 | 41848.4167 | 1 | 41843.4931 | 42009.5951 | 1 | 41843.4931 | 41862.7917 | 1 | 41863.3333 | 41894.6486 | 1 | 41894.6486 | 41949.6319 | 1 | 41949.6319 | 42009.5951 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.425 | 1 | 41753.375 | 41757.425 | 1 | 41757.425 | 41761.4118 | 1 | 41761.4118 | 41768.4486 | 1 | 41768.4486 | 41779.425 | 1 | 41774.3868 | 41852.5986 | 1 | 41774.3868 | 41785.7917 | 1 | 41786.3333 | 41799.7014 | 1 | 41799.7014 | 41821.6285 | 1 | 41821.6285 | 41852.5986 | 1 | 41852.5986 | 41852.5986 | 1 | 41843.6514 | 42009.4535 | 1 | 41843.6514 | 41862.7917 | 1 | 41863.3333 | 41892.4097 | 1 | 41892.4097 | 41950.5986 | 1 | 41950.5986 | 42009.4535 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3451 | 1 | 41753.375 | 41757.4153 | 1 | 41757.4153 | 41761.5632 | 1 | 41761.5632 | 41768.5465 | 1 | 41768.5465 | 41780.3451 | 1 | 41774.4333 | 41851.6785 | 1 | 41774.4333 | 41785.7917 | 1 | 41786.3333 | 41800.5451 | 1 | 41800.5451 | 41822.6014 | 1 | 41822.6014 | 41851.6785 | 1 | 41851.6785 | 41851.6785 | 1 | 41845.3868 | 42017.4667 | 1 | 41845.3868 | 41862.7917 | 1 | 41863.3333 | 41897.5819 | 1 | 41897.5819 | 41941.4569 | 1 | 41941.4569 | 42017.4667 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.5736 | 1 | 41753.375 | 41757.4285 | 1 | 41757.4285 | 41764.3347 | 1 | 41764.3347 | 41771.3986 | 1 | 41771.3986 | 41780.5736 | 1 | 41774.6681 | 41848.4035 | 1 | 41774.6681 | 41785.7917 | 1 | 41786.3333 | 41800.4368 | 1 | 41800.4368 | 41821.4132 | 1 | 41821.4132 | 41848.4035 | 1 | 41848.4035 | 41848.4035 | 1 | 41848.6118 | 41996.4833 | 1 | 41848.6118 | 41862.7917 | 1 | 41863.3333 | 41891.45 | 1 | 41891.45 | 41939.35 | 1 | 41939.35 | 41996.4833 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.5965 | 1 | 41753.375 | 41757.375 | 1 | 41757.375 | 41760.6333 | 1 | 41760.6333 | 41767.5799 | 1 | 41767.5799 | 41778.5965 | 1 | 41774.4299 | 41850.3931 | 1 | 41774.4299 | 41785.7917 | 1 | 41786.3333 | 41800.35 | 1 | 41800.35 | 41817.6681 | 1 | 41817.6681 | 41850.3931 | 1 | 41850.3931 | 41850.3931 | 1 | 41844.5785 | 42009.4535 | 1 | 41844.5785 | 41862.7917 | 1 | 41863.3333 | 41898.5917 | 1 | 41898.5917 | 41950.5583 | 1 | 41950.5583 | 42009.4535 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3583 | 1 | 41753.375 | 41757.3486 | 1 | 41757.3486 | 41761.3549 | 1 | 41761.3549 | 41768.4319 | 1 | 41768.4319 | 41780.3583 | 1 | 41775.4 | 41856.5951 | 1 | 41775.4 | 41785.7917 | 1 | 41786.3333 | 41801.6917 | 1 | 41801.6917 | 41823.4167 | 1 | 41823.4167 | 41856.5951 | 1 | 41856.5951 | 41856.5951 | 1 | 41845.4632 | 42012.3736 | 1 | 41845.4632 | 41862.7917 | 1 | 41863.3333 | 41892.4333 | 1 | 41892.4333 | 41943.6549 | 1 | 41943.6549 | 42012.3736 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6264 | 1 | 41753.375 | 41757.3681 | 1 | 41757.3681 | 41761.5931 | 1 | 41761.5931 | 41768.6736 | 1 | 41768.6736 | 41780.6264 | 1 | 41774.5882 | 41852.6986 | 1 | 41774.5882 | 41785.7917 | 1 | 41786.3333 | 41800.5583 | 1 | 41800.5583 | 41822.5681 | 1 | 41822.5681 | 41852.6986 | 1 | 41852.6986 | 41852.6986 | 1 | 41849.3333 | 42005.4903 | 1 | 41849.3333 | 41862.7917 | 1 | 41863.3333 | 41897.5549 | 1 | 41897.5549 | 41946.3597 | 1 | 41946.3597 | 42005.4903 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6833 | 1 | 41753.375 | 41757.375 | 1 | 41757.375 | 41761.6403 | 1 | 41761.6403 | 41768.5965 | 1 | 41768.5965 | 41780.6833 | 1 | 41775.3965 | 41850.4 | 1 | 41775.3965 | 41785.7917 | 1 | 41786.3333 | 41800.6847 | 1 | 41800.6847 | 41822.5549 | 1 | 41822.5549 | 41850.4 | 1 | 41850.4 | 41850.4 | 1 | 41844.4069 | 42006.3403 | 1 | 41844.4069 | 41862.7917 | 1 | 41863.3333 | 41892.3403 | 1 | 41892.3403 | 41940.4132 | 1 | 41940.4132 | 42006.3403 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6535 | 1 | 41753.375 | 41757.4049 | 1 | 41757.4049 | 41761.6569 | 1 | 41761.6569 | 41768.6368 | 1 | 41768.6368 | 41779.6535 | 1 | 41774.4868 | 41848.3701 | 1 | 41774.4868 | 41785.7917 | 1 | 41786.3333 | 41799.6083 | 1 | 41799.6083 | 41821.4569 | 1 | 41821.4569 | 41848.3701 | 1 | 41848.3701 | 41848.3701 | 1 | 41842.6785 | 42010.4597 | 1 | 41842.6785 | 41862.7917 | 1 | 41863.3333 | 41892.5514 | 1 | 41892.5514 | 41941.4799 | 1 | 41941.4799 | 42010.4597 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3583 | 1 | 41753.375 | 41757.4083 | 1 | 41757.4083 | 41761.3951 | 1 | 41761.3951 | 41771.3382 | 1 | 41771.3382 | 41780.3583 | 1 | 41774.625 | 41851.5847 | 1 | 41774.625 | 41785.7917 | 1 | 41786.3333 | 41800.625 | 1 | 41800.625 | 41820.6986 | 1 | 41820.6986 | 41851.5847 | 1 | 41851.5847 | 41851.5847 | 1 | 41845.6347 | 41996.4299 | 1 | 41845.6347 | 41862.7917 | 1 | 41863.3333 | 41891.3597 | 1 | 41891.3597 | 41936.3431 | 1 | 41936.3431 | 41996.4299 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4514 | 1 | 41753.375 | 41757.3785 | 1 | 41757.3785 | 41761.4382 | 1 | 41761.4382 | 41768.5868 | 1 | 41768.5868 | 41779.4514 | 1 | 41774.4236 | 41851.6917 | 1 | 41774.4236 | 41785.7917 | 1 | 41786.3333 | 41799.5583 | 1 | 41799.5583 | 41822.6382 | 1 | 41822.6382 | 41851.6917 | 1 | 41851.6917 | 41851.6917 | 1 | 41845.4632 | 42002.6951 | 1 | 41845.4632 | 41862.7917 | 1 | 41863.3333 | 41892.5986 | 1 | 41892.5986 | 41940.4931 | 1 | 41940.4931 | 42002.6951 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3882 | 1 | 41753.375 | 41757.4882 | 1 | 41757.4882 | 41761.4847 | 1 | 41761.4847 | 41768.5903 | 1 | 41768.5903 | 41780.3882 | 1 | 41773.6986 | 41849.6986 | 1 | 41773.6986 | 41785.7917 | 1 | 41786.3333 | 41800.3465 | 1 | 41800.3465 | 41821.3403 | 1 | 41821.3403 | 41849.6986 | 1 | 41849.6986 | 41849.6986 | 1 | 41843.3431 | 42011.4465 | 1 | 41843.3431 | 41862.7917 | 1 | 41863.3333 | 41898.3736 | 1 | 41898.3736 | 41941.7014 | 1 | 41941.7014 | 42011.4465 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41781.3951 | 1 | 41753.375 | 41757.4486 | 1 | 41757.4486 | 41761.5667 | 1 | 41761.5667 | 41771.4014 | 1 | 41771.4014 | 41781.3951 | 1 | 41774.6451 | 41850.4465 | 1 | 41774.6451 | 41785.7917 | 1 | 41786.3333 | 41800.3368 | 1 | 41800.3368 | 41822.4 | 1 | 41822.4 | 41850.4465 | 1 | 41850.4465 | 41850.4465 | 1 | 41848.4333 | 42010.5882 | 1 | 41848.4333 | 41862.7917 | 1 | 41863.3333 | 41901.3632 | 1 | 41901.3632 | 41950.6319 | 1 | 41950.6319 | 42010.5882 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6299 | 1 | 41753.375 | 41757.375 | 1 | 41757.375 | 41760.6632 | 1 | 41760.6632 | 41768.6167 | 1 | 41768.6167 | 41779.6299 | 1 | 41774.6785 | 41850.4903 | 1 | 41774.6785 | 41785.7917 | 1 | 41786.3333 | 41799.6583 | 1 | 41799.6583 | 41821.6653 | 1 | 41821.6653 | 41850.4903 | 1 | 41850.4903 | 41850.4903 | 1 | 41845.6583 | 42004.4931 | 1 | 41845.6583 | 41862.7917 | 1 | 41863.3333 | 41899.6882 | 1 | 41899.6882 | 41948.3569 | 1 | 41948.3569 | 42004.4931 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6903 | 1 | 41753.375 | 41757.3486 | 1 | 41757.3486 | 41761.4417 | 1 | 41761.4417 | 41768.6903 | 1 | 41768.6903 | 41779.6903 | 1 | 41774.3736 | 41849.5583 | 1 | 41774.3736 | 41785.7917 | 1 | 41786.3333 | 41800.6785 | 1 | 41800.6785 | 41821.5917 | 1 | 41821.5917 | 41849.5583 | 1 | 41849.5583 | 41849.5583 | 1 | 41848.6153 | 42016.5 | 1 | 41848.6153 | 41862.7917 | 1 | 41863.3333 | 41893.6986 | 1 | 41893.6986 | 41936.6819 | 1 | 41936.6819 | 42016.5 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6035 | 1 | 41753.375 | 41757.4014 | 1 | 41757.4014 | 41761.6569 | 1 | 41761.6569 | 41771.4486 | 1 | 41771.4486 | 41779.6035 | 1 | 41775.3569 | 41850.5451 | 1 | 41775.3569 | 41785.7917 | 1 | 41786.3333 | 41800.6181 | 1 | 41800.6181 | 41821.5653 | 1 | 41821.5653 | 41850.5451 | 1 | 41850.5451 | 41850.5451 | 1 | 41848.4868 | 42033.575 | 1 | 41848.4868 | 41862.7917 | 1 | 41863.3333 | 41904.4868 | 1 | 41904.4868 | 41957.4299 | 1 | 41957.4299 | 42033.575 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6132 | 1 | 41753.375 | 41757.3583 | 1 | 41757.3583 | 41761.3785 | 1 | 41761.3785 | 41768.3583 | 1 | 41768.3583 | 41778.6132 | 1 | 41775.4965 | 41851.625 | 1 | 41775.4965 | 41785.7917 | 1 | 41786.3333 | 41799.5917 | 1 | 41799.5917 | 41821.6285 | 1 | 41821.6285 | 41851.625 | 1 | 41851.625 | 41851.625 | 1 | 41848.35 | 42005.6681 | 1 | 41848.35 | 41862.7917 | 1 | 41863.3333 | 41898.675 | 1 | 41898.675 | 41947.5785 | 1 | 41947.5785 | 42005.6681 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6264 | 1 | 41753.375 | 41757.3986 | 1 | 41757.3986 | 41761.3715 | 1 | 41761.3715 | 41767.6264 | 1 | 41767.6264 | 41778.6264 | 1 | 41774.5618 | 41850.4167 | 1 | 41774.5618 | 41785.7917 | 1 | 41786.3333 | 41800.5917 | 1 | 41800.5917 | 41821.5653 | 1 | 41821.5653 | 41850.4167 | 1 | 41850.4167 | 41850.4167 | 1 | 41844.3431 | 41991.6347 | 1 | 41844.3431 | 41862.7917 | 1 | 41863.3333 | 41892.6118 | 1 | 41892.6118 | 41935.35 | 1 | 41935.35 | 41991.6347 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4549 | 1 | 41753.375 | 41757.4153 | 1 | 41757.4153 | 41761.65 | 1 | 41761.65 | 41771.4549 | 1 | 41771.4549 | 41780.4549 | 1 | 41775.3403 | 41851.3799 | 1 | 41775.3403 | 41785.7917 | 1 | 41786.3333 | 41799.5819 | 1 | 41799.5819 | 41820.5785 | 1 | 41820.5785 | 41851.3799 | 1 | 41851.3799 | 41851.3799 | 1 | 41845.3465 | 42013.4 | 1 | 41845.3465 | 41862.7917 | 1 | 41863.3333 | 41897.4903 | 1 | 41897.4903 | 41947.3368 | 1 | 41947.3368 | 42013.4 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6368 | 1 | 41753.375 | 41757.4681 | 1 | 41757.4681 | 41761.5632 | 1 | 41761.5632 | 41768.6132 | 1 | 41768.6132 | 41779.6368 | 1 | 41774.4 | 41850.4465 | 1 | 41774.4 | 41785.7917 | 1 | 41786.3333 | 41800.3931 | 1 | 41800.3931 | 41821.6049 | 1 | 41821.6049 | 41850.4465 | 1 | 41850.4465 | 41850.4465 | 1 | 41848.6181 | 42018.4167 | 1 | 41848.6181 | 41862.7917 | 1 | 41863.3333 | 41893.6819 | 1 | 41893.6819 | 41942.675 | 1 | 41942.675 | 42018.4167 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4715 | 1 | 41753.375 | 41757.375 | 1 | 41757.375 | 41761.5833 | 1 | 41761.5833 | 41771.3549 | 1 | 41771.3549 | 41780.4715 | 1 | 41775.4132 | 41848.5917 | 1 | 41775.4132 | 41785.7917 | 1 | 41786.3333 | 41800.3535 | 1 | 41800.3535 | 41820.5785 | 1 | 41820.5785 | 41848.5917 | 1 | 41848.5917 | 41848.5917 | 1 | 41848.3403 | 42019.3868 | 1 | 41848.3403 | 41862.7917 | 1 | 41863.3333 | 41904.6653 | 1 | 41904.6653 | 41957.4736 | 1 | 41957.4736 | 42019.3868 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6799 | 1 | 41753.375 | 41757.3785 | 1 | 41757.3785 | 41761.4347 | 1 | 41761.4347 | 41768.5799 | 1 | 41768.5799 | 41779.6799 | 1 | 41775.4167 | 41848.6951 | 1 | 41775.4167 | 41785.7917 | 1 | 41786.3333 | 41800.3833 | 1 | 41800.3833 | 41820.5451 | 1 | 41820.5451 | 41848.6951 | 1 | 41848.6951 | 41848.6951 | 1 | 41843.5486 | 42017.3868 | 1 | 41843.5486 | 41862.7917 | 1 | 41863.3333 | 41891.5 | 1 | 41891.5417 | 41936.4535 | 1 | 41936.4535 | 42017.3868 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6333 | 1 | 41753.375 | 41757.4083 | 1 | 41757.4083 | 41761.3785 | 1 | 41761.3785 | 41768.3917 | 1 | 41768.3917 | 41779.6333 | 1 | 41774.4097 | 41848.45 | 1 | 41774.4097 | 41785.7917 | 1 | 41786.3333 | 41799.6049 | 1 | 41799.6049 | 41820.4465 | 1 | 41820.4465 | 41848.45 | 1 | 41848.45 | 41848.45 | 1 | 41843.3597 | 42026.6653 | 1 | 41843.3597 | 41862.7917 | 1 | 41863.3333 | 41894.4431 | 1 | 41894.4431 | 41949.4736 | 1 | 41949.4736 | 42026.6653 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5431 | 1 | 41753.375 | 41757.4451 | 1 | 41757.4451 | 41761.6368 | 1 | 41761.6368 | 41771.3653 | 1 | 41771.3653 | 41779.5431 | 1 | 41775.3465 | 41849.6951 | 1 | 41775.3465 | 41785.7917 | 1 | 41786.3333 | 41800.5486 | 1 | 41800.5486 | 41821.6347 | 1 | 41821.6347 | 41849.6951 | 1 | 41849.6951 | 41849.6951 | 1 | 41844.6319 | 42025.3903 | 1 | 41844.6319 | 41862.7917 | 1 | 41863.3333 | 41897.7049 | 1 | 41897.7049 | 41948.5 | 1 | 41948.5417 | 42025.3903 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3819 | 1 | 41753.375 | 41757.3951 | 1 | 41757.3951 | 41761.5868 | 1 | 41761.5868 | 41771.375 | 1 | 41771.375 | 41780.3819 | 1 | 41775.3403 | 41848.6549 | 1 | 41775.3403 | 41785.7917 | 1 | 41786.3333 | 41799.4236 | 1 | 41799.4236 | 41822.3764 | 1 | 41822.3764 | 41848.6549 | 1 | 41848.6549 | 41848.6549 | 1 | 41844.5618 | 42002.7083 | 1 | 41844.5618 | 41862.7917 | 1 | 41863.3333 | 41899.4097 | 1 | 41899.4097 | 41942.3431 | 1 | 41942.3431 | 42002.7083 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5799 | 1 | 41753.375 | 41757.4049 | 1 | 41757.4049 | 41761.3618 | 1 | 41761.3618 | 41768.5931 | 1 | 41768.5931 | 41779.5799 | 1 | 41775.3403 | 41850.4 | 1 | 41775.3403 | 41785.7917 | 1 | 41786.3333 | 41800.3701 | 1 | 41800.3701 | 41822.4465 | 1 | 41822.4465 | 41850.4 | 1 | 41850.4 | 41850.4 | 1 | 41848.5819 | 42010.6049 | 1 | 41848.5819 | 41862.7917 | 1 | 41863.3333 | 41904.4035 | 1 | 41904.4035 | 41948.4264 | 1 | 41948.4264 | 42010.6049 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3819 | 1 | 41753.375 | 41757.4285 | 1 | 41757.4285 | 41761.4951 | 1 | 41761.4951 | 41768.3951 | 1 | 41768.3951 | 41779.3819 | 1 | 41774.5549 | 41845.4597 | 1 | 41774.5549 | 41785.7917 | 1 | 41786.3333 | 41799.6653 | 1 | 41799.6653 | 41817.7049 | 1 | 41817.7049 | 41845.4597 | 1 | 41845.4597 | 41845.4597 | 1 | 41843.6347 | 42012.6118 | 1 | 41843.6347 | 41862.7917 | 1 | 41863.3333 | 41894.675 | 1 | 41894.675 | 41943.6681 | 1 | 41943.6681 | 42012.6118 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3583 | 1 | 41753.375 | 41757.4486 | 1 | 41757.4486 | 41761.5799 | 1 | 41761.5799 | 41768.6799 | 1 | 41768.6799 | 41780.3583 | 1 | 41774.6681 | 41850.4431 | 1 | 41774.6681 | 41785.7917 | 1 | 41786.3333 | 41799.6785 | 1 | 41799.6785 | 41822.4368 | 1 | 41822.4368 | 41850.4431 | 1 | 41850.4431 | 41850.4431 | 1 | 41845.4597 | 42016.3465 | 1 | 41845.4597 | 41862.7917 | 1 | 41863.3333 | 41894.6181 | 1 | 41894.6181 | 41949.6785 | 1 | 41949.6785 | 42016.3465 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4417 | 1 | 41753.375 | 41757.3486 | 1 | 41757.3486 | 41760.6903 | 1 | 41760.6903 | 41767.6965 | 1 | 41767.6965 | 41779.4417 | 1 | 41774.6514 | 41850.3368 | 1 | 41774.6514 | 41785.7917 | 1 | 41786.3333 | 41799.5917 | 1 | 41799.5917 | 41821.3931 | 1 | 41821.3931 | 41850.3368 | 1 | 41850.3368 | 41850.3368 | 1 | 41844.4201 | 42031.3368 | 1 | 41844.4201 | 41862.7917 | 1 | 41863.3333 | 41899.3868 | 1 | 41899.3868 | 41953.4167 | 1 | 41953.4167 | 42031.3368 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5833 | 1 | 41753.375 | 41757.3951 | 1 | 41757.3951 | 41761.6736 | 1 | 41761.6736 | 41768.7069 | 1 | 41768.7069 | 41779.5833 | 1 | 41774.6014 | 41848.6347 | 1 | 41774.6014 | 41785.7917 | 1 | 41786.3333 | 41800.35 | 1 | 41800.35 | 41821.5451 | 1 | 41821.5451 | 41848.6347 | 1 | 41848.6347 | 41848.6347 | 1 | 41848.4764 | 42023.675 | 1 | 41848.4764 | 41862.7917 | 1 | 41863.3333 | 41892.4868 | 1 | 41892.4868 | 41946.6549 | 1 | 41946.6549 | 42023.675 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4583 | 1 | 41753.375 | 41757.4181 | 1 | 41757.4181 | 41761.3986 | 1 | 41761.3986 | 41768.5764 | 1 | 41768.5764 | 41779.4583 | 1 | 41774.4069 | 41849.4701 | 1 | 41774.4069 | 41785.7917 | 1 | 41786.3333 | 41799.6819 | 1 | 41799.6819 | 41822.4167 | 1 | 41822.4167 | 41849.4701 | 1 | 41849.4701 | 41849.4701 | 1 | 41844.4667 | 42011.6618 | 1 | 41844.4667 | 41862.7917 | 1 | 41863.3333 | 41900.3799 | 1 | 41900.3799 | 41949.6986 | 1 | 41949.6986 | 42011.6618 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41778.6903 | 1 | 41753.375 | 41754.6931 | 1 | 41754.6931 | 41761.4014 | 1 | 41761.4014 | 41768.4549 | 1 | 41768.4549 | 41778.6903 | 1 | 41775.3931 | 41851.6715 | 1 | 41775.3931 | 41785.7917 | 1 | 41786.3333 | 41800.7049 | 1 | 41800.7049 | 41821.7049 | 1 | 41821.7049 | 41851.6715 | 1 | 41851.6715 | 41851.6715 | 1 | 41845.6653 | 42009.4201 | 1 | 41845.6653 | 41862.7917 | 1 | 41863.3333 | 41899.4403 | 1 | 41899.4403 | 41953.4 | 1 | 41953.4 | 42009.4201 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6465 | 1 | 41753.375 | 41757.4118 | 1 | 41757.4118 | 41761.3819 | 1 | 41761.3819 | 41768.4451 | 1 | 41768.4451 | 41779.6465 | 1 | 41774.4701 | 41848.6715 | 1 | 41774.4701 | 41785.7917 | 1 | 41786.3333 | 41799.4667 | 1 | 41799.4667 | 41820.5986 | 1 | 41820.5986 | 41848.6715 | 1 | 41848.6715 | 41848.6715 | 1 | 41844.3701 | 42016.3903 | 1 | 41844.3701 | 41862.7917 | 1 | 41863.3333 | 41897.3701 | 1 | 41897.3701 | 41949.4465 | 1 | 41949.4465 | 42016.3903 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4486 | 1 | 41753.375 | 41757.4417 | 1 | 41757.4417 | 41761.4382 | 1 | 41761.4382 | 41768.4618 | 1 | 41768.4618 | 41779.4486 | 1 | 41774.4931 | 41845.5486 | 1 | 41774.4931 | 41785.7917 | 1 | 41786.3333 | 41799.5785 | 1 | 41799.5785 | 41820.6618 | 1 | 41820.6618 | 41845.5486 | 1 | 41845.5486 | 41845.5486 | 1 | 41848.6618 | 42005.3965 | 1 | 41848.6618 | 41862.7917 | 1 | 41863.3333 | 41894.35 | 1 | 41894.35 | 41939.3965 | 1 | 41939.3965 | 42005.3965 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4715 | 1 | 41753.375 | 41757.4319 | 1 | 41757.4319 | 41761.5667 | 1 | 41761.5667 | 41768.4514 | 1 | 41768.4514 | 41779.4715 | 1 | 41774.4764 | 41851.3736 | 1 | 41774.4764 | 41785.7917 | 1 | 41786.3333 | 41799.6514 | 1 | 41799.6514 | 41820.4931 | 1 | 41820.4931 | 41851.3736 | 1 | 41851.3736 | 41851.3736 | 1 | 41844.4465 | 42020.6653 | 1 | 41844.4465 | 41862.7917 | 1 | 41863.3333 | 41892.5715 | 1 | 41892.5715 | 41949.4833 | 1 | 41949.4833 | 42020.6653 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6764 | 1 | 41753.375 | 41757.4181 | 1 | 41757.4181 | 41761.6403 | 1 | 41761.6403 | 41768.6403 | 1 | 41768.6403 | 41779.6764 | 1 | 41775.3799 | 41850.5785 | 1 | 41775.3799 | 41785.7917 | 1 | 41786.3333 | 41799.6486 | 1 | 41799.6486 | 41821.6819 | 1 | 41821.6819 | 41850.5785 | 1 | 41850.5785 | 41850.5785 | 1 | 41842.6986 | 42017.6417 | 1 | 41842.6986 | 41862.7917 | 1 | 41863.3333 | 41891.4236 | 1 | 41891.4236 | 41939.675 | 1 | 41939.675 | 42017.6417 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4986 | 1 | 41753.375 | 41757.4049 | 1 | 41757.4049 | 41761.4451 | 1 | 41761.4451 | 41768.6868 | 1 | 41768.6868 | 41780.4986 | 1 | 41774.5653 | 41850.6486 | 1 | 41774.5653 | 41785.7917 | 1 | 41786.3333 | 41799.6514 | 1 | 41799.6514 | 41820.6882 | 1 | 41820.6882 | 41850.6486 | 1 | 41850.6486 | 41850.6486 | 1 | 41845.6014 | 42018.5715 | 1 | 41845.6014 | 41862.7917 | 1 | 41863.3333 | 41893.4701 | 1 | 41893.4701 | 41943.3431 | 1 | 41943.3431 | 42018.5715 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.5632 | 1 | 41753.375 | 41757.3917 | 1 | 41757.3917 | 41761.65 | 1 | 41761.65 | 41771.4681 | 1 | 41771.4681 | 41780.5632 | 1 | 41775.3403 | 41845.45 | 1 | 41775.3403 | 41785.7917 | 1 | 41786.3333 | 41799.5549 | 1 | 41799.5549 | 41820.5847 | 1 | 41820.5847 | 41845.45 | 1 | 41845.45 | 41845.45 | 1 | 41845.6917 | 41999.3833 | 1 | 41845.6917 | 41862.7917 | 1 | 41863.3333 | 41892.6319 | 1 | 41892.6319 | 41936.6951 | 1 | 41936.6951 | 41999.3833 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3514 | 1 | 41753.375 | 41757.3917 | 1 | 41757.3917 | 41761.3514 | 1 | 41761.3514 | 41767.6535 | 1 | 41767.6535 | 41779.3514 | 1 | 41774.6583 | 41850.6681 | 1 | 41774.6583 | 41785.7917 | 1 | 41786.3333 | 41801.4965 | 1 | 41801.4965 | 41822.4799 | 1 | 41822.4799 | 41850.6681 | 1 | 41850.6681 | 41850.6681 | 1 | 41842.6486 | 42023.3535 | 1 | 41842.6486 | 41862.7917 | 1 | 41863.3333 | 41897.6181 | 1 | 41897.6181 | 41957.3931 | 1 | 41957.3931 | 42023.3535 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.3618 | 1 | 41753.375 | 41754.7035 | 1 | 41754.7035 | 41761.4785 | 1 | 41761.4785 | 41771.3514 | 1 | 41771.3514 | 41780.3618 | 1 | 41774.3597 | 41855.3368 | 1 | 41774.3597 | 41785.7917 | 1 | 41786.3333 | 41801.4403 | 1 | 41801.4403 | 41822.4632 | 1 | 41822.4632 | 41855.3368 | 1 | 41855.3368 | 41855.3368 | 1 | 41848.4465 | 42010.4736 | 1 | 41848.4465 | 41862.7917 | 1 | 41863.3333 | 41891.3368 | 1 | 41891.3368 | 41943.5819 | 1 | 41943.5819 | 42010.4736 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4049 | 1 | 41753.375 | 41757.4514 | 1 | 41757.4514 | 41761.4285 | 1 | 41761.4285 | 41768.4319 | 1 | 41768.4319 | 41779.4049 | 1 | 41775.3368 | 41849.6951 | 1 | 41775.3368 | 41785.7917 | 1 | 41786.3333 | 41799.6583 | 1 | 41799.6583 | 41821.5847 | 1 | 41821.5847 | 41849.6951 | 1 | 41849.6951 | 41849.6951 | 1 | 41845.5951 | 42004.6285 | 1 | 41845.5951 | 41862.7917 | 1 | 41863.3333 | 41892.3632 | 1 | 41892.3632 | 41941.5618 | 1 | 41941.5618 | 42004.6285 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.3882 | 1 | 41753.375 | 41757.3618 | 1 | 41757.3618 | 41760.6833 | 1 | 41760.6833 | 41768.4583 | 1 | 41768.4583 | 41779.3882 | 1 | 41775.3903 | 41845.6118 | 1 | 41775.3903 | 41785.7917 | 1 | 41786.3333 | 41800.6785 | 1 | 41800.6785 | 41821.5986 | 1 | 41821.5986 | 41845.6118 | 1 | 41845.6118 | 41845.6118 | 1 | 41845.3368 | 42013.3965 | 1 | 41845.3368 | 41862.7917 | 1 | 41863.3333 | 41892.6181 | 1 | 41892.6181 | 41948.6819 | 1 | 41948.6819 | 42013.3965 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.5535 | 1 | 41753.375 | 41757.4215 | 1 | 41757.4215 | 41761.3819 | 1 | 41761.3819 | 41767.6799 | 1 | 41767.6799 | 41779.5535 | 1 | 41775.5583 | 41849.3569 | 1 | 41775.5583 | 41785.7917 | 1 | 41786.3333 | 41801.4701 | 1 | 41801.4701 | 41822.4264 | 1 | 41822.4264 | 41849.3569 | 1 | 41849.3569 | 41849.3569 | 1 | 41848.4035 | 41996.5847 | 1 | 41848.4035 | 41862.7917 | 1 | 41863.3333 | 41897.4368 | 1 | 41897.4368 | 41939.6382 | 1 | 41939.6382 | 41996.5847 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6132 | 1 | 41753.375 | 41757.3681 | 1 | 41757.3681 | 41761.425 | 1 | 41761.425 | 41768.5632 | 1 | 41768.5632 | 41779.6132 | 1 | 41774.575 | 41851.4465 | 1 | 41774.575 | 41785.7917 | 1 | 41786.3333 | 41799.6153 | 1 | 41799.6153 | 41820.5819 | 1 | 41820.5819 | 41851.4465 | 1 | 41851.4465 | 41851.4465 | 1 | 41845.4701 | 41996.4465 | 1 | 41845.4701 | 41862.7917 | 1 | 41863.3333 | 41894.4201 | 1 | 41894.4201 | 41939.6653 | 1 | 41939.6653 | 41996.4465 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6097 | 1 | 41753.375 | 41757.4083 | 1 | 41757.4083 | 41761.3882 | 1 | 41761.3882 | 41768.65 | 1 | 41768.65 | 41779.6097 | 1 | 41774.3931 | 41851.3868 | 1 | 41774.3931 | 41785.7917 | 1 | 41786.3333 | 41801.3535 | 1 | 41801.3535 | 41822.3701 | 1 | 41822.3701 | 41851.3868 | 1 | 41851.3868 | 41851.3868 | 1 | 41845.6549 | 42004.4132 | 1 | 41845.6549 | 41862.7917 | 1 | 41863.3333 | 41892.5583 | 1 | 41892.5583 | 41947.4201 | 1 | 41947.4201 | 42004.4132 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.4785 | 1 | 41753.375 | 41757.3715 | 1 | 41757.3715 | 41760.6333 | 1 | 41760.6333 | 41768.3951 | 1 | 41768.3951 | 41779.4785 | 1 | 41774.4069 | 41850.4965 | 1 | 41774.4069 | 41785.7917 | 1 | 41786.3333 | 41800.3764 | 1 | 41800.3764 | 41817.7014 | 1 | 41817.7014 | 41850.4965 | 1 | 41850.4965 | 41850.4965 | 1 | 41842.6681 | 42003.6819 | 1 | 41842.6681 | 41862.7917 | 1 | 41863.3333 | 41899.6486 | 1 | 41899.6486 | 41946.5847 | 1 | 41946.5847 | 42003.6819 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.6368 | 1 | 41753.375 | 41757.3785 | 1 | 41757.3785 | 41761.5597 | 1 | 41761.5597 | 41771.4014 | 1 | 41771.4014 | 41780.6368 | 1 | 41774.5847 | 41852.3868 | 1 | 41774.5847 | 41785.7917 | 1 | 41786.3333 | 41800.6285 | 1 | 41800.6285 | 41822.4965 | 1 | 41822.4965 | 41852.3868 | 1 | 41852.3868 | 41852.3868 | 1 | 41845.5451 | 41998.5451 | 1 | 41845.5451 | 41862.7917 | 1 | 41863.3333 | 41898.4236 | 1 | 41898.4236 | 41942.3833 | 1 | 41942.3833 | 41998.5451 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41779.6736 | 1 | 41753.375 | 41757.3451 | 1 | 41757.3451 | 41761.5736 | 1 | 41761.5736 | 41771.4014 | 1 | 41771.4014 | 41779.6736 | 1 | 41775.3931 | 41850.3465 | 1 | 41775.3931 | 41785.7917 | 1 | 41786.3333 | 41800.6382 | 1 | 41800.6382 | 41821.6083 | 1 | 41821.6083 | 41850.3465 | 1 | 41850.3465 | 41850.3465 | 1 | 41844.6215 | 42004.6118 | 1 | 41844.6215 | 41862.7917 | 1 | 41863.3333 | 41897.4535 | 1 | 41897.4535 | 41948.4264 | 1 | 41948.4264 | 42004.6118 | 1
41751.375 | 41753.375 | 1 | 41753.375 | 41780.4583 | 1 | 41753.375 | 41757.4819 | 1 | 41757.4819 | 41761.6132 | 1 | 41761.6132 | 41771.5965 | 1 | 41771.5965 | 41780.4583 | 1 | 41775.4035 | 41849.6681 | 1 | 41775.4035 | 41785.7917 | 1 | 41786.3333 | 41799.6917 | 1 | 41799.6917 | 41821.3868 | 1 | 41821.3868 | 41849.6681 | 1 | 41849.6681 | 41849.6681 | 1 | 41844.4597 | 42003.6583 | 1 | 41844.4597 | 41862.7917 | 1 | 41863.3333 | 41894.6986 | 1 | 41894.6986 | 41941.6486 | 1 | 41941.6486 | 42003.6583 | 1
Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1 | Sim#1